## Opportunity RA
|  |  |  | Opporunity Levels | [9 empty] | Comments, notes, explanation, Plan of Action
Risk Reg Ref No |  | Owner | Description | Performance | Reputational | Financial | Operational | Highest Score | Probability level | Opportunity Level | Plan | Date Entered | Reviewed Date | Comments, notes, explanation, Plan of Action
| Unique Risk Ref | [13 empty] | 1 | Accept | N/A | 2 | 4 | 8 | 12 | 16
OP_003 |  | CEO | The cloud | 100 | 1000 | 1000 | 1 | 1000 | 12 | 12000 | Pursue | 2016-03-01 | 2017-06-03 | New Customer " Andrew" Intility Largest Cloud provider Norway | 3 | Avoid | Accept | Transfer | Avoid | Control |  |  | N/A | 2 | 4 | 8 | 12 | 16
OP_005 |  | CEO | Expansion to Denmark | 100 | 1000 | 1000 | 5 | 1000 | 12 | 12000 | Competed | 2016-03-01 | 2017-06-13 | Completed Mar 2018 | [9 empty] | 1 | 5 | 20 | 100 | 1000
OP_007 |  | Head of Operations | Expand AVS Services | 20 | 20 | 1000 | 20 | 1000 | 12 | 12000 | Pursue | 2016-03-01 | 2017-05-31 | ELT Strategic Programme 2017 | [8 empty] | Pursue | Monitor | Avoid
OP_008 |  | CEO | Attract global customers | 100 | 100 | 1000 | 20 | 1000 | 12 | 12000 | Pursue | 2016-03-01 | 2017-05-01 | Sales Pipeline , Marketing Strategy
OP_014 |  | CCO | Expansion DNAS level 3 | 100 | 100 | 1000 | 5 | 1000 | 12 | 12000 | Pursue | 2018-01-01 | 2018-03-01 | Ongoing- Operational August
OP_015 |  | CCO | Expansion DRAS level 2 | 100 | 100 | 1000 | 5 | 1000 | 12 | 12000 | Pursue | 2018-01-01 | 2018-04-01 | Ongoing- Operational July
OP_006 |  | CDO | Expand MMR Business (Point of Presence for Carriers) | 100 | 100 | 1000 | 5 | 1000 | 8 | 8000 | Pursue | 2016-03-01 | 2017-05-31 | Implemented in Sweden
OP_010 |  | HR | Developing Competent People | 100 | 100 | 100 | 1000 | 1000 | 8 | 8000 | Closed | 2016-03-01 | 2017-05-01 | Hogan Assessments , ELT Workouts
OP_013 |  | CCO | Expansion DFAS 2 | 100 | 100 | 1000 | 5 | 1000 | 8 | 8000 | Pursue | 2018-01-08 | 2018-02-01 | Project " William "
OP_018 |  | CCO | Expansion of DS2 | 100 | 100 | 1000 | 5 | 1000 | 8 | 8000 | Pursue | 2018-01-01 | 2018-07-01 | Project George
OP_001 | URR_001 | CEO | EU-U.S Privacy Shield | 100 | 100 | 20 | 1 | 100 | 12 | 1200 | Monitor | 2016-03-01 | 2017-06-13 | GDPR
OP_011 |  | Head of Operations | Community Development Around (DNAS) (DRAS) (DS1) = Transfer Heat to Melt Roads/ Paths | 20 | 100 | 20 | 20 | 100 | 8 | 800 | Closed | 2016-03-01 | 2017-05-01 | District Heating Project
OP_012 |  | CDO | Rain Harvesting Improvements DS1 | 100 | 100 | 20 | 20 | 100 | 8 | 800 | Pursue | 2017-06-01 | 2018-06-01 | Project " Cameron"
OP_016 |  | CCO | GDPR | 100 | 100 | 20 | 5 | 100 | 4 | 400 | Closed | 2018-01-01 | 2018-05-01 | Communicating as a Driver
OP_002 |  | FD | Energy tax relief | 5 | 1 | 20 | 1 | 20 | 12 | 240 | Completed | 2016-03-01 | 2017-06-13 | Obtained Energy Tax relief ( 0.5 Mw) for DNAS DRAS
OP_017 | URR_004 | CCO | Brexit- Customer Leaving UK | 100 | 100 | 20 | 1 | 100 | 2 | 200 | Monitor | 2018-01-01 | 2018-06-01 | Very little impact likely to move to Germany/ Ireland
OP_009 | URR_002 | CMO | Advisory Services - Market Intelligence | 20 | 20 | 5 | 20 | 20 | 8 | 160 | Monitor | 2016-03-01 | 2017-05-01
OP_004 |  | CEO | Expansion to Finland | 20 | 20 | 20 | 5 | 20 | 4 | 80 | Monitor | 2016-03-01 | 2017-06-13
OP-019 |  | CDO | Deploy Lessons Learnt form DFAS | 20 | 100 | 100 | 20 | 20 | 4 | 80 | Completed | 2018-03-01 | Spet -18 | Moved from Risk Register Mar 18 | 4 | Control
5

## RiSK Tool
[9 empty] | Impact Scores | [10 empty] | Risk Level Goal
Differentiator | Risk No. | Unique Identity | Risk Level | Risk Reg Ref No |  | Risk | Risk Owner | Description | Performance | Reputational | Financial | Operational | Legal | Highest Score | Probability level | Risk Level | Existing Control Measures | Document Reference | Additional Controls required | Probability level | Impact Score | Risk Level | Risk Treatment Plan | Date Added | Risk Treated Date | Last Risk Review Date | Comments, notes, explanation, Plan of Action
#VALUE! |  | #VALUE! |  | RA_001 | URR_001 | People | HR | Key Leadership Team Staff Retention | 100 | 5 | 100 | 20 | 20 | 100 | 4 | 400 | Personnel Development plan Appraisal Talk process description | Appraisal Talk process description |  | 4 | 100 | 400 | Accept | 2015-05-06 |  | 2018-03-01 |  | 1 | Accept | N/A | 2 | 4 | 8 | 12 | 16
#VALUE! |  | #VALUE! |  | RA_002 |  | People | HR | Key Employee Staff Retention | 100 | 20 | 100 | 5 | 1 | 100 | 16 | 1600 | Personnel Development plan Appraisal Talk process description | Appraisal Talk process description | Development of a Retention scheme that will be which will be in place over the summer. Also recalibrated contracts on key employees. | 8 | 100 | 800 | Mitigate | 2015-05-06 |  | 2019-01-01 |  |  |  |  | 1 | 5 | 20 | 100 | 1000
|  |  |  | RA_003 |  |  | Head of Security | Physical Risk -Unauthorised Access/entry DNAS | 100 | 100 | 100 | 1000 | 100 | 1000 | 2 | 2000 | Access Control, Onsite Security , Alarms, CCTV Security Perimeter Fence | RTV | Considering Central Services for Security Run from DS1 - Update 04072017- Project underway to set up SOC in Stockholm |  |  |  | Tolerate | 2019-01-01 |  | Jul_19
|  |  |  | RA_004 |  |  | Head of Security | Physical Risk -Unauthorised Access/enrty DRAS | 100 | 100 | 100 | 1000 | 100 | 1000 | 16 | 16000 | Access Control Alarms CCTV | RTV | Develop Plan - Physical & Technical. Steinar to fact find with Customer on Perception and understand Customer Requirements Untrained Reception Staff, No Onsite Secuity provided by landlord |  |  |  | Treat | 2019-01-01 |  | Jul_19
|  |  |  | RA_005 |  |  | Head of Security | Physical Risk -Unauthorised Access/entry DFAS | 100 | 100 | 20 | 1000 | 100 | 1000 | 2 | 2000 | Access Control, Onsite Security , Alarms, CCTV Security Perimeter Fence | RTV | Considering Central Services for Security Run from DS1 - Update 04072017- Project underway to set up SOC in Stockholm |  |  |  | Tolerate | 2019-01-01 |  | Jul_19
|  |  |  | RA_006 |  |  | Head of Security | Physical Risk -Threat , Guarding- DS1 | 100 | 100 | 20 | 1000 | 100 | 1000 | 2 | 2000 | Access Control, Onsite Security , Alarms, CCTV Security Double Perimeter Fence | RTV |  |  |  |  | Tolerate | 2019-01-01 |  | Jul_19
#VALUE! |  | #VALUE! |  | RA_007 |  | Security | Head of Security | Physical Risk -Threat , Guarding - DC1 | 100 | 100 | 100 | 1000 | 100 | 1000 | 12 | 12000 | Access Control, Monitored Security , Alarms, Some CCTV Security Partial Perimeter Fence Security enhancement specifications available Security costs available - considered excessive based on DC1 existing customer base | RTV | Replace Access Control System Extend CCTV coverage Install new perimeter fence | 4 | 1000 | 4000 | Treat | 2018-05-06 |  | Jul_19
#VALUE! |  | #VALUE! |  | RA_008 |  | Operational | CDO | Project Management Capacity -Fai cf3lure to deliver large projects, Project Control Linked to Risk RA-022 | 100 | 100 | 1000 | 5 | 100 | 1000 | 4 | 4000 | Steering Committee Meetings Appointment of CDO,Recruitment of QS, and Project Team Robust processes employed CPS to PM larger contract works | Minutes from SCM | First Party Contractors - QS Capability- Costing of a Project at start. First Party QS to monitor | 4 | 1000 | 4000 | Mitigate | 2015-05-06 |  | 2019-01-01
#VALUE! |  | #VALUE! |  | RA_009 |  | Operational | IT Director | End User- * Laptops | 100 | 100 | 5 | 100 | 5 | 100 | 4 | 400 | Manged by Device as a Service |  | Deploy WEB protection - Oct-19 | 4 | 100 | 400 | Accept | 2018-09-18 |  | 2019-01-01 | RTV reworked. Next forming to action plan | 3 | Avoid | Accept | Transfer | Avoid | Control
|  |  |  | RA_010 |  |  | IT Director | End User- * Desktops (OPS / datacenter) | 100 | 1000 | 100 | 100 | 5 | 1000 | 4 | 4000 | unmanaged |  | Managed by DaaS project all sites 01/04/2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_011 |  |  | IT Director | End User- *Mobile | 100 | 100 | 5 | 100 | 5 | 100 | 4 | 400 | unmanaged |  | Deploy DaaS & Checkpoint Secure Mobile -Feb 2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_012 |  |  | IT Director | Cloud-* Office365 | 100 | 100 | 5 | 100 | 5 | 100 | 4 | 400 | Admin security hardening Information classificcation and hardening |  | O365 hardening Oct-18 Roll out infomation classification 30/04/2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_013 |  |  | IT Director | Cloud-* ServiceNow | 100 | 100 | 5 | 100 | 5 | 100 | 4 | 400 |  |  | External users admin framework Define process and requirements- Nov-18 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_014 |  |  | IT Director | Cloud-* SalesForce | 100 | 100 | 5 | 100 | 5 | 100 | 4 | 400 |  |  | Activate SSO with Azure AD target date 01/04/2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_015 |  |  | IT Director | Cloud-* Xledger | 100 | 100 | 5 | 100 | 5 | 100 | 4 | 400 | Satisifactory | [5 empty] | Accept | 2018-09-18 | 2018-10-01 | 2019-01-01
|  |  |  | RA_016 |  |  | IT Director | Production - Network & IT Platform | 100 | 100 | 100 | 1000 | 5 | 1000 | 4 | 4000 |  |  | Log collection & correlation project Q1-2 2019 Target 30/06/2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_017 |  |  | IT Director | Production - Network** DNAS / DRAS | 100 | 100 | 100 | 1000 | 5 | 1000 | 12 | 12000 |  |  | Network refresh project DNAS/DRAS 30/06/2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_018 |  |  | IT Director | Production - Network**DFAS | 100 | 100 | 100 | 1000 | 5 | 1000 | 12 | 12000 |  |  | Network refresh project DFAS 15/09/2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_019 |  |  | IT Director | Production - Network**DS1 | 100 | 1000 | 5 | 100 | 5 | 1000 | 8 | 8000 | Acceptable operated by IT-Total, |  | Network refresh project DS1 30/06/2020 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_020 |  |  | IT Director | Production - Network**DC1 | 100 | 100 | 5 | 100 | 5 | 100 | 8 | 800 | Migrated to DP network | [5 empty] | Accept | 2018-09-18 | 2018-12-22 | 2019-01-01
|  |  |  | RA_021 |  |  | IT Director | Architecture insufficiently documented to interface future systems and changes | 100 | 100 | 5 | 1000 | 5 | 1000 | 8 | 8000 |  |  | Establish Application governance across Digiplex with sign-offs-Jan -2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_022 |  |  | IT Director | Production - *Systems** DNAS / DRAS-Lacking documentation and insufficient vendor support contract | 100 | 100 | 5 | 1000 | 5 | 1000 | 8 | 8000 |  |  | Vmware completion Jan 2019 Network fresh Q1-2 2019 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_023 |  |  | IT Director | Production - *Systems-**DFAS-External vendor need better follow up | 100 | 100 | 5 | 100 | 5 | 100 | 8 | 800 | Support agreement in place |  | Will improve further with refresh Q1-2 |  |  |  | Mitigate | 2018-09-18 |  | 2019-01-01
|  |  |  | RA_024 |  |  | IT Director | Production - *Systems-**DS1-Differnet solutions and "living its own life" | 100 | 100 | 5 | 1000 | 5 | 1000 | 8 | 8000 |  |  | Startup with DS1 team Jan 2019 target 31/03/2019 |  |  |  | Mitigate | 2019-09-18 |  | 2019-01-01
|  |  |  | RA_025 |  |  | IT Director | Production - *Systems **DC1 | 100 | 100 | 5 | 100 | 5 | 100 | 4 | 400 | Migrated to DP standards | [5 empty] | Accept | 2018-09-18 | 2018-12-21 | 2019-01-01
#VALUE! |  | #VALUE! |  | RA_026 |  | Strategic | IT Director | Lack of IT Strategy | 20 | 5 | 5 | 20 | 5 | 20 | 4 | 80 | IT Director Appointed Deployment of harmonised automatic systems |  |  | 4 | 20 | 80 | Closed | 2015-05-06 | 2016-12-01 | 2018-03-01 |  | 2 | Transfer
#VALUE! |  | #VALUE! |  | RA_027 | URR_002 | Operational | Head of Operations | SLA Breach priority 1 incident | 100 | 1000 | 5 | 100 | 1 | 1000 | 8 | 8000 | Whole range of tools, controls and techniques deployed In Norway - Sweden to adopt |  | Deployed but needing rigorous enforcement | 4 | 1000 | 4000 | Mitigate | 2015-05-06 |  | 2019-01-01
#VALUE! |  | #VALUE! |  | RA_028 |  | Strategic | CCO | Failure to Expand/ Sell Stockholm | 100 | 20 | 100 | 5 | 5 | 100 | 4 | 400 | Sales Meetings - Pipeline CCO Appointed, Securred Customer, Stronger Pipeline |  |  | 8 | 100 | 800 | Mitigate | 2015-05-06 |  | 2018-03-01
#VALUE! |  | #VALUE! |  | RA_029 |  | Legal | HR | Health and Safety Compliance | 5 | 1000 | 100 | 100 | 100 | 1000 | 4 | 4000 | OSHAS 18001Certifcation Group DNAS DRAS DS1 DFAS Regular Audits Procurement Process |  | Build Construction requirements into Management System in progress | 4 | 1000 | 4000 | Mitigate | 2015-05-06 |  | 2019-01-01
#VALUE! |  | #VALUE! |  | RA_030 |  | Legal | CEO | Corporate Governance ( Companies Act) Compliance | 5 | 20 | 20 | 20 | 20 | 20 | 4 | 80 |  |  |  | 4 | 20 | 80 | Closed | 2015-05-06 | 2019-03-01 | 2018-03-01
#VALUE! |  | #VALUE! |  | RA_031 |  | Legal | COO | Environmental protection | 5 | 20 | 20 | 20 | 20 | 20 | 12 | 240 | ISO 14001 Certification Group DNAS DRAS DS1 DFAS Regular Audits |  |  | 4 | 20 | 80 | Accept | 2015-05-06 | 2016-09-01 | 2018-03-01 | RTV reworked. Next forming to action plan
#VALUE! |  | #VALUE! |  | RA_032 |  | Legal | Head of Security | Physical Security Compliance | 5 | 100 | 20 | 20 | 100 | 100 | 4 | 400 | ISO 27001 Certification Group DNAS DRAS DS1 DFAS Regular Audits, Head of Security Appointed |  | Should this be closed as refined risks are above? | 4 | 100 | 400 | Tolerate | 2019-03-01 | 2016-09-01 | Jul_19
#VALUE! |  | #VALUE! |  | RA_033 |  | Legal | HR | Employment Law Compliance | 5 | 20 | 20 | 20 | 100 | 100 | 2 | 200 |  |  |  | 4 | 100 | 400 | Closed | 2015-05-06 | 2018-03-01 | 2018-03-01
#VALUE! |  | #VALUE! |  | RA_034 |  | Legal | IT Director | IT Law Compliance | 5 | 5 | 1 | 20 | 5 | 20 | 4 | 80 | ISO 27001 Certification Group DNAS DRAS DS1 DFAS Regular Audits |  |  | 4 | 20 | 80 | Closed | 2015-05-06 | 2016-09-01 | 2018-03-01
#VALUE! |  | #VALUE! |  | RA_035 | URR_004 | Legal | FD | Financial Law Compliance | 1 | 20 | 20 | 1 | 20 | 20 | 4 | 80 |  |  |  | 4 | 20 | 80 | Closed | 2015-05-06 | 2018-03-01 | 2018-03-01
#VALUE! |  | #VALUE! |  | RA_036 | URR_006 | Legal | CDO | Construction Law Compliance | 5 | 20 | 20 | 20 | 20 | 20 | 2 | 40 |  |  | Construction requirements into Management System in progress See Risk #10 | 4 | 20 | 80 | Closed | 2015-05-06 | 2018-03-01 | 2018-03-01 | RTV reworked. Next forming to action plan
#VALUE! |  | #VALUE! |  | RA_037 | URR_008 | People | HR | Serious Employee Injury | 20 | 1 | 100 | 100 | 20 | 100 | 2 | 200 | HSE Log |  |  | 8 | 100 | 800 | Accept | 2015-05-06 |  | 2018-03-01
#VALUE! |  | #VALUE! |  | RA_038 | URR_009 | Operational | FD | Procurement Management | 5 | 1 | 20 | 20 | 5 | 20 | 4 | 80 | Finance Processes Contractor and Equipment Processes |  |  | 4 | 20 | 80 | Closed | 2015-05-06 | 2018-03-01 | 2018-03-01
#VALUE! |  | #VALUE! |  | RA_039 | URR_003 | Operational | CMO | Management of information -External/Press etc | 20 | 1000 | 20 | 5 | 1 | 1000 | 4 | 4000 | Appointment of CMO Appointed Head of communications Crisis Communication Manual . Monitored Siginificant Events and took lessons learnt | Crisis Communication Manual | Update 8/6/20181. Called in Inger Marie to help us form a structure around which processes to create documented “process flows” for 2. The team is currently maping out all relevant marketing/comms processes, documenting and creating process flows 3. Following the Nancy incident we have put a plan in place to speak to our top customers and form a joint comms BCP – in readiness for the next incident (which hopefully will not occur!) 4. The crisis comms document is undergoing revision to included lessons learnt from the Nancy incident 5. As part of the company wide GDPR efforts we are GDPR proofing Pardot – our marketing backbone system. | 4 | 1000 | 4000 | Mitigate | 2015-05-06 |  | 2018-03-01
-1e-08 |  | 400 |  | RA_040 | URR_004 | Strategic | CEO | Corporate Governance- Lack of following Internal controls | 100 | 100 | 100 | 100 | 100 | 100 | 4 | 400 |  |  |  | 4 | 100 | 400 | Accept | 2015-05-06 |  | 2018-03-01
-2e-08 |  | 400 |  | RA_041 |  | Legal | CCO | Unaware of undisclosed legal pitfalls' customer contracts | 5 | 20 | 100 | 20 | 5 | 100 | 4 | 400 | Contract "Cook book" Sales Process | Revising Standard Contracts |  | 4 | 100 | 400 | Mitigate | 2015-05-06 |  | 2018-03-01
-3e-08 |  | 4000 |  | RA_042 |  | Legal | CDO | Large Vendor contracts management | 5 | 20 | 1000 | 100 | 100 | 1000 | 4 | 4000 | Employed CPS to PM larger contract works |  | Site Manager to recruited. Contractor Management | 4 | 1000 | 4000 | Mitigate | 2015-05-06 |  | 2019-01-01
#REF! |  | #REF! |  | RA_043 |  | People | HR | Overlapping of Skills sets -Succession planning | 20 | 5 | 20 | 1 | 1 | 100 | 4 | 400 | Succession Planning process | Succession Plan |  | 8 | 100 | 800 | Accept | 2015-05-06 |  | 2018-03-01 | Deployed
#REF! |  | #REF! |  | RA_044 |  | Strategic | CEO | Impact on Changes in Market Place- competitors/Technology | 20 | 100 | 100 | 20 | 5 | 100 | 8 | 800 | Business plans reviews Business Planning | Business Planning |  | 8 | 100 | 800 | Accept | 2015-05-06 |  | 2018-03-01
#REF! |  | #REF! |  | RA_045 | URR_005 | Strategic | Head of Security | Lack of Security Plan | 100 | 100 | 100 | 100 | 100 | 100 | 2 | 200 | Security Strategy in place in Management System |  | Site Security Plans to be developed | 4 | 100 | 400 | Treat | 2017-02-06 | 2019-01-01 | Jul_19
#REF! |  | #REF! |  | RA_046 |  | Operational | Head of Operations | Lack of Business Continuity Plans | 100 | 100 | 100 | 1000 | 20 | 1000 | 4 | 4000 | Business Continuity system developed but not tested | BCP process in SharePoint | Site BCP Plans being Developed BCM Framework being developed. Major Incident Team Plan under development | 4 | 1000 | 4000 | Mitigtae | 2015-05-06 |  | 2019-01-01
#REF! |  | #REF! |  | RA_047 |  | Operational | HR | GDPR Compliance | 5 | 100 | 100 | 5 | 100 | 100 | 8 | 800 | Independent Project set up with Steering Committee |  |  | 4 | 100 | 400 | Accept | 2016-12-12 |  | 2018-03-01
#REF! |  | #REF! |  | RA_048 |  | Operational | FD | Economy /Market Rate | 5 | 1 | 5 | 5 | 1 | 5 | 2 | 10 |  |  |  | 8 | 5 | 40 | Closed | 2015-05-06 |  | 2018-03-01
#REF! |  | #REF! |  | RA_049 | URR_001 | Security | Head of Operations | Theft from Site | 1 | 100 | 5 | 1 | 5 | 100 | 8 | 800 | Risk Threat and vulnerability processes considerations |  | Strengthen RTV and team education | 8 | 100 | 800 | Accept | 2015-05-01 |  | 2018-03-01 | Deployed
#REF! |  | #REF! |  | RA_050 |  | Operational | Head of Operations | Fibre Cable Strike DNAS | 100 | 100 | 5 | 100 | 1 | 100 | 8 | 800 | Carrier relationships managed as part of MMR processes. |  |  | 8 | 100 | 800 | Monitor | 2015-05-06 |  | 2018-03-01 |  | 4 | Control
#REF! |  | #REF! |  | RA_051 |  | Operational | Head of Security | Sabotage - Attacks against Norway/Sweden/Denmark | 100 | 100 | 100 | 100 | 5 | 100 | 2 | 200 | Risk Threat and vulnerability processes considerations. Terrroist and Political Maps Reviewed Quarterly by Compliance and Assurance Director. Annual Security threat reports by National Security organisations reviewd by Head of Security. Countries all rank low and stable | AON Risk Maps | Reassess if threat status changes to a higher level. | 4 | 100 | 400 | Tolerate | 2015-05-06 |  | Jul_19
#REF! |  | #REF! |  | RA_052 |  | Operational | Head of Security | Sabotage - Attacks against Customer | 1000 | 1000 | 5 | 100 | 100 | 1000 | 2 | 2000 | Site Physical Security Measures Customer responsibility for its own logical security |  | Investigate further | 4 | 1000 | 4000 | Tolerate | 2015-05-06 |  | Jul_19 | [9 empty] | Avoid
#REF! |  | #REF! |  | RA_053 | URR_002 | Operational | FD | Inadequate Insurance towards Customer | 20 | 20 | 100 | 1 | 20 | 100 | 4 | 400 |  |  |  | 8 | 100 | 800 | Accept | 2015-05-06 |  | 2018-03-01 | [9 empty] | Transfer
#REF! |  | #REF! |  | RA_054 | URR_004 | People | HR | Conflict with Workforce | 20 | 20 | 20 | 20 | 20 | 100 | 2 | 200 | None | None |  | 4 | 100 | 400 | Closed | 2015-05-06 | 2018-03-01 | 2018-03-01 | [9 empty] | Accept
#REF! |  | #REF! |  | RA_055 | URR_005 | People | HR | Work Life Balance | 1 | 1 | 1 | 5 | 1 | 5 | 2 | 10 | Engagement Survey | Survey Results Y-O-Y |  | 8 | 5 | 40 | Closed | 2015-05-06 | 2018-03-01 | 2018-03-01 | Deployed
#REF! |  | #REF! |  | RA_056 |  | Security | IT Director | Changing threats around cyber and vulnerability -Cyber Security Attacks e.g. Ransomware | 100 | 20 | 100 | 1000 | 1 | 1000 | 8 | 8000 |  |  | Ongoing Hardening log collection linked to various risks above. | 8 | 1000 | 8000 | Mitigate | 2016-02-01 |  | 2018-03-01
#REF! |  | #REF! |  | RA_057 |  | Operational | FD | Single Customer Site goes into Payment Default | 5 | 100 | 100 | 5 | 100 | 100 | 2 | 200 | Regular review of outstanding balances, CEO meetings with Customer's senior team. |  |  | 4 | 100 | 400 | Monitor | 2016-02-01 |  | 2018-03-01
#REF! |  | #REF! |  | RA_058 |  | Operational | HR | Background checks on Companies not employees who enter a Datacentre ( Linked with Risk #29) | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | Customers that require background check also have to control the access, and have implemented their own access control system for the relevant modules |  | None | 2 | 1000 | 2000 |  | 2016-02-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_059 |  | Operational | Head of Security | Lack of 24/7 Security at Sites | 100 | 20 | 100 | 100 | 20 | 100 | 8 | 800 | DNAS - 24/7 Security presence on site DFAS - 24/7 Security presence on site DS1 - 24/7 Security presence on site DC1 - 24/7 Security presence available in adjacent Telia building DRAS - 24/7 alarm monitoring by DNAS and DS1. All sites have access control systems All sites have CCTV surveillance |  | RTV Works and SOC establishment intended to reduce exposure | 8 | 100 | 800 | Treat | 2016-02-01 |  | Jul_19
#REF! |  | #REF! |  | RA_060 |  | Strategic | FD | Breach of Debt Financing Covenants | 1 | 5 | 100 | 1 | 1 | 100 | 12 | 1200 | Monthly/Quarterly Cash Flow Projections & Half-Yearly Forecast/Annual Budgets |  |  | 8 | 100 | 800 | Accept | 2016-06-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_061 |  | Operational | HR | Unhappy Employee Uses Social Media to Publise issues i.e sexual harrasment (Me2) | 5 | 1000 | 20 | 20 | 20 | 1000 | 2 | 2000 | This is In place now |  |  | 2 | 1000 | 2000 | Monitor | 2018-03-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_062 |  | Strategic | FD | Refinacing Bond Expiry | 1 | 1 | 1000 | 1 | 1 | 1000 | 2 | 2000 | Bond loans for DNAS/DRAS and DFAS expire summer 2019. Refinancing in process | [5 empty] | Monitor | 2018-03-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_063 |  | Operational | FD | 24/7 Office Platform high risk due to supplier solidity, and software access/ cyber crime | 1 | 1 | 100 | 1 | 1 | 100 | 4 | 400 | In process of changing ERP system to Xledger. Implementation 1 October 2018 |  |  |  |  | Mitigate | Mitigate | 2018-03-01 |  | 2018-03-01
#REF! |  | #REF! |  | RA_064 |  | Opertional | HR | Not enough Human Capacity | 100 | 20 | 20 | 100 | 5 | 100 | 16 | 1600 | Staffing Scenario Plan developed with a FTE build up integrated ref current cases. Will start a slow build up and invest as we grow strategy. Also signing strategic supplier contracts to mitigate the current risk. | [5 empty] | Mitigate | 2018-03-01 |  | 2019-01-18
#REF! |  | #REF! |  | RA_065 |  | Operational | FD | Fraud- Kickback payments | 20 | 100 | 20 | 1 | 100 | 100 | 4 | 400 | Whistle blower system (internal and external). Contract signing authorisation and invoice approval by minimum 2 with approval rights. Supplier vetting and Procurement procedure. Business Code of Conduct and Supplier Code of Practice Quantity controller controlling the capex costs |  | Implement that we have to have a tender with minimum 3 suppliers for all builds above a certain size Consider controls avoid bribing of customer? |  |  |  | Monitor | 2018-03-01
#REF! |  | #REF! |  | RA_066 |  | Operational | Head of Operations | Smart hands missing in Oslo | 5 | 100 | 20 | 20 | 5 | 100 | 4 | 400 | [6 empty] | Accept | 2018-03-01 |  | 2018-03-01
#REF! |  | #REF! |  | RA_067 |  |  | CDO | IT not being involved in Projects | 5 | 100 | 20 | 20 | 5 | 100 | 4 | 400 | Meeting Held with Development and IT to agree on Boundries | [6 empty] | 2018-07-01
#REF! |  | #REF! |  | RA_068 |  |  | IT Director | Dell lacking employee capacitiy in Scandinavia | 100 | 100 | 20 | 100 | 5 | 100 | 8 | 800 | Support contract signed with Friday Networks and no dependency on Dell Engineers. Dell network replacement 2019-2020 |  | Short-term: Outsourcing partner identified (independent of Dell Engineer resources) to take on board network operations DFAS, DNAS & DRAS Mid/long term: Replace Dell network componenets with industry standard devices from Cisco whcih is supported by 90% of the service providors |  |  |  | Accept | 2018-07-18 | 2018-10-18 | 2019-01-01
#REF! |  | #REF! |  | RA_069 |  |  | CCO | Selling to match the business plan | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 |  |  | Consider US salesforce. Packaged hyperscale “PoP” offering Use account based or large deal team structure |  |  |  |  | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_070 |  |  | Head of Ops | Operating in accord with business plan | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_071 |  |  | Head of Ops | Meeting hyperscale operational performance demands | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 |  |  | Team to reach the standard required in the time available |  |  |  |  | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_072 |  |  | FD | Financial planning misses items, underestimates or trails with higher actual costs | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_074 |  |  | IT Director | Field asset vulnerability, service delivery weakness and security vulnerabilty | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | need to find out more information about risk sm. Requires review |  | bms controllers network munteres controller talking to bms could get through back door could take us down generator could be taken down |  |  |  |  | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_076 |  |  | Head of Security | Government assess DC as area of threat | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | DigiPlex has government agencies as customers in its data centres. Those customers have a requirement for DigiPlex to comply with the Security Act and in some cases to sign a Security Agreement with them. DigiPlex works with these customers to ensure compliance. |  | Ensure compliance with Security Act requirements |  |  |  | Tolerate | 2019-01-01 |  | Jul_19
#REF! |  | #REF! |  | RA_077 |  |  | Head of Security | Security - dawn raid processes | 1 | 100 | 100 | 100 | 100 | 100 | 2 | 200 | Process exists at DFAS and DNAS |  | Develop Process across all sites |  |  |  | Treat | 2019-01-20 |  | Jul_19
#REF! |  | #REF! |  | RA_078 |  |  | Head of Security | Social engineering security threat | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | Social Engineering security threat Awareness training conducted during Town Hall Meeting. Followed up by a questionaire and audit question on the most recent Pulse Survey. |  | Further continuation training required at future Town hall meetings |  |  |  | Treat | 2019-01-01 |  | Jul_19
#REF! |  | #REF! |  | RA_079 |  |  | FD | Fraud by such as fake payment requests & invoices | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_080 |  |  | FD | Sub-tenant deploys cryptocurrency negating ability to obtain power tax credits | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 |  |  | Code of conduct with customers Adjust contracts re. cryptocurrency hosting and liability to compensate |  |  |  |  | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_081 |  |  | CDO | Legacy BMS infra. outmoded needs replace/upgrade | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_082 |  |  | Head of Ops | DFAS infra. wasn't acceptance tested | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_083 |  |  | CDO | DS1 masterplan incompatible with business plan? | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_084 |  |  | CDO | Difficulty holding hyperscale CapEx price as Europe is flooded with demand | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 |  |  | Mismatched build/deliver resources Poaching resources Land & power grabbing Construction companies over worked Access to plant (gen's, cooling) |  |  |  |  | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_085 |  |  | CDO | Insufficent commercial awareness | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 |  |  | Cultural competence, experience Common sense review and rereview Check negotiation status before signing off Build “just good enough” to remain competitive Procure the cheapest that is works Commercialisation of the the organisation |  |  |  |  | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF! |  | RA_086 |  |  | Head of Security | Interpretation of Security Act and Security Agreements | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | DigiPlex procedures are compliant with the Norwegian Security Act verified by customer audit CEO holds a Norwegian Security Clearance |  | Some customers may require a Security Agreement Customers such as Huawei may become unwelcome without more segmentation Cloud act (US) compliance Discuss implications and strategy at SLT meeting |  |  |  | Treat | 2019-01-01 |  | Jul_19
#REF! |  | #REF! |  | RA_087 |  |  | Head of Operations | Safe system of works permiting lapsed since migration to Service Now | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | RA_085 |  |  | CDO | Issues in Commisiong Management | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01
|  |  |  | RA_085 |  |  | Head of Security | Public Profiles re. Kidnap / ransom | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | Profiles of senior DigiPlex management team are available on DigiPlex.com web site. |  | This is a balance between security and marketing. DigiPlex has a policy of embracing and exploiting social media. If this is considered to be a credible Risk then options available are Tolerate the risk- Take no action Treat the risk- Would require excessive personal protection measures for the team - Not practical Terminate the risk- Remove the personal profiles from the web site - Recommended action from a purely security perspective Transfer the risk - Insure against kidnap - not practical and not ideal on a personal level for the team affected Discuss implications and strategy at SLT meeting |  |  |  | Treat | 2019-01-01 |  | Jul_19
|  |  |  | RA_085 |  |  | FD | Lack of Anti Money Laundering and Terriost Funding policies | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 16 | 16000 | [7 empty] | 2019-01-01 |  | 2019-01-01

## Risk Levels (hidden)
Probability level | Impact Score
| 1 | 5 | 20 | 100 | 1000
2 | 2 | 10 | 40 | 200 | 2000
4 | 4 | 20 | 80 | 400 | 4000
8 | 8 | 40 | 160 | 800 | 8000
12 | 12 | 60 | 240 | 1200 | 12000
16 | 16 | 80 | 320 | 1600 | 16000
Need to determine levels
High
Medium
Low
Score | Rate
2 | Very Low
4 | Very Low
8 | Very Low
12 | Very Low
16 | Very Low
10 | Very Low
20 | Very Low
40 | Low
60 | Low
80 | Low
160 | Medium
240 | Medium
320 | Medium
200 | Medium
400 | Medium
800 | Medium
1200 | Very High
1600 | Very High
2000 | Very High
4000 | Very High
8000 | Very High
12000 | Very High
16000 | Very High