## Page 1
Number | Site | Short description | Type | State | Planned start date | Planned end date | Assigned to | Updated | Closed | Closed by | CAB date | Approval | Approval history | Actual start | Actual end | Created
CHG0031623 | DigiPlex Norway AS | Bytte av 2 Power modul og Static Switch i UPS D6 | Normal | Assess | 2020-01-13 08:00 | 2020-01-13 16:00 |  | 2020-01-10 10:51 |  |  |  | Requested | 10.01.2020 10:50:59 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2020-01-10 08:59
CHG0031621 | DigiPlex Rosenholm AS | Installasjon av trådstiger | Normal | Implement | 2020-01-10 09:12 | 2020-01-17 09:12 |  | 2020-01-10 09:00 |  |  |  | Approved | 09.01.2020 10:53:30 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 09.01.2020 10:33:47 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2020-01-10 09:13 |  | 2020-01-09 09:15
CHG0031620 | DigiPlex Norway AS | Power migration Part 1 | Normal | Scheduled | 2020-02-18 08:00 | 2020-02-20 17:00 |  | 2020-01-10 08:41 |  |  |  | Approved | 09.01.2020 14:43:54 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). |  |  | 2020-01-08 12:45
CHG0031619 | DigiPlex Rosenholm AS | DRS - Rep av gen 3.3 | Normal | Implement | 2020-01-08 08:30 | 2020-02-29 08:30 |  | 2020-01-09 17:00 |  |  |  | Approved | 09.01.2020 08:23:21 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). |  |  | 2020-01-08 08:30
CHG0031618 | DigiPlex Rosenholm AS | Enter your description here | Normal | Canceled | 2020-01-09 15:30 | 2020-01-17 15:30 | Anders Lundin Bjørnstad | 2020-01-10 10:58 | 2020-01-10 10:58 | Kristin Ohnstad |  | Requested | 07.01.2020 16:54:54 - Kristin Ohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). | 2020-01-09 15:30 |  | 2020-01-07 15:56
CHG0031617 | DigiPlex Rosenholm AS | DRAS - Rep av Deep Sea paneler | Normal | Closed | 2020-01-07 07:00 | 2020-01-07 18:00 |  | 2020-01-09 12:30 | 2020-01-09 12:30 | Kristin Ohnstad |  | Approved | 06.01.2020 15:45:16 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 06.01.2020 15:40:40 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2020-01-07 08:31 | 2020-01-07 14:25 | 2020-01-06 15:20
CHG0031616 | DigiPlex Rosenholm AS | DRAS - Leak detection service 2020 | Normal | Implement | 2020-01-09 06:00 | 2020-01-10 18:00 |  | 2020-01-09 05:00 |  |  |  | Approved | 06.01.2020 16:48:17 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 06.01.2020 16:45:24 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2020-01-06 15:10
CHG0031615 | DigiPlex Rosenholm AS | Clean up the rack in CCR C | Normal | Implement | 2020-01-07 10:00 | 2020-01-07 12:00 |  | 2020-01-07 09:00 |  |  |  | Approved | 02.01.2020 08:47:16 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 02.01.2020 07:53:48 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2020-01-02 07:51
CHG0031614 | DigiPlex Fet AS | Inverter upgrade | Normal | Scheduled | 2020-02-03 14:07 | 2020-02-04 14:07 |  | 2020-01-06 11:34 |  |  |  | Approved | 06.01.2020 08:03:18 - Dag Oscar Brækken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2019-12-20 14:06
CHG0031611 | DigiPlex Fet AS | Network refresh DFAS | Normal | Implement | 2020-01-06 09:00 | 2020-01-13 12:00 |  | 2020-01-06 09:00 |  |  |  | Approved | 06.01.2020 08:04:29 - Dag Oscar Brækken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2019-12-20 07:32
CHG0031609 | DigiPlex Rosenholm AS | DRAS - Test av generator styring | Emergency | Closed | 2019-12-17 10:37 | 2019-12-17 16:37 |  | 2020-01-09 12:27 | 2020-01-09 12:27 | Kristin Ohnstad |  | Approved | 09.01.2020 12:26:34 - Kristin Ohnstad (Approval history) Group approval for CAB Approval NO approved by user Kristin Ohnstad (CAB approval). 17.12.2019 10:38:18 - Frode Elden Kay (Approval history) Group approval for eCAB Approval approved by user Frode Elden Kay (eCAB approval). | 2019-12-17 11:00 | 2019-12-17 15:31 | 2019-12-17 10:37
CHG0031606 | DigiPlex Fet AS | Temporary Security Arrangements | Normal | Scheduled | 2020-01-19 10:29 | 2020-02-14 10:29 |  | 2019-12-20 11:17 |  |  |  | Approved | 19.12.2019 09:09:21 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 18.12.2019 13:32:47 - Kristin Ohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-12-16 17:16
CHG0031605 | DigiPlex Norway AS | Annual CCTV maintenance | Normal | Closed | 2019-12-15 08:00 | 2019-12-18 16:00 |  | 2020-01-03 14:29 | 2020-01-03 14:29 | Kristin Ohnstad |  | Approved | 14.12.2019 11:04:35 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-12-15 08:00 | 2019-12-19 16:00 | 2019-12-13 14:14
CHG0031604 | DigiPlex Stockholm 1 AB | Survey Generator | Normal | Closed | 2019-12-16 09:00 | 2019-12-16 18:00 |  | 2019-12-19 15:19 | 2019-12-19 15:19 | Christian Eghult |  | Approved |  | 2019-12-16 12:00 | 2019-12-19 17:00 | 2019-12-13 09:33
CHG0031603 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A1_7 | Normal | Scheduled | 2020-01-16 08:00 | 2020-01-16 16:00 |  | 2019-12-19 08:20 |  |  |  | Approved | 19.12.2019 07:14:49 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-13 09:14
CHG0031602 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A1_4 | Normal | Scheduled | 2020-01-16 08:00 | 2020-01-16 16:00 |  | 2019-12-19 08:21 |  |  |  | Approved | 19.12.2019 07:14:24 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-13 09:07
CHG0031601 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A1_3 | Normal | Scheduled | 2020-01-15 08:00 | 2020-01-15 16:00 |  | 2019-12-19 08:21 |  |  |  | Approved | 19.12.2019 07:13:58 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-13 09:01
CHG0031600 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A1_2 | Normal | Scheduled | 2020-01-14 08:00 | 2020-01-14 16:00 |  | 2019-12-19 08:22 |  |  |  | Approved | 19.12.2019 07:11:24 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-13 08:58
CHG0031599 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A1_1 | Normal | Scheduled | 2020-01-13 08:00 | 2020-01-13 16:00 |  | 2019-12-19 08:22 |  |  |  | Approved | 19.12.2019 07:10:46 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-13 08:53
CHG0031598 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A2_4 | Normal | Scheduled | 2020-01-24 08:00 | 2020-01-24 16:00 |  | 2019-12-19 08:23 |  |  |  | Approved | 19.12.2019 07:10:23 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-12 15:01
CHG0031597 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A2_2 | Normal | Scheduled | 2020-01-20 08:00 | 2020-01-20 16:00 |  | 2019-12-19 08:23 |  |  |  | Approved | 19.12.2019 07:09:55 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-12 14:56
CHG0031596 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A2_1 | Normal | Scheduled | 2020-01-17 08:00 | 2020-01-17 16:00 |  | 2019-12-19 08:23 |  |  |  | Approved | 19.12.2019 07:09:16 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-12 14:49
CHG0031595 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A2_6 | Normal | Scheduled | 2020-01-23 08:00 | 2020-01-23 16:00 |  | 2019-12-19 08:24 |  |  |  | Approved | 19.12.2019 07:08:48 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-12 14:42
CHG0031594 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A2_5 | Normal | Scheduled | 2020-01-22 08:00 | 2020-01-22 16:00 |  | 2019-12-19 08:24 |  |  |  | Approved | 19.12.2019 07:08:16 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-12 14:36
CHG0031593 | DigiPlex Fet AS | DFAS - Semiannual Maintenance + Monthly Test, Generator A2_3 | Normal | Scheduled | 2020-01-21 08:00 | 2020-01-21 16:00 |  | 2019-12-19 08:24 |  |  |  | Approved | 19.12.2019 07:07:43 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-12 12:56
CHG0031592 | DigiPlex Rosenholm AS | Network refresh DRAS | Normal | Closed | 2019-12-16 09:00 | 2019-12-16 16:00 |  | 2020-01-03 14:24 | 2020-01-03 14:24 | Kristin Ohnstad |  | Approved | 13.12.2019 09:37:16 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-12-18 10:00 | 2019-12-18 16:30 | 2019-12-12 08:30
CHG0031591 | DigiPlex Rosenholm AS | Network refresh DRAS | Normal | Closed | 2019-12-16 09:00 | 2019-12-16 16:00 |  | 2020-01-03 14:24 | 2020-01-03 14:24 | Kristin Ohnstad |  | Approved | 13.12.2019 09:36:23 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-12-16 10:30 | 2019-12-17 15:00 | 2019-12-12 08:18
CHG0031590 | DigiPlex Norway AS | Upgrade CCU in 00MOD04.3 | Normal | Implement | 2019-12-12 08:00 | 2019-12-25 14:57 |  | 2019-12-13 11:00 |  |  |  | Approved | 13.12.2019 09:08:11 - Hans Petter Enevoldsen (Approval history) Group approval for Change-Technical assess group approved by user Hans Petter Enevoldsen (Technical approvals norway). |  |  | 2019-12-11 14:58
CHG0031589 | DigiPlex Norway AS | Årlig service på fukt følere | Normal | Implement | 2019-12-12 09:49 | 2019-12-19 09:50 |  | 2019-12-16 11:00 |  |  |  | Approved | 12.12.2019 07:39:06 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-11 14:43
CHG0031584 | DigiPlex Fet AS | Moving camera c-48 | Normal | Implement | 2019-12-16 11:42 | 2019-12-20 11:43 |  | 2019-12-16 11:00 |  |  |  | Approved | 11.12.2019 08:24:17 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). |  |  | 2019-12-10 11:42
CHG0031583 | DigiPlex Stockholm 1 AB | Submittal of Fuel Truck Sensor | Normal | Closed | 2019-12-09 09:15 | 2019-12-10 09:15 |  | 2019-12-19 15:17 | 2019-12-19 15:17 | Christian Eghult |  | Approved |  | 2019-12-09 08:00 | 2019-12-09 18:00 | 2019-12-09 09:26
CHG0031582 | DigiPlex Norway AS | 00MOD04.3, oppgradering modul. | Normal | Implement | 2019-12-09 08:00 | 2020-03-13 14:26 |  | 2019-12-09 09:26 |  |  |  | Approved | 09.12.2019 08:35:17 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-12-06 14:35
CHG0031580 | DigiPlex Norway AS | Annual full scale test | Normal | Closed | 2019-12-09 08:00 | 2019-12-11 14:00 |  | 2020-01-09 12:31 | 2020-01-09 12:31 | Kristin Ohnstad |  | Approved | 06.12.2019 10:28:21 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 06.12.2019 09:31:01 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-12-09 09:00 | 2019-12-10 16:00 | 2019-12-06 09:18
CHG0031579 | DigiPlex Norway AS | Hjelpe til medService på CCU'er | Normal | Closed | 2019-12-04 08:01 | 2019-12-30 15:45 | Kristin Ohnstad | 2020-01-09 12:28 | 2020-01-09 12:28 | Kristin Ohnstad |  | Approved | 04.12.2019 07:09:03 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 03.12.2019 16:30:21 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-12-04 14:10 | 2020-01-30 14:10 | 2019-12-03 16:08
CHG0031578 | DigiPlex Rosenholm AS | Change switch ports | Normal | Closed | 2019-12-05 10:00 | 2019-12-05 11:00 |  | 2019-12-19 08:48 | 2019-12-19 08:48 | Kristin Ohnstad |  | Approved | 03.12.2019 16:26:04 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 03.12.2019 16:22:48 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-12-05 10:00 | 2019-12-05 10:30 | 2019-12-03 14:08
CHG0031577 | DigiPlex Norway AS | Sette opp gass varsler strobe | Normal | Implement | 2019-12-04 08:00 | 2019-12-04 16:00 |  | 2019-12-04 13:00 |  |  |  | Approved | 03.12.2019 14:38:19 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 03.12.2019 13:43:40 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-12-03 12:59
CHG0031576 | DigiPlex Fet AS | DFAS - Semiannual Maintenance of Generator A2_3, A2_5 and A2_6 (Major) | Normal | Canceled | 2019-12-17 08:00 | 2019-12-19 16:00 |  | 2019-12-18 11:41 | 2019-12-18 11:41 | Frode Elden Kay |  | Approved | 03.12.2019 15:36:05 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 03.12.2019 14:46:57 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-12-02 17:23
CHG0031575 | DigiPlex Stockholm 1 AB | Fuel Truck Sensor | Normal | Closed | 2019-12-04 08:00 | 2019-12-05 18:00 |  | 2019-12-19 15:07 | 2019-12-19 15:07 | Christian Eghult |  | Approved |  | 2019-12-04 08:00 | 2019-12-04 14:00 | 2019-12-02 12:21
CHG0031573 | DigiPlex Stockholm 1 AB | Generator Controls Inspection | Normal | Closed | 2019-12-04 08:00 | 2019-12-04 18:00 |  | 2019-12-19 15:12 | 2019-12-19 15:12 | Christian Eghult |  | Approved |  | 2019-12-04 15:00 | 2019-12-04 18:00 | 2019-11-30 09:58
CHG0031572 | DigiPlex Stockholm 1 AB | DH1 UPS module reinstall and battery test | Normal | Closed | 2019-12-07 08:00 | 2019-12-07 18:00 |  | 2019-12-19 15:01 | 2019-12-19 15:01 | Christian Eghult |  | Approved |  | 2019-12-07 08:03 | 2019-12-07 11:33 | 2019-11-29 13:32
CHG0031571 | DigiPlex Fet AS | LOR 3. Monthly test of Generator A2_3, A2_5 and A2_6 | Normal | Closed | 2019-12-17 08:00 | 2019-12-19 16:00 |  | 2020-01-06 13:43 | 2020-01-06 13:43 | Dag Oscar Brækken |  | Approved | 03.12.2019 15:59:24 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 03.12.2019 15:55:33 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-12-17 13:41 | 2019-12-19 13:41 | 2019-11-29 12:51
CHG0031567 | DigiPlex Norway AS | Move connection to VMWare server from old network to new network. | Normal | Closed | 2019-11-25 10:00 | 2019-11-25 16:00 |  | 2019-11-26 16:37 | 2019-11-26 16:37 | Kristin Ohnstad |  | Approved | 25.11.2019 14:28:58 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 22.11.2019 11:00:29 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-25 14:15 | 2019-11-25 15:30 | 2019-11-22 10:11
CHG0031566 | DigiPlex Norway AS | Move connection to VMWare server from old network to new network | Normal | Canceled | 2019-11-25 06:53 |  |  | 2019-11-22 11:00 | 2019-11-22 11:00 | Kristin Ohnstad |  | Not Yet Requested |  |  |  | 2019-11-22 07:39
CHG0031565 | DigiPlex Norway AS | BMS upgrade CCUs -01MOD08 shelter | Normal | Canceled | 2019-11-25 08:00 | 2019-11-26 16:00 | Kristin Ohnstad | 2019-11-28 10:47 | 2019-11-28 09:24 | John Petter Jahr |  | Approved | 21.11.2019 22:48:34 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). | 2019-11-25 08:01 | 2019-11-26 16:00 | 2019-11-21 10:00
CHG0031564 | DigiPlex Stockholm 1 AB | Welding of filling pipe for new GEN/DH7/C | Normal | Closed | 2019-11-20 07:00 | 2019-11-28 17:00 |  | 2019-12-19 14:09 | 2019-12-19 14:09 | Kristin Ohnstad |  | Approved |  | 2019-11-26 07:00 | 2019-11-28 16:00 | 2019-11-19 15:12
CHG0031562 | DigiPlex Rosenholm AS | Fiberkabling CCR-A -->10.2 | Normal | Closed | 2019-11-21 07:00 | 2019-11-29 16:00 |  | 2019-11-26 14:21 | 2019-11-26 14:21 | Kristin Ohnstad |  | Approved | 20.11.2019 08:07:38 - Dag Oscar Brækken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2019-11-21 07:00 | 2019-11-21 16:48 | 2019-11-18 08:48
CHG0031560 | DigiPlex Norway AS | '-01MOD08.2, upgrading CCU. | Normal | Closed | 2019-11-18 08:00 | 2019-12-27 16:00 | Kristin Ohnstad | 2020-01-03 14:26 | 2020-01-03 14:26 | Kristin Ohnstad |  | Approved | 16.11.2019 12:16:43 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 15.11.2019 14:56:25 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-18 18:00 | 2019-11-26 16:00 | 2019-11-15 14:27
CHG0031559 | DigiPlex Norway AS | Replace Meru wifi network with Cisco Meraki network | Normal | Implement | 2019-11-18 14:37 | 2019-12-13 14:00 |  | 2019-12-20 07:20 |  |  |  | Approved | 15.11.2019 22:04:21 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 15.11.2019 14:59:41 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-11-15 14:37
CHG0031558 | DigiPlex Fet AS | Installation of lighting in hot aisles | Normal | Implement | 2019-11-18 14:25 | 2019-12-20 14:27 |  | 2019-11-19 08:27 |  |  |  | Approved | 18.11.2019 08:42:19 - Dag Oscar Brækken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 15.11.2019 14:58:50 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-11-15 14:27
CHG0031557 | DigiPlex Norway AS | Repair of CCU in -01MOD08.2 | Normal | Closed | 2019-11-18 08:00 | 2019-11-22 16:00 | Kristin Ohnstad | 2020-01-03 14:27 | 2020-01-03 14:27 | Kristin Ohnstad |  | Approved | 16.11.2019 12:16:41 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 15.11.2019 14:49:47 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-18 08:00 | 2019-11-22 10:54 | 2019-11-15 13:31
CHG0031555 | DigiPlex Norway AS | Replace old switches di-ul-sw017 and sw-020 with new switches | Normal | Closed | 2019-11-18 08:59 | 2019-11-18 08:59 |  | 2019-11-25 08:20 | 2019-11-25 08:20 | Kristin Ohnstad |  | Approved | 15.11.2019 22:04:19 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 15.11.2019 15:00:00 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-20 06:46 | 2019-11-21 06:46 | 2019-11-15 09:00
CHG0031554 | DigiPlex Norway AS | Replace old switch di-ul-sw-015 (Hjørnekontor) with new switch. Replace old Meru accesspoint with Cisco Meraki AP | Normal | Closed | 2019-11-18 09:00 | 2019-11-18 10:00 |  | 2019-11-26 16:36 | 2019-11-26 16:36 | Kristin Ohnstad |  | Approved | 15.11.2019 22:04:18 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 15.11.2019 15:00:26 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-18 09:30 | 2019-11-18 11:15 | 2019-11-15 07:32
CHG0031553 | DigiPlex Rosenholm AS | CCR-B + CCR-C, new feeds to rack. | Normal | Closed | 2019-11-18 14:29 | 2019-11-29 14:29 |  | 2019-12-03 13:43 | 2019-12-03 13:43 | Kristin Ohnstad |  | Approved | 15.11.2019 06:50:08 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-18 08:58 | 2019-11-26 08:58 | 2019-11-14 14:40
CHG0031552 | DigiPlex Rosenholm AS | DRAS - UPS Service | Normal | Closed | 2019-11-25 12:24 | 2019-11-29 12:24 |  | 2019-11-28 09:20 | 2019-11-28 09:20 | Kristin Ohnstad | 2019-11-21 | Approved | 21.11.2019 10:31:42 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 20.11.2019 15:47:31 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-25 08:56 | 2019-11-27 08:56 | 2019-11-15 09:11
CHG0031551 | DigiPlex Norway AS | Bytte Efektmodul i UPS A Rack 2 | Emergency | Implement | 2019-11-13 12:00 | 2019-11-13 14:01 |  | 2019-11-15 14:42 |  |  |  | Approved | 15.11.2019 14:41:47 - Pål Rune Viken (Approval history) Group approval for CAB Approval NO approved by user Pål Rune Viken (CAB approval). 13.11.2019 11:36:29 - Alexander Olsen (Approval history) Group approval for approved by user Alexander Olsen (eCAB approval). | 2019-11-13 13:00 |  | 2019-11-13 11:07
CHG0031550 | DigiPlex Norway AS | Move link on switch di-ul-sw-023 to new network | Normal | Closed | 2019-11-13 07:37 | 2019-11-14 07:37 |  | 2019-11-26 14:18 | 2019-11-26 14:18 | Kristin Ohnstad |  | Approved | 13.11.2019 10:45:36 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 13.11.2019 07:42:46 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-18 19:28 | 2019-11-18 19:28 | 2019-11-13 07:38
CHG0031548 | DigiPlex Norway AS | Network refresh in 02PLT02. | Normal | Implement | 2019-12-12 09:00 | 2019-12-12 16:00 |  | 2019-12-20 07:22 |  |  |  | Approved | 13.11.2019 11:35:27 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 13.11.2019 07:43:12 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-11-12 14:03
CHG0031547 | DigiPlex Norway AS | Craning baracks 2019 | Normal | Closed | 2019-11-11 12:06 | 2019-11-22 12:06 |  | 2019-11-28 09:16 | 2019-11-28 09:16 | Kristin Ohnstad |  | Approved | 12.11.2019 07:15:00 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-11 12:15 | 2019-11-18 11:15 | 2019-11-11 12:11
CHG0031546 | DigiPlex Fet AS | Disk failure CCTV server A2 #2 | Emergency | Closed | 2019-11-11 14:00 | 2019-11-11 14:30 | Kristin Ohnstad | 2019-11-26 14:35 | 2019-11-26 14:35 | Kristin Ohnstad |  | Approved | 12.11.2019 10:44:18 - Karl Audun Lad (Approval history) Group approval for CAB Approval NO approved by user Karl Audun Lad (CAB approval). 11.11.2019 11:40:47 - Karl Audun Lad (Approval history) Group approval for eCAB Approval approved by user Karl Audun Lad (eCAB approval). | 2019-11-11 14:00 | 2019-11-11 14:30 | 2019-11-11 10:12
CHG0031545 | DigiPlex Norway AS | Checking the gas pressure in the Chiller C compressor 1 | Emergency | Implement | 2019-11-11 11:59 | 2019-11-15 11:59 |  | 2019-11-11 13:00 |  |  |  | Requested | 11.11.2019 11:59:57 - Anders Lundin Bjørnstad (Approval history) Group approval for approved by user Anders Lundin Bjørnstad (eCAB approval). | 2019-11-11 13:00 |  | 2019-11-11 09:56
CHG0031542 | DigiPlex Norway AS | Move Firewall port from old sw -012 to new core switch 01 and 02 | Normal | Closed | 2019-11-13 11:00 | 2019-11-13 16:30 |  | 2019-12-05 09:07 | 2019-12-05 09:07 | Kristin Ohnstad |  | Approved | 12.11.2019 12:03:09 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 11.11.2019 11:40:43 - Kristin Ohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-13 14:30 | 2019-12-02 16:30 | 2019-11-10 21:41
CHG0031541 | DigiPlex Norway AS | Swap switch di-ul-sw-019 in Ulvenvein to new switch | Normal | Closed | 2019-11-13 16:00 | 2019-11-13 18:30 |  | 2019-11-26 16:36 | 2019-11-26 16:36 | Kristin Ohnstad |  | Approved | 11.11.2019 11:37:44 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 11.11.2019 07:59:42 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-13 16:20 | 2019-11-13 18:00 | 2019-11-10 21:34
CHG0031540 | DigiPlex Stockholm 1 AB | Disassembly of crossbeams in steel structure | Normal | Closed | 2019-11-13 07:00 | 2019-11-15 17:00 |  | 2019-11-22 12:07 | 2019-11-22 12:07 | Kristin Ohnstad |  | Approved |  | 2019-11-13 07:00 | 2019-11-14 16:00 | 2019-11-09 10:26
CHG0031539 | DigiPlex Rosenholm AS | DRAS - PPM service på CCUer. | Normal | Closed | 2019-11-25 12:30 | 2019-12-06 12:30 |  | 2020-01-03 14:31 | 2020-01-03 14:31 | Kristin Ohnstad |  | Approved | 11.11.2019 07:22:16 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-25 13:01 | 2019-12-10 13:01 | 2019-11-08 12:22
CHG0031538 | DigiPlex Fet AS | Maintenance on turnstiles. | Normal | Closed | 2019-11-08 08:57 | 2019-11-08 08:57 |  | 2019-11-28 11:22 | 2019-11-28 11:22 | Dag Oscar Brækken |  | Approved | 12.11.2019 07:14:25 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-08 11:21 | 2019-11-08 11:21 | 2019-11-08 08:57
CHG0031537 | DigiPlex Rosenholm AS | DRAS - Minor service på generatorer | Normal | Closed | 2019-11-18 08:02 | 2019-11-20 08:02 |  | 2020-01-03 14:35 | 2020-01-03 14:35 | Kristin Ohnstad |  | Approved | 08.11.2019 22:28:55 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-18 15:42 | 2019-12-04 15:43 | 2019-11-08 08:02
CHG0031536 | DigiPlex Norway AS | Symmetra Annual maintenance | Normal | Implement | 2019-11-25 08:00 | 2019-11-29 16:00 |  | 2019-11-25 07:00 |  |  |  | Approved | 07.11.2019 18:42:07 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 07.11.2019 15:02:35 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-11-07 14:48
CHG0031535 | DigiPlex Norway AS | Uniflair Chiller Semi-Annual Maintenance | Normal | Closed | 2019-12-12 08:00 | 2019-12-19 16:00 |  | 2020-01-09 12:30 | 2020-01-09 12:30 | Kristin Ohnstad |  | Approved | 07.11.2019 18:40:14 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 07.11.2019 15:03:08 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-12-12 14:16 | 2019-12-19 14:16 | 2019-11-07 14:29
CHG0031534 | DigiPlex Norway AS | CCU CW Annual maintenance | Normal | Closed | 2019-11-25 08:00 | 2019-11-27 16:00 |  | 2019-12-05 09:08 | 2019-12-05 09:08 | Kristin Ohnstad |  | Approved | 07.11.2019 18:40:56 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 07.11.2019 15:02:06 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-25 08:00 | 2019-11-28 15:00 | 2019-11-07 14:10
CHG0031533 | DigiPlex Norway AS | CCU CW Annual maintenance | Normal | Closed | 2019-12-09 08:00 | 2019-12-09 16:00 |  | 2020-01-09 12:29 | 2020-01-09 12:29 | Kristin Ohnstad |  | Approved | 07.11.2019 18:40:32 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 07.11.2019 15:02:53 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-12-09 08:00 | 2019-12-09 16:00 | 2019-11-07 14:03
CHG0031532 | DigiPlex Fet AS | Enter your description here | Normal | Canceled | 2019-11-27 13:04 | 2019-11-27 13:04 |  | 2019-11-11 10:42 | 2019-11-11 10:42 | Frode Elden Kay |  | Requested |  |  |  | 2019-11-07 13:07
CHG0031531 | DigiPlex Norway AS | CCU CW Annual maintenance | Normal | Closed | 2019-11-21 08:00 | 2019-11-22 16:00 |  | 2019-11-28 09:15 | 2019-11-28 09:15 | Kristin Ohnstad |  | Approved | 07.11.2019 12:42:23 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 07.11.2019 12:41:48 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-21 09:30 | 2019-11-21 16:00 | 2019-11-07 12:37
CHG0031530 | DigiPlex Norway AS | Scanning of PLT room, POD PLT 01. | Normal | Review | 2019-11-08 08:00 | 2019-11-21 16:00 |  | 2020-01-09 12:42 |  |  |  | Approved | 12.11.2019 07:16:27 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 08.11.2019 10:37:01 - Rune Asak (Approval history) Group approval for Change-Technical assess group rejected by user Rune Asak (Technical approvals norway). | 2019-11-08 08:00 | 2019-11-20 16:00 | 2019-11-07 10:43
CHG0031529 | DigiPlex Fet AS | Maintenance on watermist systems. | Normal | Closed | 2019-11-22 10:31 | 2019-11-22 10:31 |  | 2019-11-28 11:33 | 2019-11-28 11:33 | Dag Oscar Brækken |  | Approved | 12.11.2019 07:16:00 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-22 11:32 | 2019-11-22 11:32 | 2019-11-07 09:32
CHG0031526 | DigiPlex Fet AS | Establish existing VLANs on new core switches in A1 and A2 | Normal | Closed | 2019-11-11 08:00 | 2019-11-11 16:19 |  | 2019-11-12 20:59 | 2019-11-12 20:49 | Kristin Ohnstad |  | Approved | 06.11.2019 20:58:43 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). 06.11.2019 18:48:37 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-11 15:59 | 2019-11-11 17:00 | 2019-11-06 16:23
CHG0031525 | DigiPlex Rosenholm AS | DRAS - Konfigurering av adgangskontroll, CCTV og innbruddsalarm | Normal | Closed | 2019-11-18 07:40 | 2019-11-29 14:40 |  | 2020-01-07 15:20 | 2020-01-07 15:20 | Kristin Ohnstad |  | Approved | 08.11.2019 07:33:29 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 06.11.2019 15:20:25 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-18 13:04 | 2019-12-13 13:04 | 2019-11-06 14:42
CHG0031524 | DigiPlex Rosenholm AS | DRAS - kabeltrekking til nytt kontor | Normal | Closed | 2019-11-11 14:26 | 2019-12-06 14:26 |  | 2019-11-28 08:56 | 2019-11-28 08:56 | Anders Lundin Bjørnstad |  | Approved | 07.11.2019 22:49:53 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). | 2019-11-11 08:55 | 2019-11-25 08:55 | 2019-11-06 14:27
CHG0031523 | DigiPlex Rosenholm AS | DRAS - Flytte kontorer | Normal | Canceled | 2019-11-06 09:20 | 2019-12-31 09:20 |  | 2019-11-06 14:28 | 2019-11-06 14:28 | Anders Lundin Bjørnstad |  | Rejected | 06.11.2019 14:11:09 - Kristin Ohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-11-06 09:21
CHG0031522 | DigiPlex Norway AS | Swap "SW91" and 3 old HP switches in -01PLT01 | Normal | Closed | 2019-11-06 17:09 | 2019-11-07 17:09 |  | 2019-11-12 20:38 | 2019-11-12 20:38 | Kristin Ohnstad |  | Approved | 06.11.2019 08:23:15 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). | 2019-11-07 08:06 | 2019-11-07 08:06 | 2019-11-05 17:10
CHG0031521 | DigiPlex Rosenholm AS | DRAS - Utskifting av flaskebank | Normal | Closed | 2019-11-11 10:14 | 2019-11-26 10:14 |  | 2020-01-03 14:34 | 2020-01-03 14:34 | Kristin Ohnstad |  | Approved | 06.11.2019 14:20:51 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 06.11.2019 14:19:49 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-11 11:54 | 2019-12-05 15:40 | 2019-11-05 15:27
CHG0031518 | DigiPlex Fet AS | Milestone CCTV recording server device driver update | Emergency | Closed | 2019-11-04 20:30 | 2019-11-04 22:00 |  | 2019-11-22 08:39 | 2019-11-22 08:39 | Kristin Ohnstad |  | Approved | 07.11.2019 09:06:30 - Atle Torp (Approval history) Group approval for CAB Approval NO approved by user Atle Torp (CAB approval). 04.11.2019 19:59:09 - Halvor Bjerke (Approval history) Group approval for approved by user Halvor Bjerke (eCAB approval). | 2019-11-04 21:00 | 2019-11-04 22:00 | 2019-11-04 19:52
CHG0031517 | DigiPlex Rosenholm AS | R01MOD04.2, cable trays, BMS and CAC | Normal | Closed | 2019-11-04 19:01 | 2019-11-29 19:01 |  | 2020-01-03 14:28 | 2020-01-03 14:28 | Kristin Ohnstad |  | Approved | 05.11.2019 07:22:27 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-05 08:18 | 2019-11-26 16:00 | 2019-11-04 19:07
CHG0031516 | DigiPlex Norway AS | reparer rampe | Normal | Closed | 2019-11-05 09:57 | 2019-11-07 09:57 |  | 2019-11-11 11:42 | 2019-11-11 11:42 | Kristin Ohnstad |  | Approved | 04.11.2019 11:51:08 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 04.11.2019 11:04:57 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-05 16:00 | 2019-11-06 15:00 | 2019-11-04 09:56
CHG0031515 | DigiPlex Norway AS | Fylle opp gassflasker for slukke gass i 00PLT02. | Normal | Closed | 2019-11-04 09:13 | 2019-11-04 16:00 |  | 2019-11-12 20:35 | 2019-11-12 20:35 | Kristin Ohnstad |  | Approved | 05.11.2019 09:09:22 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 04.11.2019 16:42:37 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-04 10:00 | 2019-11-04 16:00 | 2019-11-04 09:31
CHG0031513 | DigiPlex Norway AS | Power migration | Normal | Canceled | 2019-12-04 08:00 | 2019-12-05 16:00 |  | 2019-11-26 17:44 | 2019-11-26 15:40 | Frode Elden Kay |  | Approved | 07.11.2019 12:48:40 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 04.11.2019 16:42:10 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-11-04 09:24
CHG0031512 | DigiPlex Norway AS | Mapping av rør i kjølekretsen, må inn og se under gulv over alt. | Normal | Implement | 2019-11-04 11:35 | 2019-11-08 11:35 |  | 2019-11-04 11:00 |  |  | 2019-11-01 | Approved | 04.11.2019 07:13:17 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-04 11:35 |  | 2019-11-01 11:38
CHG0031508 | DigiPlex Stockholm 1 AB | Scaffolding in corridor to mount cabling and busbars | Normal | Closed | 2019-11-06 08:30 | 2019-11-15 18:00 |  | 2019-12-19 14:08 | 2019-12-19 14:08 | Kristin Ohnstad |  | Approved |  | 2019-11-10 07:00 | 2019-11-22 15:00 | 2019-10-31 16:35
CHG0031507 | DigiPlex Stockholm 1 AB | Drilling of holes in facade for cable inlets, C-string | Normal | Closed | 2019-11-04 08:00 | 2019-11-30 16:30 |  | 2019-11-22 12:06 | 2019-11-22 12:06 | Kristin Ohnstad |  | Approved |  | 2019-11-07 07:00 | 2019-11-07 16:00 | 2019-10-31 16:27
CHG0031506 | DigiPlex Rosenholm AS | Vask av gulv | Normal | Closed | 2019-11-04 12:41 | 2019-11-04 12:41 |  | 2019-11-12 20:47 | 2019-11-12 20:47 | Kristin Ohnstad |  | Approved | 01.11.2019 08:25:27 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-04 10:48 | 2019-11-04 14:00 | 2019-10-31 12:41
CHG0031505 | DigiPlex Stockholm 1 AB | BMS integration of AHU | Normal | Closed | 2019-11-05 07:00 | 2019-11-07 18:00 |  | 2019-11-22 12:07 | 2019-11-22 12:07 | Kristin Ohnstad |  | Approved |  | 2019-11-05 09:00 | 2019-11-07 14:00 | 2019-10-30 17:13
CHG0031504 | DigiPlex Fet AS | Reparasjon av kuldeboksene i taket i MSFT kontorene i A3.2 | Normal | Implement | 2019-10-31 07:57 | 2019-10-31 07:57 |  | 2019-11-19 08:26 |  |  |  | Approved | 31.10.2019 08:12:26 - Dag Oscar Brækken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2019-10-30 07:57
CHG0031503 | DigiPlex Norway AS | Move BMS connection Vlan 16 from old HP and 3Com switch to new Cisco switch in cabling rack | Normal | Closed | 2019-11-04 10:00 | 2019-11-04 15:00 |  | 2019-11-12 20:31 | 2019-11-12 20:31 | Kristin Ohnstad |  | Approved | 31.10.2019 05:43:57 - Karl Audun Lad (Approval history) Group approval for Change-Technical assess group approved by user Karl Audun Lad (Technical approvals norway). | 2019-11-04 15:57 | 2019-11-04 15:57 | 2019-10-29 20:30
CHG0031502 | DigiPlex Stockholm 1 AB | Roof repair | Normal | Closed | 2019-10-30 14:30 | 2019-10-30 17:00 |  | 2019-10-31 14:01 | 2019-10-31 14:01 | Christian Eghult |  | Approved |  | 2019-10-30 14:31 | 2019-10-30 17:00 | 2019-10-29 15:13
CHG0031501 | DigiPlex Fet AS | Lekkasje i brotaket til MSFT kontorer i 2.etasje | Normal | Implement | 2019-10-30 14:23 | 2019-11-15 14:23 |  | 2019-10-30 15:00 |  |  |  | Approved | 29.10.2019 07:41:16 - Dag Oscar Brækken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 28.10.2019 15:28:56 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-10-28 14:12
CHG0031500 | DigiPlex Fet AS | Lekkasje i brotaket til MSFT kontorer i 2.etasje | Normal | Canceled | 2019-10-30 11:52 | 2019-11-15 11:52 | Kristin Ohnstad | 2019-10-30 10:24 | 2019-10-28 15:29 | Kristin Ohnstad |  | Requested |  |  |  | 2019-10-28 11:47
CHG0031494 | DigiPlex Norway AS | Gen A, testing Deep Sea software. | Normal | Closed | 2019-10-29 11:01 | 2019-11-29 10:54 |  | 2019-11-05 09:17 | 2019-11-05 09:17 | Kristin Ohnstad |  | Approved | 29.10.2019 10:51:54 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-10-31 08:00 | 2019-10-31 16:00 | 2019-10-28 11:02
CHG0031493 | DigiPlex Fet AS | Monthly check of Emergency Lighting and General Lighting | Standard | Canceled |  |  |  | 2019-10-28 11:06 | 2019-10-28 11:06 | Bjørn W Sætre |  | Approved |  |  |  | 2019-10-28 10:55
CHG0031492 | DigiPlex Fet AS | One fiber patch cable is squeezed in rack. | Normal | Closed | 2019-10-28 12:24 | 2019-10-28 12:24 |  | 2019-10-31 08:07 | 2019-10-31 08:07 | Kristin Ohnstad |  | Approved | 29.10.2019 07:20:44 - Dag Oscar Brækken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2019-10-30 07:43 | 2019-10-30 07:43 | 2019-10-26 12:26
CHG0031491 | DigiPlex Norway AS | Reactive repair access control system | Normal | Closed | 2019-10-31 08:00 | 2019-10-31 16:00 |  | 2019-11-12 20:48 | 2019-11-12 20:48 | Kristin Ohnstad |  | Approved | 28.10.2019 07:42:00 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-10-31 09:00 | 2019-10-31 15:00 | 2019-10-25 11:42
CHG0031490 | DigiPlex Norway AS | Vaske Apron | Normal | Closed | 2019-10-26 08:00 | 2019-10-27 16:00 |  | 2019-11-05 09:15 | 2019-11-05 09:15 | Kristin Ohnstad |  | Approved | 25.10.2019 11:31:23 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 25.10.2019 11:28:43 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-26 08:00 | 2019-11-26 16:00 | 2019-10-25 10:42
CHG0031489 | DigiPlex Norway AS | POD PLT 01, 1 way valve | Normal | Implement | 2019-10-25 14:53 | 2019-11-29 14:53 |  | 2019-10-25 14:00 |  |  |  | Approved | 25.10.2019 09:38:39 - Geir Almquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 24.10.2019 16:06:21 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-10-24 14:59
CHG0031488 | DigiPlex Norway AS | Replace defect patch cable to BMS in 00PLT01 | Emergency | Closed | 2019-10-24 15:01 | 2019-10-24 15:01 |  | 2019-11-12 20:24 | 2019-11-12 20:24 | Kristin Ohnstad |  | Approved | 24.10.2019 16:02:39 - Pål Rune Viken (Approval history) Group approval for CAB Approval NO approved by user Pål Rune Viken (CAB approval). 24.10.2019 15:04:34 - Pål Rune Viken (Approval history) Group approval for approved by user Pål Rune Viken (eCAB approval). | 2019-10-24 16:00 | 2019-10-24 16:04 | 2019-10-24 15:01
CHG0031486 | DigiPlex Norway AS | Raise roof in the CAC to get room for 48U racks. | Normal | Closed | 2019-11-03 08:00 | 2019-11-08 16:00 |  | 2019-11-21 08:38 | 2019-11-21 08:38 | Kristin Ohnstad |  | Approved | 23.10.2019 15:35:07 - Lars Valseth (Approval history) Group approval for Change-Technical assess group approved by user Lars Valseth (Technical approvals norway). 23.10.2019 13:09:07 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-06 08:00 | 2019-11-08 14:00 | 2019-10-23 09:02
CHG0031485 | DigiPlex Fet AS | LOR 3. Monthly test of generators. | Normal | Closed | 2019-11-12 08:00 | 2019-11-21 08:01 | Kristin Ohnstad | 2019-11-21 13:27 | 2019-11-21 13:27 | Dag Oscar Brækken |  | Approved | 23.10.2019 11:16:06 - Anders Lundin Bjørnstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). 23.10.2019 11:03:24 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-12 12:52 | 2019-11-21 12:53 | 2019-10-23 08:07
CHG0031484 | DigiPlex Norway AS | Replace di-ul-sw10,11,12,13 and 14 with new Cisco switches | Normal | Closed | 2019-10-23 11:03 | 2019-11-07 11:03 |  | 2019-11-26 14:14 | 2019-11-26 14:14 | Kristin Ohnstad |  | Approved | 24.10.2019 09:09:53 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-10-23 16:25 | 2019-11-25 16:25 | 2019-10-22 11:09
CHG0031480 | DigiPlex Norway AS | Fjerning av rust med blåsing av tørris. maling og isolering. | Normal | Closed | 2019-10-22 11:43 | 2019-10-22 16:00 | Kristin Ohnstad | 2019-11-12 20:33 | 2019-11-12 20:33 | Kristin Ohnstad |  | Approved | 22.10.2019 10:24:24 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 22.10.2019 09:59:25 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-22 08:39 | 2019-11-06 14:39 | 2019-10-22 09:44
CHG0031479 | DigiPlex Norway AS | Garanti kontroll av 6 brytere i UPS a og UPS B | Normal | Closed | 2019-10-22 10:01 | 2019-10-22 16:01 | Kristin Ohnstad | 2019-11-12 20:32 | 2019-11-12 20:32 | Kristin Ohnstad |  | Approved | 22.10.2019 10:22:46 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 21.10.2019 16:19:55 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-22 08:43 | 2019-10-22 14:43 | 2019-10-21 15:37
CHG0031478 | DigiPlex Norway AS | Install 2 new Cisco switches in old cabling rack in 00PLT01 | Normal | Closed | 2019-10-23 10:32 | 2019-10-28 10:32 |  | 2019-10-31 08:07 | 2019-10-31 08:07 | Kristin Ohnstad |  | Approved | 24.10.2019 09:08:58 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-10-28 19:55 | 2019-10-28 19:55 | 2019-10-21 10:34
CHG0031477 | DigiPlex Rosenholm AS | DRAS - Fiberkabling til nye kontorområder | Normal | Closed | 2019-10-28 10:03 | 2019-12-13 10:03 |  | 2020-01-03 14:33 | 2020-01-03 14:33 | Kristin Ohnstad |  | Approved | 25.10.2019 07:11:45 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-11-18 13:02 | 2019-12-02 13:02 | 2019-10-21 10:04
CHG0031476 | DigiPlex Norway AS | Chang global configuration on old Cisco switch di-ul-sw093. This switch have a VTP server configured. VTP server push VLAN configuration to the network. | Normal | Closed | 2019-10-23 09:53 | 2019-10-23 09:53 |  | 2019-10-31 08:06 | 2019-10-31 08:06 | Kristin Ohnstad |  | Approved | 24.10.2019 09:10:27 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-10-24 14:38 | 2019-10-24 14:39 | 2019-10-21 09:56
CHG0031473 | DigiPlex Norway AS | Montere telt og demontere rør insulation | Normal | Closed | 2019-10-21 10:32 | 2019-10-22 15:32 |  | 2019-12-05 09:08 | 2019-12-05 09:08 | Kristin Ohnstad |  | Approved | 21.10.2019 10:17:02 - Patrick Bakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 21.10.2019 10:16:12 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-21 08:32 | 2019-10-31 08:32 | 2019-10-21 08:35
CHG0031472 | DigiPlex Norway AS | Swap old 8 port switches with new managed switches | Normal | Closed | 2019-10-21 14:04 | 2019-11-07 14:04 |  | 2019-11-26 14:14 | 2019-11-26 14:14 | Kristin Ohnstad |  | Approved | 22.10.2019 17:53:12 - Alexander Olsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-10-31 10:46 | 2019-11-07 10:48 | 2019-10-18 13:18
CHG0031468 | DigiPlex Rosenholm AS | DRAS - Service på CCUer R02 | Normal | Closed | 2019-10-22 11:34 | 2019-10-25 11:34 |  | 2019-11-05 09:17 | 2019-11-05 09:17 | Kristin Ohnstad |  | Approved | 21.10.2019 06:21:04 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 18.10.2019 13:54:38 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-24 09:00 | 2019-10-25 09:00 | 2019-10-18 11:34
CHG0031467 | DigiPlex Norway AS | Loading bay, PLS control. | Normal | Implement | 2019-10-21 10:12 | 2019-11-29 10:18 |  | 2019-11-11 15:00 |  |  |  | Approved | 11.11.2019 11:24:07 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 21.10.2019 06:23:36 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 18.10.2019 13:53:54 - Kristin Ohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-10-18 10:19
CHG0031463 | DigiPlex Norway AS | CCR-A2 and CCR-B, new feed to existing rack. | Normal | Implement | 2019-10-17 12:31 | 2019-11-29 12:31 |  | 2019-10-17 12:00 |  |  |  | Approved | 17.10.2019 08:18:02 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-10-16 12:36
CHG0031460 | DigiPlex Rosenholm AS | Unmount decommisioned servers from rack DRAS CCRA | Normal | Implement | 2019-10-15 09:00 | 2019-10-17 16:00 |  | 2019-10-23 11:30 |  |  | 2019-10-10 | Approved | 10.10.2019 09:22:40 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 10.10.2019 09:18:07 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-21 10:00 | 2019-10-23 11:26 | 2019-10-09 15:43
CHG0031459 | DigiPlex Rosenholm AS | DRAS - Flytte tilførselskabler til =493.03-FS05 | Normal | Closed | 2019-10-14 07:45 | 2019-10-25 13:45 |  | 2020-01-07 15:19 | 2020-01-07 15:19 | Kristin Ohnstad |  | Approved | 10.10.2019 09:07:53 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-10-14 08:37 | 2019-11-13 13:03 | 2019-10-09 13:46
CHG0031458 | DigiPlex Norway AS | Replace Tap-off boxes in 03MOD03.2 | Normal | Closed | 2019-10-10 22:00 | 2019-10-10 23:59 |  | 2019-10-18 14:00 | 2019-10-18 14:00 | Kristin Ohnstad |  | Approved | 10.10.2019 08:38:24 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 09.10.2019 15:25:55 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-10 22:01 | 2019-10-10 23:00 | 2019-10-09 08:05
CHG0031456 | DigiPlex Rosenholm AS | DRAS - Test av tilførselskabler til UH3.3 | Normal | Closed | 2019-10-09 07:25 | 2019-10-09 15:25 |  | 2019-10-18 14:01 | 2019-10-18 14:01 | Kristin Ohnstad |  | Approved | 09.10.2019 09:37:44 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 08.10.2019 15:31:50 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-09 10:35 | 2019-10-09 13:35 | 2019-10-08 15:26
CHG0031455 | DigiPlex Rosenholm AS | DRAS - Service på sluse | Normal | Closed | 2019-10-17 14:43 | 2019-10-17 14:44 |  | 2019-11-12 20:34 | 2019-11-12 20:34 | Kristin Ohnstad |  | Approved | 08.10.2019 06:52:26 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-10-17 08:55 | 2019-10-17 13:56 | 2019-10-07 14:44
CHG0031453 | DigiPlex Fet AS | Monthly test of generators. | Normal | Canceled | 2019-10-14 14:12 | 2019-10-18 14:13 | Kristin Ohnstad | 2019-10-23 08:12 | 2019-10-23 08:12 | Dag Oscar Brækken |  | Approved | 09.10.2019 11:48:26 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-10-07 14:12
CHG0031452 | DigiPlex Norway AS | lowering busbar | Normal | Closed | 2019-10-07 11:00 | 2019-10-07 15:00 |  | 2019-11-05 09:19 | 2019-11-05 09:19 | Kristin Ohnstad |  | Approved | 07.10.2019 10:40:29 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 07.10.2019 10:35:35 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-07 12:00 | 2019-10-07 14:30 | 2019-10-07 10:33
CHG0031451 | DigiPlex Rosenholm AS | DRAS - Service på pumper | Normal | Closed | 2019-10-09 08:54 | 2019-10-09 08:54 |  | 2019-11-05 09:14 | 2019-11-05 09:14 | Kristin Ohnstad |  | Approved | 07.10.2019 10:46:31 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 07.10.2019 09:33:30 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-09 08:48 | 2019-10-09 16:48 | 2019-10-07 08:55
CHG0031450 | DigiPlex Norway AS | Reactive maintenance/repair generator B | Normal | Closed | 2019-11-04 08:00 | 2019-11-08 16:00 |  | 2019-11-26 14:13 | 2019-11-26 14:13 | Kristin Ohnstad |  | Approved | 09.10.2019 11:52:06 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 03.10.2019 17:36:37 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-04 09:00 | 2019-11-06 16:00 | 2019-10-03 14:15
CHG0031449 | DigiPlex Stockholm 1 AB | DS1 UPS Annual Maintenance | Normal | Closed | 2019-10-07 07:00 | 2019-10-13 18:00 |  | 2019-10-24 08:57 | 2019-10-24 08:57 | Christian Eghult |  | Approved | 03.10.2019 14:05:41 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-07 08:36 | 2019-10-13 17:00 | 2019-10-03 13:47
CHG0031448 | DigiPlex Norway AS | Annual generator D maintenance | Normal | Closed | 2019-10-30 08:00 | 2019-11-01 16:00 |  | 2019-11-12 22:09 | 2019-11-12 22:09 | Kristin Ohnstad |  | Approved | 10.10.2019 12:23:35 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 03.10.2019 17:36:01 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-30 08:00 | 2019-10-30 16:00 | 2019-10-03 13:41
CHG0031447 | DigiPlex Stockholm 1 AB | Crane lift from roof | Normal | Closed | 2019-10-04 09:00 | 2019-10-04 14:00 |  | 2019-10-17 09:02 | 2019-10-17 09:02 | Kristin Ohnstad |  | Approved | 03.10.2019 14:04:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-04 09:00 | 2019-10-04 14:00 | 2019-10-03 12:24
CHG0031446 | DigiPlex Norway AS | Annual generator A maintenance | Normal | Closed | 2019-10-28 08:00 | 2019-10-29 16:00 |  | 2019-11-12 22:10 | 2019-11-12 22:10 | Kristin Ohnstad |  | Approved | 09.10.2019 11:51:02 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 03.10.2019 17:36:58 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-28 09:00 | 2019-10-28 16:00 | 2019-10-03 11:20
CHG0031444 | DigiPlex Stockholm 1 AB | Yearly scheduled maintenance/inspection of HV and LV switchgears, breakers and transformers for all power pods at DS1 | Normal | Closed | 2019-10-04 08:00 | 2019-10-05 18:00 |  | 2019-10-10 14:08 | 2019-10-10 14:08 | Kristin Ohnstad |  | Approved | 03.10.2019 14:04:03 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-04 08:00 | 2019-10-05 17:00 | 2019-10-03 07:47
CHG0031443 | DigiPlex Norway AS | 03MOD03.2, relocating existing busbars. | Normal | Closed | 2019-10-07 15:19 | 2019-10-11 15:19 |  | 2019-11-05 09:21 | 2019-11-05 09:21 | Kristin Ohnstad |  | Approved | 08.10.2019 06:51:44 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-10-10 12:31 | 2019-10-10 12:31 | 2019-10-02 15:22
CHG0031441 | DigiPlex Norway AS | Fiber cabling 00Mod01.5->CCR-B | Normal | Closed | 2019-10-01 07:00 | 2019-10-04 16:00 |  | 2019-11-05 09:14 | 2019-11-05 09:14 | Kristin Ohnstad |  | Approved | 30.09.2019 08:54:23 - lvalseth (Approval history) Group approval for Change-Technical assess group approved by user Lars Valseth (Technical approvals norway). | 2019-10-01 07:30 | 2019-10-03 16:00 | 2019-09-27 16:00
CHG0031440 | DigiPlex Norway AS | 03MOD03.4, replace faulty address unti. | Normal | Closed | 2019-09-30 13:47 | 2019-11-01 13:53 |  | 2019-11-26 14:13 | 2019-11-26 14:13 | Kristin Ohnstad |  | Approved | 07.10.2019 09:41:14 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-10-23 12:00 | 2019-10-24 14:00 | 2019-09-27 13:54
CHG0031439 | DigiPlex Norway AS | 02MOD04, core drilling. | Normal | Implement | 2019-09-30 09:26 | 2019-10-25 09:26 |  | 2019-10-07 14:00 |  |  |  | Approved | 07.10.2019 11:51:10 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). |  |  | 2019-09-27 09:34
CHG0031438 | DigiPlex Norway AS | Fiber cabling 02Mod06.3->CCR-A2 and CCR-B | Normal | Closed | 2019-09-30 08:00 | 2019-10-18 16:00 |  | 2019-11-05 09:13 | 2019-11-05 09:13 | Kristin Ohnstad |  | Approved | 26.09.2019 11:47:59 - lvalseth (Approval history) Group approval for Change-Technical assess group approved by user Lars Valseth (Technical approvals norway). | 2019-10-01 07:30 | 2019-10-03 16:00 | 2019-09-25 10:07
CHG0031437 | DigiPlex Stockholm 1 AB | Balancing air flow | Normal | Closed | 2019-09-30 07:00 | 2019-10-11 18:00 |  | 2019-10-18 13:59 | 2019-10-18 13:59 | Kristin Ohnstad |  | Approved |  | 2019-09-30 07:00 | 2019-10-03 15:00 | 2019-09-23 14:03
CHG0031434 | DigiPlex Stockholm 1 AB | Core drilling into DH8 | Normal | Closed | 2019-10-01 07:00 | 2019-10-01 18:00 |  | 2019-11-07 12:48 | 2019-11-07 12:48 | Christian Eghult |  | Approved |  | 2019-10-01 09:00 | 2019-10-01 12:00 | 2019-09-19 16:25
CHG0031433 | DigiPlex Rosenholm AS | DRAS - Installere brannklokke i CCR-A og MOD 06 | Normal | Implement | 2019-09-19 14:25 | 2019-10-11 14:25 |  | 2019-09-19 18:00 |  |  |  | Approved | 19.09.2019 16:35:21 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 19.09.2019 15:46:13 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-09-19 14:25
CHG0031432 | DigiPlex Rosenholm AS | DRAS - Rep av Gen 3.3 | Normal | Closed | 2019-09-19 14:05 | 2019-10-31 14:05 |  | 2019-11-05 09:12 | 2019-11-05 09:12 | Kristin Ohnstad |  | Approved | 19.09.2019 16:35:20 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 19.09.2019 15:45:19 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-19 08:58 | 2019-10-25 08:58 | 2019-09-19 14:05
CHG0031431 | DigiPlex Norway AS | Repprasjon av feil på DX etter årlig service. | Normal | Closed | 2019-09-19 11:13 | 2019-09-20 11:13 |  | 2019-10-07 09:39 | 2019-10-07 09:39 | Geir Almquist |  | Approved | 18.09.2019 12:12:57 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 18.09.2019 11:51:57 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-19 11:28 | 2019-09-23 11:29 | 2019-09-18 11:13
CHG0031429 | DigiPlex Stockholm 1 AB | Replacing Munters Ducting | Normal | Closed | 2019-09-18 07:00 | 2019-10-04 18:00 |  | 2019-10-18 14:00 | 2019-10-18 14:00 | Kristin Ohnstad |  | Approved |  | 2019-09-30 07:00 | 2019-10-04 15:00 | 2019-09-16 13:38
CHG0031428 | DigiPlex Norway AS | Master drawing update | Normal | Closed | 2019-09-16 09:20 | 2019-09-30 16:00 |  | 2019-11-05 09:11 | 2019-11-05 09:11 | Kristin Ohnstad |  | Approved | 16.09.2019 09:35:19 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 16.09.2019 09:23:54 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-17 08:00 | 2019-10-30 14:38 | 2019-09-16 09:20
CHG0031427 | DigiPlex Norway AS | Master drawing update | Normal | Canceled | 2019-09-16 09:05 | 2019-09-30 16:00 |  | 2019-09-16 09:20 | 2019-09-16 09:20 | John Petter Jahr |  | Requested |  |  |  | 2019-09-16 09:04
CHG0031425 | DigiPlex Stockholm 1 AB | Installation of new outdoor DX unit | Normal | Closed | 2019-09-30 07:00 | 2019-10-01 17:00 |  | 2019-10-31 14:09 | 2019-10-31 14:09 | Christian Eghult |  | Approved |  | 2019-09-30 08:00 | 2019-10-23 13:07 | 2019-09-12 18:57
CHG0031423 | DigiPlex Stockholm 1 AB | Fuel Installation | Normal | Closed | 2019-09-30 07:00 | 2019-09-30 17:00 |  | 2019-11-22 12:04 | 2019-11-22 12:04 | Kristin Ohnstad |  | Approved | 12.09.2019 14:33:21 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-30 10:14 | 2019-09-30 16:14 | 2019-09-12 10:18
CHG0031422 | DigiPlex Stockholm 1 AB | Yearly maintenance of DS1 generators | Normal | Closed | 2019-09-16 07:00 | 2019-09-20 20:00 |  | 2019-10-10 14:20 | 2019-10-10 14:20 | Kristin Ohnstad |  | Approved |  | 2019-09-16 08:30 | 2019-09-20 17:30 | 2019-09-12 09:51
CHG0031421 | DigiPlex Fet AS | Disconnect Munters units from Network. | Normal | Closed | 2019-09-17 08:31 | 2019-09-17 08:31 |  | 2019-09-26 07:29 | 2019-09-26 07:29 | Kristin Ohnstad |  | Approved | 16.09.2019 15:28:26 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-09-17 13:59 | 2019-09-17 13:59 | 2019-09-12 08:33
CHG0031419 | DigiPlex Stockholm 1 AB | De-snagging inside DH7.3 | Normal | Closed | 2019-09-12 12:00 | 2019-09-12 17:00 |  | 2019-10-31 14:02 | 2019-10-31 14:02 | Christian Eghult |  | Approved |  | 2019-09-12 12:16 | 2019-09-12 16:45 | 2019-09-11 12:01
CHG0031417 | DigiPlex Rosenholm AS | DRAS - 6M Service på BMS | Normal | Closed | 2019-09-16 11:02 | 2019-09-20 11:02 |  | 2019-09-26 11:02 | 2019-09-26 11:02 | Kristin Ohnstad |  | Approved | 11.09.2019 12:46:14 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 10.09.2019 11:04:17 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-18 08:23 | 2019-09-19 16:23 | 2019-09-10 11:02
CHG0031415 | DigiPlex Norway AS | BMS Service DNAS | Normal | Closed | 2019-09-16 10:45 | 2019-09-20 10:45 |  | 2019-10-31 09:56 | 2019-10-31 09:56 | Patrick Bakke | 2019-09-12 | Approved | 11.09.2019 12:45:36 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 10.09.2019 11:06:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-16 10:45 | 2019-09-20 10:45 | 2019-09-10 10:37
CHG0031411 | DigiPlex Norway AS | BSM Service | Normal | Canceled | 2019-09-16 07:00 | 2019-09-20 20:00 |  | 2019-09-10 11:00 | 2019-09-10 11:00 |  | 2019-09-12 | Not Yet Requested |  | 2019-09-16 07:00 | 2019-09-20 20:00 | 2019-09-10 10:20
CHG0031410 | DigiPlex Norway AS | '-01MOD01.2 + -01MOD09, upgrading CCU electrical distrubution. | Normal | Implement | 2019-09-10 13:42 | 2019-11-01 13:42 |  | 2019-10-02 12:45 |  |  |  | Approved | 13.09.2019 14:51:59 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). |  |  | 2019-09-09 13:47
CHG0031409 | DigiPlex Norway AS | '-01PLT04, replacing LLCS -01/07 | Normal | Implement | 2019-09-10 13:21 | 2019-11-01 13:21 |  | 2019-09-16 10:00 |  |  |  | Approved | 13.09.2019 14:47:38 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). |  |  | 2019-09-09 13:26
CHG0031408 | DigiPlex Rosenholm AS | DRAS - Årlig service på kortleser og kamera systemer. | Normal | Closed | 2019-09-24 08:42 | 2019-09-24 08:42 |  | 2019-09-26 11:02 | 2019-09-26 11:02 | Kristin Ohnstad |  | Approved | 06.09.2019 21:14:51 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-09-24 08:39 | 2019-09-24 15:39 | 2019-09-06 08:51
CHG0031407 | DigiPlex Stockholm 1 AB | Reroute office ducting | Normal | Closed | 2019-09-10 07:00 | 2019-09-13 18:00 |  | 2019-09-19 14:38 | 2019-09-19 14:38 |  |  | Approved |  | 2019-09-13 07:00 | 2019-09-13 17:00 | 2019-09-06 08:32
CHG0031406 | DigiPlex Rosenholm AS | DRAS - Årlig termofotografering | Normal | Closed | 2019-09-09 07:41 | 2019-09-13 07:41 |  | 2019-09-26 11:01 | 2019-09-26 11:01 | Kristin Ohnstad |  | Approved | 06.09.2019 21:14:50 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-09-12 11:24 | 2019-09-23 11:24 | 2019-09-06 07:41
CHG0031405 | DigiPlex Rosenholm AS | DRAS, relocating BMS sensores. | Normal | Closed | 2019-09-09 14:27 | 2019-10-25 14:27 |  | 2019-09-26 11:01 | 2019-09-26 11:01 | Kristin Ohnstad |  | Approved | 06.09.2019 06:57:52 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-09-16 08:37 | 2019-09-23 08:37 | 2019-09-05 14:31
CHG0031403 | DigiPlex Norway AS | Fire sealing shaft. | Normal | Closed | 2019-09-04 09:32 | 2019-11-01 09:32 |  | 2019-11-12 20:26 | 2019-11-12 20:26 | Kristin Ohnstad |  | Approved | 04.09.2019 15:01:20 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 04.09.2019 12:20:12 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-04 09:32 | 2019-10-31 14:40 | 2019-09-04 09:45
CHG0031402 | DigiPlex Fet AS | Install Netapp storage A1 & A2 for CCTV storage William | Normal | Closed | 2019-09-06 09:00 | 2019-09-06 13:00 |  | 2019-11-26 14:12 | 2019-11-26 14:12 | Kristin Ohnstad | 2019-09-05 | Approved | 10.10.2019 09:22:13 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 05.09.2019 09:16:26 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-06 10:00 | 2019-09-06 15:00 | 2019-09-04 07:54
CHG0031398 | DigiPlex Norway AS | 02MOD04, turning off power Lab rectifier. | Normal | Closed | 2019-09-04 08:30 | 2019-10-11 08:30 |  | 2019-09-26 11:00 | 2019-09-26 11:00 | Kristin Ohnstad |  | Approved | 06.09.2019 11:18:24 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-09-09 10:00 | 2019-09-11 12:00 | 2019-09-03 08:43
CHG0031397 | DigiPlex Stockholm 1 AB | DH7.2 Plenum retrofit | Normal | Closed | 2019-09-04 07:00 | 2019-09-13 18:00 |  | 2019-10-17 09:02 | 2019-10-17 09:02 | Kristin Ohnstad |  | Approved |  | 2019-09-23 07:00 | 2019-09-27 17:00 | 2019-09-02 15:56
CHG0031396 | DigiPlex Norway AS | Kontroll av DX i 02 mod08 og -01mod09 | Normal | Closed | 2019-09-02 08:57 | 2019-09-03 16:57 |  | 2019-10-18 14:01 | 2019-10-18 14:01 | Kristin Ohnstad |  | Approved | 02.09.2019 14:20:20 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 02.09.2019 12:31:08 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-03 09:28 | 2019-09-03 09:28 | 2019-09-02 08:58
CHG0031395 | DigiPlex Stockholm 1 AB | Ducting measurement | Normal | Closed | 2019-09-02 08:31 | 2019-09-06 08:31 |  | 2019-09-19 14:39 | 2019-09-19 14:39 |  |  | Approved | 30.08.2019 08:46:32 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-04 07:00 | 2019-09-05 17:00 | 2019-08-30 08:38
CHG0031394 | DigiPlex Norway AS | Service på Chillere av Schneider/ABK | Normal | Closed | 2019-09-03 10:32 | 2019-09-24 10:32 |  | 2019-10-18 14:15 | 2019-10-18 14:15 | Kristin Ohnstad | 2019-08-29 | Approved | 30.08.2019 15:29:02 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-09-03 15:07 | 2019-10-24 15:07 | 2019-08-29 11:06
CHG0031393 | DigiPlex Stockholm 1 AB | Installation of Troax wall in DH7.2 | Normal | Closed | 2019-08-29 12:00 | 2019-09-13 16:00 |  | 2019-09-19 14:42 | 2019-09-19 14:42 |  |  | Approved | 29.08.2019 10:51:24 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-08-29 14:00 | 2019-09-05 17:00 | 2019-08-29 09:24
CHG0031392 | DigiPlex Norway AS | Annual UPS maintenance | Normal | Closed | 2019-09-09 08:00 | 2019-09-14 16:00 |  | 2019-09-19 09:20 | 2019-09-19 09:20 |  |  | Approved | 02.09.2019 08:07:38 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 29.08.2019 10:54:52 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-08 09:00 | 2019-09-14 17:00 | 2019-08-29 09:10
CHG0031391 | DigiPlex Stockholm 1 AB | Repair Munters Process Water | Normal | Closed | 2019-09-09 07:00 | 2019-09-11 18:00 |  | 2019-11-29 09:07 | 2019-11-29 09:07 | Kristin Ohnstad |  | Approved |  | 2019-08-29 09:00 | 2019-09-06 17:00 | 2019-08-28 13:49
CHG0031390 | DigiPlex Norway AS | Årlig EL.kontrol med termografering av tavler DNAS . | Normal | Closed | 2019-09-02 08:00 | 2019-09-04 16:00 |  | 2019-10-18 14:14 | 2019-10-18 14:14 | Kristin Ohnstad |  | Approved | 28.08.2019 13:02:23 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 27.08.2019 15:34:32 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-02 15:06 | 2019-09-20 15:06 | 2019-08-27 15:22
CHG0031389 | DigiPlex Norway AS | Årlig service på brannalarm (sentraler) | Normal | Closed | 2019-09-02 08:00 | 2019-09-03 16:00 |  | 2019-10-18 14:14 | 2019-10-18 14:14 | Kristin Ohnstad |  | Approved | 28.08.2019 13:01:43 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 27.08.2019 15:33:36 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-02 09:21 | 2019-09-02 09:21 | 2019-08-26 10:49
CHG0031388 | DigiPlex Stockholm 1 AB | Install new after heater battery | Normal | Closed | 2019-08-23 08:00 | 2019-08-23 18:00 |  | 2019-10-31 14:08 | 2019-10-31 14:08 | Christian Eghult |  | Approved | 22.08.2019 13:49:03 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-08-23 08:15 | 2019-08-23 18:00 | 2019-08-22 13:24
CHG0031385 | DigiPlex Norway AS | E and F + Gen 1 - 4 works. | Normal | Closed | 2019-08-26 15:27 | 2019-10-18 15:27 |  | 2019-11-25 08:18 | 2019-11-25 08:18 | Kristin Ohnstad |  | Approved | 26.08.2019 07:22:09 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-28 12:23 | 2019-10-25 12:23 | 2019-08-21 15:32
CHG0031384 | DigiPlex Stockholm 1 AB | Plenum refitting above DH7.1 | Normal | Closed | 2019-08-26 07:00 | 2019-09-13 18:00 |  | 2019-10-17 09:02 | 2019-10-17 09:02 | Kristin Ohnstad |  | Approved | 20.08.2019 14:19:55 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-26 07:00 | 2019-09-25 14:00 | 2019-08-20 13:56
CHG0031383 | DigiPlex Stockholm 1 AB | Re-painting floor on level 3 | Normal | Closed | 2019-09-06 07:00 | 2019-09-09 09:00 |  | 2019-09-18 08:48 | 2019-09-18 08:48 |  |  | Approved | 20.08.2019 14:25:31 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-06 15:00 | 2019-09-06 19:00 | 2019-08-20 13:37
CHG0031382 | DigiPlex Fet AS | Upgrade Internet capacity from 100 Mb to 200 Mb | Normal | Closed | 2019-08-21 09:00 | 2019-08-21 09:31 |  | 2019-11-26 14:11 | 2019-11-26 14:11 | Kristin Ohnstad |  | Approved | 21.08.2019 07:51:24 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 20.08.2019 14:21:34 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-12 09:25 | 2019-11-20 09:55 | 2019-08-19 16:13
CHG0031379 | DigiPlex Norway AS | Montering av "containment for cooling " i POD PLT 08 F | Normal | Closed | 2019-08-19 08:01 | 2019-08-19 15:58 |  | 2019-10-04 14:32 | 2019-10-04 14:32 | Geir Almquist |  | Approved | 19.08.2019 08:42:30 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-19 14:30 | 2019-08-22 14:31 | 2019-08-15 12:57
CHG0031378 | DigiPlex Norway AS | Annual maintenance on access control system | Normal | Closed | 2019-08-19 08:00 | 2019-08-30 16:00 |  | 2019-09-26 07:32 | 2019-09-26 07:32 | Kristin Ohnstad |  | Approved | 16.08.2019 13:53:02 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2019-08-19 08:00 | 2019-09-23 14:00 | 2019-08-15 10:41
CHG0031376 | DigiPlex Stockholm 1 AB | FDP power supply | Normal | Closed | 2019-08-16 07:00 | 2019-08-21 18:00 |  | 2019-09-19 14:41 | 2019-09-19 14:41 |  |  | Approved |  | 2019-08-16 07:00 | 2019-08-23 17:00 | 2019-08-14 15:37
CHG0031375 | DigiPlex Stockholm 1 AB | BMS data transfer DH1 | Normal | Canceled | 2019-08-19 07:00 | 2019-08-27 17:00 |  | 2019-08-29 09:15 | 2019-08-29 09:15 |  |  | Not Yet Requested |  |  |  | 2019-08-14 14:09
CHG0031371 | DigiPlex Norway AS | Installation of racks in Shared Space | Normal | Closed | 2019-08-13 14:50 | 2019-09-13 14:50 |  | 2019-10-17 08:59 | 2019-10-17 08:59 | Kristin Ohnstad |  | Approved | 13.08.2019 16:35:15 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 13.08.2019 15:19:24 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-08-13 14:51 | 2019-08-29 14:06 | 2019-08-13 14:50
CHG0031370 | DigiPlex Stockholm 1 AB | Electrical installation in new customer module DH7.2.2 | Normal | Closed | 2019-09-02 07:00 | 2019-09-06 16:00 |  | 2019-09-19 14:41 | 2019-09-19 14:41 |  |  | Approved | 13.08.2019 15:18:28 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-02 07:00 | 2019-09-05 17:00 | 2019-08-13 14:53
CHG0031367 | DigiPlex Fet AS | Leakasje observert ved og rundt AHU enheten i A3.2 | Normal | Closed | 2019-08-15 11:01 | 2019-08-15 11:01 |  | 2019-11-11 11:43 | 2019-11-11 11:43 | Kristin Ohnstad |  | Approved | 13.08.2019 14:37:59 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 13.08.2019 12:54:26 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-10-14 08:42 | 2019-10-15 08:42 | 2019-08-13 11:02
CHG0031365 | DigiPlex Stockholm 1 AB | Installation of new door to customer module DH7.2.2 | Normal | Closed | 2019-08-13 07:00 | 2019-08-16 16:00 |  | 2019-08-22 15:07 | 2019-08-22 14:35 |  |  | Approved |  | 2019-08-13 08:00 | 2019-08-14 17:00 | 2019-08-12 16:21
CHG0031363 | DigiPlex Stockholm 1 AB | Patch upgrade of Gridvis system | Normal | Closed | 2019-11-05 09:00 | 2019-11-05 16:00 |  | 2019-11-29 09:03 | 2019-11-29 09:03 | Kristin Ohnstad |  | Approved | 12.08.2019 15:46:18 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-11-05 09:58 | 2019-11-05 14:58 | 2019-08-12 14:49
CHG0031362 | DigiPlex Rosenholm AS | DRAS - Årlig service av rør. | Normal | Closed | 2019-09-02 12:53 | 2019-09-06 12:53 |  | 2019-09-18 08:46 | 2019-09-18 08:46 |  |  | Approved | 13.08.2019 08:24:14 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-09-02 09:15 | 2019-09-06 09:16 | 2019-08-12 12:54
CHG0031359 | DigiPlex Rosenholm AS | DRAS - Feilsøking på CCUer | Normal | Closed | 2019-08-13 09:57 | 2019-08-16 09:57 |  | 2019-11-05 09:11 | 2019-11-05 09:11 | Kristin Ohnstad |  | Approved | 12.08.2019 12:56:48 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 12.08.2019 12:52:50 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-08-13 08:50 | 2019-10-11 08:50 | 2019-08-12 09:57
CHG0031358 | DigiPlex Rosenholm AS | DRAS - Sjekk av vannkvalitet | Normal | Closed | 2019-08-15 11:04 | 2019-08-15 11:04 |  | 2019-08-22 13:51 | 2019-08-22 13:51 |  |  | Approved | 12.08.2019 10:04:45 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 09.08.2019 18:49:02 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-08-15 13:20 | 2019-08-15 13:20 | 2019-08-09 11:03
CHG0031357 | DigiPlex Stockholm 1 AB |  | Normal | Canceled |  |  |  | 2019-08-13 15:21 | 2019-08-13 15:21 |  |  | Not Yet Requested |  |  |  | 2019-08-08 14:23
CHG0031354 | DigiPlex Fet AS | Utbedring av gulvet på nivå 3 i screening området på DFAS | Normal | Closed | 2019-08-09 11:12 | 2019-08-12 11:12 |  | 2019-08-15 08:43 | 2019-08-15 08:43 |  |  | Approved | 08.08.2019 15:14:26 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 08.08.2019 15:09:01 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-08-09 10:26 | 2019-08-10 10:26 | 2019-08-08 11:16
CHG0031348 | DigiPlex Stockholm 1 AB | Termination of AHU to Mech Board | Normal | Closed | 2019-08-19 07:00 | 2019-08-23 18:00 |  | 2019-09-19 14:42 | 2019-09-19 14:42 |  |  | Approved |  | 2019-08-20 07:00 | 2019-08-20 17:00 | 2019-08-02 14:16
CHG0031347 | DigiPlex Rosenholm AS | DRAS - Major generator service 2019 | Normal | Closed | 2019-08-12 11:34 | 2019-08-23 11:34 |  | 2019-08-22 09:11 | 2019-08-22 09:11 |  |  | Approved | 08.08.2019 14:51:18 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 01.08.2019 13:11:32 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-08-12 08:46 | 2019-08-21 08:46 | 2019-08-01 11:34
CHG0031345 | DigiPlex Stockholm 1 AB | Capacity upgrade of UPS systems for DH6 and DH7 | Normal | Closed | 2019-08-26 08:00 | 2019-08-30 17:00 |  | 2019-10-10 14:20 | 2019-10-10 14:20 | Kristin Ohnstad |  | Approved |  | 2019-08-26 08:10 | 2019-10-09 15:00 | 2019-07-26 09:18
CHG0031344 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-08-20 07:00 | 2019-08-29 17:00 |  | 2019-11-05 09:10 | 2019-11-05 09:10 | Kristin Ohnstad |  | Approved |  | 2019-08-20 07:00 | 2019-08-29 15:00 | 2019-07-24 13:55
CHG0031341 | DigiPlex Norway AS | 03MOD03.1+03.2, new cage. | Normal | Closed | 2019-07-15 10:42 | 2019-08-30 10:42 |  | 2019-09-19 09:21 | 2019-09-19 09:21 |  |  | Approved | 15.07.2019 11:11:19 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 09.07.2019 11:15:43 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-07-09 11:00 | 2019-09-15 09:20 | 2019-07-09 10:47
CHG0031340 | DigiPlex Fet AS | DFAS. Annual service of UPS's in A2-1 | Normal | Closed | 2019-08-26 13:18 | 2019-08-30 13:27 |  | 2019-09-26 07:31 | 2019-09-26 07:31 | Kristin Ohnstad |  | Approved | 07.08.2019 14:02:29 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-08-26 09:20 | 2019-08-30 09:20 | 2019-07-05 13:26
CHG0031339 | DigiPlex Fet AS | DFAS. Replace faulty batteries in UPS strings | Normal | Closed | 2019-09-02 08:00 | 2019-09-06 16:00 |  | 2019-09-26 07:30 | 2019-09-26 07:30 | Kristin Ohnstad |  | Approved | 08.07.2019 07:21:31 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-09-02 09:17 | 2019-09-13 09:17 | 2019-07-05 13:08
CHG0031338 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-07-22 07:00 | 2019-07-26 16:00 |  | 2019-07-30 09:08 | 2019-07-30 09:08 |  |  | Approved |  | 2019-07-23 08:00 | 2019-07-26 10:54 | 2019-07-04 12:53
CHG0031336 | DigiPlex Fet AS | DFAS. Annual service of Munters units A2-3 | Normal | Closed | 2019-08-26 09:40 | 2019-08-30 09:44 |  | 2019-09-18 08:36 | 2019-09-18 08:36 |  |  | Approved | 08.07.2019 07:18:43 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-26 13:08 | 2019-08-30 13:09 | 2019-07-04 09:39
CHG0031334 | DigiPlex Fet AS | DFAS. Annual service of Munters units A2-2 | Normal | Closed | 2019-08-26 09:51 | 2019-08-30 09:51 |  | 2019-09-02 13:08 | 2019-09-02 13:08 | Dag Oscar Brækken |  | Approved | 08.07.2019 07:17:54 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-26 12:59 | 2019-08-30 12:59 | 2019-07-04 09:33
CHG0031333 | DigiPlex Fet AS | DFAS. Annual service of Munters units A2-1 | Normal | Closed | 2019-08-26 09:27 | 2019-08-30 09:53 |  | 2019-09-18 08:36 | 2019-09-18 08:36 |  |  | Approved | 08.07.2019 07:16:53 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-26 13:09 | 2019-08-30 13:09 | 2019-07-04 09:26
CHG0031332 | DigiPlex Fet AS | DFAS. Annual service of Munters units A1-3 | Normal | Closed | 2019-08-19 09:18 | 2019-08-23 09:18 |  | 2019-09-18 08:35 | 2019-09-18 08:35 |  |  | Approved | 08.07.2019 07:15:36 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-19 13:59 | 2019-08-23 13:59 | 2019-07-04 09:17
CHG0031331 | DigiPlex Fet AS | DFAS. Annual service of Munters units A1-2 | Normal | Closed | 2019-08-21 09:12 | 2019-08-23 09:12 |  | 2019-09-18 08:39 | 2019-09-18 08:39 |  |  | Approved | 08.07.2019 07:14:34 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-21 14:00 | 2019-08-23 14:00 | 2019-07-04 09:10
CHG0031330 | DigiPlex Fet AS | DFAS. Annual service of Munters units A1-1 | Normal | Closed | 2019-08-19 09:00 | 2019-08-23 09:00 |  | 2019-09-18 08:39 | 2019-09-18 08:39 |  |  | Approved | 08.07.2019 07:12:59 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-08-19 13:57 | 2019-08-22 13:57 | 2019-07-04 08:36
CHG0031328 | DigiPlex Copenhagen 1 ApS | Annual inspection of roof drainages in technical areas | Normal | Closed | 2019-06-12 | 2019-07-01 |  | 2019-10-17 09:01 | 2019-10-17 09:01 | Kristin Ohnstad |  | Approved |  | 2019-06-26 08:00 | 2019-06-26 16:00 | 2019-07-03 13:41
CHG0031327 | DigiPlex Norway AS | 03MOD03.1, new cagemodule. | Normal | Closed | 2019-07-02 09:42 | 2019-09-27 09:42 |  | 2019-09-19 09:20 | 2019-09-19 09:20 |  |  | Approved | 04.07.2019 13:46:51 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 02.07.2019 10:01:45 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-07-02 09:42 | 2019-09-16 09:14 | 2019-07-02 09:53
CHG0031326 | DigiPlex Norway AS | Oppgradering av Software | Normal | Closed | 2019-07-02 08:00 | 2019-07-03 15:41 |  | 2019-08-08 09:57 | 2019-08-08 09:57 | Geir Almquist |  | Approved | 02.07.2019 09:23:01 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 02.07.2019 09:19:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-07-02 10:00 | 2019-07-03 14:01 | 2019-07-01 14:05
CHG0031324 | DigiPlex Norway AS | Level 3 pipes isolating. | Normal | Implement | 2019-07-01 10:46 | 2019-08-30 10:46 |  | 2019-11-28 09:20 |  |  |  | Approved | 02.07.2019 09:31:23 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). |  |  | 2019-07-01 11:28
CHG0031323 | DigiPlex Copenhagen 1 ApS | New installation - outdoor fall protections | Normal | Closed | 2019-06-01 08:00 | 2019-06-30 16:00 |  | 2019-07-03 13:47 | 2019-07-03 13:47 | Mark Kjeldstrøm |  | Approved |  | 2019-06-11 08:00 | 2019-06-11 16:00 | 2019-06-28 11:47
CHG0031322 | DigiPlex Fet AS | Tilførselgrøft for nye parkeringsplasser | Normal | Closed | 2019-07-01 07:00 | 2019-07-09 16:00 |  | 2019-08-01 15:16 | 2019-08-01 15:16 |  |  | Approved | 01.07.2019 07:06:22 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2019-07-01 12:36 | 2019-07-09 12:36 | 2019-06-27 14:53
CHG0031321 | DigiPlex Norway AS | Intern nettverks -kabling hos kunde | Normal | Closed | 2019-07-01 15:13 | 2019-08-01 15:13 |  | 2019-10-17 08:59 | 2019-10-17 08:59 | Kristin Ohnstad |  | Approved | 08.07.2019 09:19:06 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-07-23 14:05 | 2019-09-10 14:06 | 2019-06-27 14:39
CHG0031320 | DigiPlex Norway AS | Årlig pumpe service utført av KSB | Normal | Canceled | 2019-06-28 08:00 | 2019-06-28 16:01 |  | 2019-07-04 09:53 | 2019-07-04 09:53 | Geir Almquist |  | Not Yet Requested |  |  |  | 2019-06-26 13:15
CHG0031319 | DigiPlex Copenhagen 1 ApS | DC1 - Installation of NH3 emergency ventilation system | Normal | Closed | 2019-05-01 08:00 | 2019-07-31 16:00 |  | 2019-08-26 12:42 | 2019-08-26 12:42 | Mark Kjeldstrøm |  | Approved |  | 2019-05-20 08:00 | 2019-06-26 13:43 | 2019-06-26 10:02
CHG0031316 | DigiPlex Rosenholm AS | DRAS - Vask av tekniske rom | Normal | Closed | 2019-07-01 09:52 | 2019-07-05 09:52 |  | 2019-08-22 13:51 | 2019-08-22 13:51 |  |  | Approved | 26.06.2019 09:26:27 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-07-01 13:10 | 2019-08-14 13:10 | 2019-06-25 09:47
CHG0031315 | DigiPlex Rosenholm AS | Antistatic Cleaning | Normal | Closed | 2019-07-01 08:00 | 2019-07-01 17:00 |  | 2019-07-16 09:51 | 2019-07-16 09:51 |  |  | Approved | 25.06.2019 09:26:53 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2019-07-01 08:00 | 2019-07-01 16:30 | 2019-06-24 15:25
CHG0031313 | DigiPlex Norway AS | Antistatic Cleaning | Normal | Closed | 2019-07-02 08:00 | 2019-07-05 17:00 |  | 2019-07-16 09:52 | 2019-07-16 09:52 |  |  | Approved | 26.06.2019 09:25:42 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-07-02 08:00 | 2019-07-05 16:00 | 2019-06-24 15:19
CHG0031312 | DigiPlex Norway AS | Update of the firmware in the UPS in E and F. | Normal | Canceled | 2019-07-02 08:01 | 2019-07-02 16:00 |  | 2019-07-04 09:53 | 2019-07-04 09:53 | Geir Almquist |  | Requested | 24.06.2019 15:53:32 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-06-24 13:19
CHG0031309 | DigiPlex Norway AS | Temporary covering the perforated door into -01MOD03. | Emergency | Canceled | 2019-06-24 09:05 | 2019-06-25 16:00 |  | 2019-07-01 12:53 | 2019-07-01 12:53 | Pål Rune Viken |  | Approved | 26.06.2019 09:57:48 - fekay (Approval history) Group approval for CAB Approval NO approved by user Frode Elden Kay (CAB approval). 24.06.2019 14:44:30 - galmquist (Approval history) Group approval for eCAB Approval approved by user Geir Almquist (eCAB approval). | 2019-06-24 16:00 | 2019-06-24 16:00 | 2019-06-24 09:28
CHG0031308 | DigiPlex Norway AS | Tuning of CCU's | Normal | Closed | 2019-06-24 09:00 | 2019-06-27 16:00 |  | 2019-09-18 08:44 | 2019-09-18 08:44 |  |  | Approved | 24.06.2019 07:23:28 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-06-24 09:00 | 2019-06-27 16:00 | 2019-06-21 12:36
CHG0031306 | DigiPlex Norway AS | New access control sentral in -01 | Normal | Closed | 2019-06-24 08:00 | 2019-06-25 16:00 |  | 2019-09-19 09:22 | 2019-09-19 09:22 |  |  | Approved | 20.06.2019 08:07:38 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-06-24 08:00 | 2019-09-10 16:00 | 2019-06-19 10:06
CHG0031305 | DigiPlex Stockholm 1 AB | Penetration into DH7.2 MMR | Normal | Closed | 2019-06-24 07:00 | 2019-06-28 17:00 |  | 2019-07-16 09:53 | 2019-07-16 09:53 |  |  | Approved |  | 2019-06-28 07:00 | 2019-06-28 16:00 | 2019-06-18 15:42
CHG0031304 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-06-21 07:00 | 2019-06-28 16:00 |  | 2019-07-16 09:53 | 2019-07-16 09:53 |  |  | Approved |  | 2019-06-21 06:00 | 2019-07-03 15:00 | 2019-06-18 12:13
CHG0031303 | DigiPlex Norway AS | Roof, covering DX units. | Normal | Closed | 2019-06-18 09:39 | 2019-08-02 09:39 |  | 2019-08-29 08:10 | 2019-08-29 08:10 |  |  | Approved | 19.06.2019 08:11:20 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-08-04 09:23 | 2019-08-16 09:24 | 2019-06-18 09:51
CHG0031302 | DigiPlex Norway AS | Installation of CAC solution. | Normal | Closed | 2019-06-18 08:00 | 2019-06-28 16:00 |  | 2019-06-24 08:03 | 2019-06-24 08:03 |  |  | Approved | 18.06.2019 12:01:13 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 17.06.2019 14:25:03 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-18 08:00 | 2019-06-19 16:00 | 2019-06-17 13:40
CHG0031300 | DigiPlex Fet AS | Change 1 EEV | Normal | Closed | 2019-06-17 09:58 | 2019-06-21 09:58 |  | 2019-11-11 11:43 | 2019-11-11 11:43 | Kristin Ohnstad |  | Approved | 24.06.2019 08:19:56 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2019-06-17 08:48 | 2019-06-21 08:48 | 2019-06-17 10:24
CHG0031299 | DigiPlex Fet AS | Battery change on UPS A | Normal | Canceled |  |  |  | 2019-06-17 11:01 | 2019-06-17 11:01 | Frode Elden Kay |  | Not Yet Requested |  |  |  | 2019-06-17 10:53
CHG0031298 | DigiPlex Stockholm 1 AB | Penetration through level 3 wall | Normal | Closed | 2019-06-24 09:19 | 2019-06-26 19:19 |  | 2019-08-22 14:40 | 2019-08-22 14:40 |  |  | Approved | 17.06.2019 14:30:43 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-24 09:16 | 2019-06-28 16:00 | 2019-06-17 09:30
CHG0031292 | DigiPlex Norway AS | Bytte av power modul i UPS A | Emergency | Canceled |  |  |  | 2019-08-13 15:17 | 2019-08-13 15:05 |  |  | Not Yet Requested |  |  |  | 2019-06-13 08:59
CHG0031291 | DigiPlex Rosenholm AS | DRAS - Bytte av lys i tekniske rom | Normal | Closed | 2019-06-11 13:22 | 2019-07-05 13:22 |  | 2019-08-01 09:52 | 2019-08-01 09:52 |  |  | Approved | 11.06.2019 14:20:12 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 11.06.2019 13:34:32 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-11 10:37 | 2019-06-27 10:38 | 2019-06-11 13:22
CHG0031289 | DigiPlex Norway AS | Test of Vetas units in modules by Honeywell. | Normal | Closed | 2019-06-17 08:00 | 2019-06-21 16:00 |  | 2019-08-08 09:58 | 2019-08-08 09:58 | Geir Almquist |  | Approved | 18.06.2019 13:26:00 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 11.06.2019 13:36:20 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-17 09:54 | 2019-06-21 09:54 | 2019-06-11 10:55
CHG0031287 | DigiPlex Norway AS | Annual diesel analyze. | Normal | Closed | 2019-06-16 09:24 | 2019-06-21 09:24 |  | 2019-06-24 08:02 | 2019-06-24 08:02 |  |  | Approved | 12.06.2019 09:47:30 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 11.06.2019 13:35:09 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-20 12:05 | 2019-06-20 14:05 | 2019-06-11 09:25
CHG0031275 | DigiPlex Rosenholm AS | DRAS - Årlig vask av ADCer | Normal | Closed | 2019-06-17 14:16 | 2019-07-31 14:16 |  | 2019-08-01 09:51 | 2019-08-01 09:51 |  |  | Approved | 07.06.2019 12:48:45 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-07-01 10:39 | 2019-07-26 10:39 | 2019-06-06 14:17
CHG0031272 | DigiPlex Norway AS | Yearly service of Fire Panels, DNAS | Standard | Canceled |  |  |  | 2019-06-06 12:49 | 2019-06-06 12:49 |  |  | Approved |  |  |  | 2019-06-06 11:10
CHG0031269 | DigiPlex Rosenholm AS | GAPIT project DRAS | Normal | Implement | 2019-09-13 12:29 | 2019-11-30 12:29 |  | 2019-09-18 10:00 |  |  |  | Rejected | 02.09.2019 10:18:45 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 06.06.2019 09:32:12 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-09-16 14:04 | 2019-11-29 14:04 | 2019-06-05 12:34
CHG0031267 | DigiPlex Norway AS | Isolation of ventilation tube. | Normal | Closed | 2019-06-07 07:01 | 2019-06-28 15:00 |  | 2019-08-15 09:16 | 2019-08-15 09:16 |  |  | Approved | 07.06.2019 14:22:40 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-08-13 08:00 | 2019-08-13 12:35 | 2019-06-05 08:57
CHG0031266 | DigiPlex Norway AS | 02MOD05.4 +02MOD07.2, new feed for key cabinet. | Normal | Closed | 2019-06-04 13:13 | 2019-06-28 13:13 |  | 2019-07-30 14:12 | 2019-07-30 14:12 |  |  | Approved | 05.06.2019 08:55:47 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 04.06.2019 15:28:05 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 04.06.2019 15:16:18 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-04 08:00 | 2019-06-06 16:00 | 2019-06-04 13:24
CHG0031265 | DigiPlex Rosenholm AS | DRAS - Bytte defekt ventil | Normal | Closed | 2019-06-14 14:54 | 2019-07-05 14:55 |  | 2019-06-24 08:02 | 2019-06-24 08:02 |  |  | Approved | 05.06.2019 12:15:08 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 04.06.2019 15:13:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-06 08:41 | 2019-06-06 08:42 | 2019-06-04 14:54
CHG0031264 | DigiPlex Norway AS | New walkway outside of POD E | Normal | Closed | 2019-06-04 08:00 | 2019-06-14 16:00 |  | 2019-06-18 08:42 | 2019-06-18 08:42 |  |  | Approved | 04.06.2019 10:01:28 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-06-04 09:32 | 2019-06-06 09:32 | 2019-06-03 11:58
CHG0031263 | DigiPlex Rosenholm AS | DRAS - Oljeprøve av Gen 3.2 | Normal | Closed | 2019-06-24 08:48 | 2019-06-24 08:48 |  | 2019-08-01 09:51 | 2019-08-01 09:51 |  |  | Approved | 05.06.2019 12:16:43 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-06-24 10:43 | 2019-06-24 10:43 | 2019-06-03 08:48
CHG0031261 | DigiPlex Norway AS | Annual maintenance generator E and F | Normal | Closed | 2019-06-17 08:00 | 2019-06-28 16:00 |  | 2019-08-15 09:16 | 2019-08-15 09:16 |  |  | Approved | 03.06.2019 08:51:09 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-06-17 09:00 | 2019-07-05 14:00 | 2019-05-29 13:20
CHG0031260 | DigiPlex Norway AS | Annual manitenance genertor C | Normal | Closed | 2019-06-05 08:00 | 2019-06-07 16:00 |  | 2019-06-24 08:02 | 2019-06-24 08:02 |  |  | Approved | 03.06.2019 09:01:37 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-06-05 08:00 | 2019-06-07 14:00 | 2019-05-29 12:48
CHG0031259 | DigiPlex Norway AS | Annual maintenance generator B | Normal | Closed | 2019-06-03 08:00 | 2019-06-04 16:00 |  | 2019-06-24 08:01 | 2019-06-24 08:01 |  |  | Approved | 03.06.2019 09:14:46 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-06-03 08:00 | 2019-06-04 15:00 | 2019-05-29 11:49
CHG0031257 | DigiPlex Rosenholm AS | Gapit integration DRAS (Hardwire) | Normal | Canceled |  |  |  | 2019-09-02 10:32 | 2019-09-02 10:32 |  |  | Not Yet Requested |  |  |  | 2019-05-28 13:41
CHG0031256 | DigiPlex Rosenholm AS | Gapit integration DRAS (IT) | Normal | Canceled |  |  |  | 2019-09-02 10:33 | 2019-09-02 10:33 |  |  | Not Yet Requested |  |  |  | 2019-05-28 13:36
CHG0031255 | DigiPlex Stockholm 1 AB | Cable energization | Normal | Closed | 2019-05-28 07:00 | 2019-05-28 17:55 |  | 2019-06-07 09:05 | 2019-06-07 09:05 |  |  | Approved |  | 2019-05-28 16:31 | 2019-05-28 16:45 | 2019-05-27 18:08
CHG0031254 | DigiPlex Norway AS | Installation of CAC solution in customer module. | Normal | Closed | 2019-06-11 08:26 | 2019-07-12 08:26 |  | 2019-10-17 08:59 | 2019-10-17 08:59 | Kristin Ohnstad |  | Approved | 11.06.2019 09:21:22 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 07.06.2019 14:50:55 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 29.05.2019 12:23:46 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-06-17 08:45 | 2019-07-16 14:05 | 2019-05-27 14:50
CHG0031253 | DigiPlex Norway AS |  | Normal | Canceled |  |  |  | 2019-07-04 09:58 | 2019-07-04 09:58 | Geir Almquist |  | Not Yet Requested |  |  |  | 2019-05-24 15:06
CHG0031250 | DigiPlex Norway AS | Enter your description here | Normal | Canceled |  |  |  | 2019-05-29 06:56 | 2019-05-29 06:56 |  |  | Not Yet Requested |  |  |  | 2019-05-24 11:48
CHG0031249 | DigiPlex Rosenholm AS | Rebuild HVAC box in Level 2 | Normal | Closed | 2019-05-26 08:00 | 2019-05-31 16:00 |  | 2019-06-18 08:44 | 2019-06-18 08:44 |  |  | Approved | 28.05.2019 14:26:25 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 24.05.2019 12:47:27 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-04 09:09 | 2019-06-05 16:00 | 2019-05-23 12:58
CHG0031248 | DigiPlex Stockholm 1 AB | Installation of new fence within the vehicle trap | Normal | Closed | 2019-06-10 10:30 | 2019-06-20 10:30 |  | 2019-08-22 14:46 | 2019-08-22 14:46 |  |  | Approved | 23.05.2019 16:14:29 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-30 09:23 | 2019-07-05 09:23 | 2019-05-23 10:30
CHG0031246 | DigiPlex Stockholm 1 AB |  | Normal | Canceled |  |  |  | 2019-05-28 14:24 | 2019-05-28 14:24 |  |  | Not Yet Requested |  |  |  | 2019-05-23 09:14
CHG0031243 | DigiPlex Stockholm 1 AB | Control cable termination | Normal | Closed | 2019-05-27 08:00 | 2019-05-27 18:00 |  | 2019-06-07 09:06 | 2019-06-07 09:06 | Christian Eghult |  | Approved | 23.05.2019 16:07:04 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 22.05.2019 21:30:48 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-27 15:00 | 2019-05-27 17:00 | 2019-05-22 16:57
CHG0031242 | DigiPlex Norway AS | '-01MOD08.2, Upgrading CCU. | Normal | Canceled | 2019-05-27 14:48 | 2019-06-28 14:48 |  | 2019-11-28 10:45 | 2019-06-17 10:37 | John Petter Jahr |  | Approved | 23.05.2019 10:04:20 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 22.05.2019 21:32:43 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-05-22 15:04
CHG0031240 | DigiPlex Stockholm 1 AB | Installation of new fence within the vehicle trap | Normal | Canceled | 2019-06-10 07:00 | 2019-06-21 18:00 |  | 2019-05-23 10:30 | 2019-05-23 10:30 | Daniel Kolm |  | Rejected | 22.05.2019 13:30:10 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-05-22 13:22
CHG0031236 | DigiPlex Norway AS | Fiber cabling 03Mod03.5->00Mod05 (AVS1659) | Normal | Closed | 2019-05-27 07:30 | 2019-06-21 16:00 |  | 2019-06-18 08:41 | 2019-06-18 08:41 |  |  | Approved | 22.05.2019 10:00:50 - lvalseth (Approval history) Group approval for Change-Technical assess group approved by user Lars Valseth (Technical approvals norway). | 2019-06-04 07:00 | 2019-06-14 12:30 | 2019-05-21 10:52
CHG0031235 | DigiPlex Stockholm 1 AB | Roof Ventilation Penetration | Normal | Closed | 2019-05-21 07:00 | 2019-05-31 18:00 |  | 2019-09-26 11:42 | 2019-09-26 11:42 | Kristin Ohnstad |  | Approved |  | 2019-09-09 07:00 | 2019-09-10 16:00 | 2019-05-20 11:34
CHG0031234 | DigiPlex Copenhagen 1 ApS | DC1 - Safety ventilation of chiller room | Normal | Canceled |  |  |  | 2019-06-24 16:15 | 2019-06-24 16:15 |  |  | Not Yet Requested |  |  |  | 2019-05-20 07:28
CHG0031233 | DigiPlex Stockholm 1 AB | LV panel energisation | Normal | Closed | 2019-05-14 16:30 | 2019-05-14 18:00 |  | 2019-05-15 09:25 | 2019-05-15 09:25 | Christian Eghult |  | Approved |  | 2019-05-14 17:15 | 2019-05-15 17:30 | 2019-05-14 16:31
CHG0031232 | DigiPlex Rosenholm AS | DRAS - tilkobling og oppstart av CCU | Normal | Implement | 2019-05-15 14:51 | 2019-07-01 14:51 |  | 2019-08-15 09:14 |  |  |  | Approved | 31.05.2019 12:30:05 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). 14.05.2019 15:52:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-05-14 14:51
CHG0031231 | DigiPlex All | Endre CMDB-struktur i ServiceNow PROD | Normal | Closed | 2019-05-15 08:00 | 2019-05-16 16:00 |  | 2019-05-22 13:31 | 2019-05-22 13:31 |  |  | Approved | 14.05.2019 12:59:05 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 14.05.2019 12:33:32 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-15 08:00 | 2019-05-16 16:00 | 2019-05-14 10:38
CHG0031230 | DigiPlex Norway AS | 00MOD01/05, new BMS sensores. | Normal | Closed | 2019-05-14 14:55 | 2019-06-28 14:55 |  | 2019-06-24 08:01 | 2019-06-24 08:01 |  |  | Approved | 14.05.2019 08:29:09 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 13.05.2019 15:34:30 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-27 08:00 | 2019-06-05 14:00 | 2019-05-13 15:08
CHG0031229 | DigiPlex Norway AS | Commissioning CCU's E and F | Normal | Closed | 2019-05-20 14:26 | 2019-06-14 14:26 |  | 2019-08-08 10:05 | 2019-08-08 10:05 | Geir Almquist |  | Approved | 14.05.2019 08:27:43 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 13.05.2019 15:37:09 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-21 09:59 | 2019-06-14 09:59 | 2019-05-13 14:55
CHG0031228 | DigiPlex Norway AS | Change plates facade. | Normal | Closed | 2019-05-14 14:15 | 2019-06-14 14:15 |  | 2019-05-23 16:31 | 2019-05-23 16:31 |  |  | Approved | 14.05.2019 11:04:15 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 13.05.2019 15:31:31 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-13 14:15 | 2019-05-17 12:46 | 2019-05-13 14:21
CHG0031227 | DigiPlex Norway AS | Critical alarm UPS A. | Normal | Closed | 2019-05-14 09:00 | 2019-05-14 16:00 |  | 2019-05-22 13:31 | 2019-05-22 13:31 |  |  | Approved | 14.05.2019 08:26:51 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-05-14 14:00 | 2019-05-14 15:15 | 2019-05-13 13:36
CHG0031226 | DigiPlex Norway AS |  | Normal | Canceled | 2019-05-14 12:22 | 2019-06-14 12:22 |  | 2019-05-13 15:33 | 2019-05-13 15:33 |  |  | Rejected | 13.05.2019 12:52:11 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-05-13 12:40
CHG0031225 | DigiPlex Rosenholm AS | DRAS - Justering av gangbane | Normal | Closed | 2019-05-15 09:47 | 2019-05-24 09:47 |  | 2019-05-23 16:30 | 2019-05-23 16:30 |  |  | Approved | 14.05.2019 08:28:26 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 13.05.2019 15:35:35 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-16 09:07 | 2019-05-16 09:07 | 2019-05-13 09:52
CHG0031224 | DigiPlex Rosenholm AS | R01MOD01.3, earthing racks. | Normal | Closed | 2019-05-12 08:54 | 2019-06-07 08:54 |  | 2019-07-16 09:54 | 2019-07-16 09:54 |  |  | Approved | 10.05.2019 10:49:04 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 10.05.2019 09:21:10 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-14 09:15 | 2019-05-22 09:15 | 2019-05-10 09:01
CHG0031223 | DigiPlex Norway AS | 02MOD06.2, relocate camera. | Normal | Closed | 2019-05-12 08:34 | 2019-05-24 08:34 |  | 2019-06-24 08:01 | 2019-06-24 08:01 |  |  | Approved | 10.05.2019 10:42:13 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 10.05.2019 09:21:31 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-21 08:00 | 2019-05-21 16:00 | 2019-05-10 08:48
CHG0031222 | DigiPlex Norway AS | 03MOD03.5, new cagemodule. | Normal | Closed | 2019-05-13 08:22 | 2019-06-28 08:22 |  | 2019-06-27 09:16 | 2019-06-27 09:16 |  |  | Approved | 10.05.2019 10:57:40 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 10.05.2019 09:20:25 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-10 08:22 | 2019-06-25 12:00 | 2019-05-10 08:32
CHG0031221 | DigiPlex Rosenholm AS | DRAS - Fullskala test av hele brannvarslingsanlegget | Normal | Closed | 2019-12-12 07:01 | 2019-12-13 10:02 |  | 2020-01-07 15:18 | 2020-01-07 15:18 | Kristin Ohnstad |  | Approved | 10.05.2019 06:49:12 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). | 2019-12-12 08:26 | 2019-12-12 15:26 | 2019-05-09 09:37
CHG0031219 | DigiPlex Rosenholm AS | DRAS - PPM Sjekk av brannsentraler | Normal | Closed | 2019-09-05 08:29 | 2019-09-06 08:29 |  | 2019-09-26 07:32 | 2019-09-26 07:32 | Kristin Ohnstad |  | Approved | 09.05.2019 08:42:27 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 09.05.2019 08:41:03 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-09-05 09:17 | 2019-09-05 12:17 | 2019-05-09 08:31
CHG0031218 | DigiPlex All | Process Change | Normal | Closed | 2019-05-12 07:50 | 2019-05-12 07:50 |  | 2019-05-31 09:09 | 2019-05-31 09:09 |  |  | Approved | 09.05.2019 08:42:49 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 09.05.2019 07:59:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-13 14:37 | 2019-05-13 14:38 | 2019-05-09 07:50
CHG0031217 | DigiPlex All | TEST | Normal | Canceled |  |  |  | 2019-07-01 09:56 | 2019-07-01 09:56 | Frode Elden Kay |  | Not Yet Requested |  |  |  | 2019-05-08 10:41
CHG0031216 | DigiPlex Norway AS | '-01MOD04, new cable tray in ceiling. | Normal | Closed | 2019-05-10 08:00 | 2019-05-24 16:00 |  | 2019-07-16 10:19 | 2019-07-16 10:19 |  |  | Approved | 09.05.2019 11:55:20 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 08.05.2019 10:55:57 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-03 08:31 | 2019-06-07 08:31 | 2019-05-08 10:39
CHG0031215 | DigiPlex Norway AS | Feil på kortleser | Normal | Closed | 2019-05-09 08:00 | 2019-05-09 16:00 |  | 2019-06-24 08:00 | 2019-06-24 08:00 |  |  | Approved | 09.05.2019 08:43:07 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-05-09 08:00 | 2019-05-09 15:00 | 2019-05-08 10:05
CHG0031214 | DigiPlex Norway AS | Annual service on Chillers Enter your description here | Normal | Canceled | 2019-05-09 08:00 | 2019-05-16 16:00 |  | 2019-07-04 12:29 | 2019-07-04 12:29 | Geir Almquist |  | Rejected | 08.05.2019 07:50:10 - Rune Asak (Approval history) Group approval for Change-Technical assess group approved by user Rune Asak (Technical approvals norway). |  |  | 2019-05-07 14:20
CHG0031208 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-05-20 08:00 | 2019-05-24 16:00 |  | 2019-06-24 08:00 | 2019-06-24 08:00 |  |  | Approved |  | 2019-05-20 06:00 | 2019-05-29 16:00 | 2019-05-07 08:20
CHG0031205 | DigiPlex Rosenholm AS | Water leakage from valve in CCU. | Normal | Closed | 2019-05-12 07:00 | 2019-05-31 16:00 |  | 2019-08-01 09:50 | 2019-08-01 09:50 |  |  | Approved | 07.05.2019 08:11:44 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2019-06-24 10:42 | 2019-06-25 10:42 | 2019-05-06 12:12
CHG0031203 | DigiPlex Norway AS | Fiber cabling (AVS10025) and (AVS10057) | Normal | Closed | 2019-05-09 07:00 | 2019-05-31 16:00 |  | 2019-05-23 16:30 | 2019-05-23 16:30 |  |  | Approved | 06.05.2019 10:43:22 - lvalseth (Approval history) Group approval for Change-Technical assess group approved by user Lars Valseth (Technical approvals norway). 06.05.2019 10:38:57 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-10 07:00 | 2019-05-22 13:00 | 2019-05-06 08:55
CHG0031193 | DigiPlex Fet AS | Installering av By pass i IDF rom 1-4 | Normal | Closed | 2019-05-03 11:42 | 2019-05-08 16:01 |  | 2019-07-16 09:53 | 2019-07-16 09:53 |  |  | Approved | 09.05.2019 06:32:06 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2019-06-25 22:37 | 2019-07-29 22:37 | 2019-05-03 11:52
CHG0031191 | DigiPlex Stockholm 1 AB | Operationalizing DH7.3 Fire Alarm | Normal | Closed | 2019-05-06 08:00 | 2019-05-06 17:00 |  | 2019-05-16 16:07 | 2019-05-16 16:07 |  |  | Approved | 03.05.2019 11:49:48 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-09 08:00 | 2019-05-09 17:00 | 2019-05-03 10:45
CHG0031190 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-05-20 08:00 | 2019-05-24 16:00 |  | 2019-06-24 08:00 | 2019-06-24 08:00 |  |  | Approved |  | 2019-05-20 08:00 | 2019-05-29 16:00 | 2019-05-03 10:34
CHG0031189 | DigiPlex Fet AS | Flytte rack fra CMMR A2 -A & B (A2-105 & A2-102) | Normal | Canceled | 2019-05-14 10:00 | 2019-05-14 16:00 |  | 2019-06-26 18:52 | 2019-06-26 18:52 |  |  | Approved | 09.05.2019 08:45:06 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 08.05.2019 10:57:29 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 07.05.2019 15:31:18 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-10 08:30 | 2019-06-11 08:30 | 2019-05-03 10:23
CHG0031185 | DigiPlex Stockholm 1 AB | Network redesign to accomplish expansion in CCTV cameras | Normal | Closed | 2019-05-09 12:00 | 2019-05-09 13:00 |  | 2019-05-16 16:41 | 2019-05-16 16:41 | Karl Audun Lad | 2019-05-02 | Approved | 02.05.2019 12:08:03 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-05-09 12:00 | 2019-05-09 13:00 | 2019-05-02 09:04
CHG0031183 | DigiPlex Norway AS | Batteri feil på generator 3 | Emergency | Canceled |  |  |  | 2019-05-02 09:53 | 2019-05-02 09:46 | Frode Elden Kay |  | Not Yet Requested |  |  |  | 2019-05-02 08:53
CHG0031179 | DigiPlex Stockholm 1 AB | Integrity test DH7.2 | Normal | Closed | 2019-04-29 08:30 | 2019-04-29 13:00 |  | 2019-05-02 14:47 | 2019-05-02 14:47 |  |  | Approved |  | 2019-04-29 08:30 | 2019-04-29 13:00 | 2019-04-26 14:23
CHG0031178 | DigiPlex Stockholm 1 AB | Cutting generator cage | Normal | Closed | 2019-04-30 07:00 | 2019-04-30 17:00 |  | 2019-05-02 14:47 | 2019-05-02 14:47 |  |  | Approved |  | 2019-04-30 07:00 | 2019-04-30 17:00 | 2019-04-26 13:33
CHG0031177 | DigiPlex Norway AS | Jordprøver av tomten i sør | Normal | Closed | 2019-04-28 09:10 | 2019-04-29 09:11 |  | 2019-05-23 16:31 | 2019-05-23 16:31 |  |  | Approved | 02.05.2019 09:23:02 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 26.04.2019 11:01:54 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-29 10:07 | 2019-04-29 10:07 | 2019-04-26 09:03
CHG0031176 | DigiPlex Norway AS | Etterfylling av gass | Emergency | Closed | 2019-04-26 09:30 | 2019-04-26 16:00 |  | 2019-05-01 22:12 | 2019-05-01 22:12 |  |  | Approved | 26.04.2019 10:36:44 - pviken (Approval history) Group approval for CAB Approval NO approved by user Pål Rune Viken (CAB approval). 26.04.2019 09:43:17 - aolsen (Approval history) Group approval for eCAB Approval approved by user Alexander Olsen (eCAB approval). | 2019-04-26 10:00 | 2019-04-26 12:29 | 2019-04-26 08:37
CHG0031175 | DigiPlex Norway AS | Etterfylling av gass | Normal | Canceled | 2019-04-26 09:30 | 2019-04-26 16:00 |  | 2019-04-26 10:41 | 2019-04-26 10:41 |  |  | Requested |  |  |  | 2019-04-25 14:10
CHG0031174 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-04-26 08:00 | 2019-04-30 16:00 |  | 2019-05-06 08:48 | 2019-05-06 08:48 |  |  | Approved |  | 2019-04-26 06:00 | 2019-04-30 15:37 | 2019-04-25 09:46
CHG0031171 | DigiPlex Norway AS | Vask av Chiller | Normal | Closed | 2019-04-25 08:00 | 2019-05-10 15:54 |  | 2019-05-16 09:13 | 2019-05-16 09:13 | Geir Almquist |  | Approved | 25.04.2019 09:04:06 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 24.04.2019 12:57:08 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-24 09:06 | 2019-05-10 15:06 | 2019-04-24 08:43
CHG0031170 | DigiPlex Stockholm 1 AB | Gas Pipe Test | Normal | Closed | 2019-04-29 08:14 | 2019-05-03 18:14 |  | 2019-05-06 08:52 | 2019-05-06 08:52 |  |  | Approved | 18.04.2019 09:27:57 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-30 12:00 | 2019-04-30 14:00 | 2019-04-18 08:24
CHG0031169 | DigiPlex Norway AS | Fibercabling from CCR-A and B to -01Mod06.3 | Normal | Closed | 2019-04-23 07:30 | 2019-05-03 16:00 |  | 2019-05-06 08:49 | 2019-05-06 08:49 |  |  | Approved | 23.04.2019 09:21:59 - lvalseth (Approval history) Group approval for Change-Technical assess group approved by user Lars Valseth (Technical approvals norway). 16.04.2019 11:47:55 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-24 07:00 | 2019-05-02 16:20 | 2019-04-16 08:06
CHG0031167 | DigiPlex Stockholm 1 AB | Modify MMR gas pipe | Normal | Closed | 2019-04-17 08:00 | 2019-04-17 18:00 |  | 2019-04-25 14:29 | 2019-04-25 14:29 |  |  | Approved |  | 2019-04-17 08:00 | 2019-04-17 18:00 | 2019-04-11 16:56
CHG0031166 | DigiPlex Stockholm 1 AB | Condensate pipe installation | Normal | Closed | 2019-04-23 08:00 | 2019-04-23 18:00 |  | 2019-06-26 18:49 | 2019-06-26 18:49 |  |  | Approved |  | 2019-04-23 08:00 | 2019-06-19 16:00 | 2019-04-11 14:07
CHG0031165 | DigiPlex Norway AS | Bytte startbatterier i Generator 1-2-3og 4. | Normal | Closed | 2019-04-29 08:00 | 2019-05-03 16:00 |  | 2019-05-13 15:39 | 2019-05-13 15:39 |  |  | Approved | 25.04.2019 09:05:18 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-04-30 12:11 | 2019-05-03 15:12 | 2019-04-11 10:57
CHG0031163 | DigiPlex Norway AS | 02MOD04, rectifier installation. | Normal | Closed | 2019-04-16 14:34 | 2019-05-17 14:34 |  | 2019-07-16 10:19 | 2019-07-16 10:19 |  |  | Approved | 15.04.2019 09:31:31 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-05-27 08:32 | 2019-06-28 08:33 | 2019-04-10 14:36
CHG0031162 | DigiPlex Norway AS | Cleaning generator 1-5 | Normal | Closed | 2019-04-12 08:14 | 2019-05-17 14:14 |  | 2019-08-08 10:05 | 2019-08-08 10:05 | Geir Almquist |  | Approved | 16.04.2019 07:55:00 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-04-12 12:03 | 2019-05-16 12:03 | 2019-04-10 14:16
CHG0031161 | DigiPlex Norway AS | Coolant leak | Normal | Closed | 2019-04-11 08:57 | 2019-04-11 08:57 |  | 2019-05-23 09:48 | 2019-05-23 09:48 |  |  | Approved | 11.04.2019 09:07:44 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-04-15 10:00 | 2019-04-15 16:00 | 2019-04-10 13:50
CHG0031159 | DigiPlex Stockholm 1 AB | Block pavement removal | Normal | Closed | 2019-04-12 07:00 | 2019-04-26 18:00 |  | 2019-06-26 18:49 | 2019-06-26 18:49 |  |  | Approved |  | 2019-04-12 07:00 | 2019-06-21 16:00 | 2019-04-09 17:06
CHG0031158 | DigiPlex Rosenholm AS | New fiberpipes TP room-CCR-B. | Normal | Closed | 2019-04-09 13:15 | 2019-05-03 13:15 |  | 2019-06-26 18:57 | 2019-06-26 18:57 |  |  | Approved | 10.04.2019 15:34:14 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2019-04-15 09:01 | 2019-06-07 09:01 | 2019-04-09 13:18
CHG0031156 | DigiPlex Stockholm 1 AB | Rudolph Crane Lift | Normal | Closed | 2019-04-16 08:00 | 2019-04-23 18:00 |  | 2019-05-01 22:15 | 2019-05-01 22:15 |  |  | Approved | 08.04.2019 18:54:06 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-15 13:00 | 2019-04-26 17:00 | 2019-04-08 15:50
CHG0031155 | DigiPlex Rosenholm AS | DRAS - Installere ekstra sikringer i UPS skap CCR-C | Normal | Closed | 2019-04-09 10:58 | 2019-04-19 10:58 |  | 2019-06-06 09:06 | 2019-06-06 09:06 |  |  | Approved | 08.04.2019 13:03:54 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). 08.04.2019 11:54:34 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-09 08:07 | 2019-04-30 08:07 | 2019-04-08 10:57
CHG0031154 | DigiPlex Stockholm 1 AB | Installation of access control to new customer module DH7.1.9A | Normal | Closed | 2019-04-08 09:30 | 2019-04-12 17:00 |  | 2019-04-25 14:24 | 2019-04-25 14:24 |  |  | Approved |  | 2019-04-08 09:30 | 2019-04-12 16:00 | 2019-04-05 13:57
CHG0031153 | DigiPlex Stockholm 1 AB | Reinstate MMR ceiling | Normal | Closed | 2019-04-09 08:00 | 2019-04-09 18:00 |  | 2019-04-26 11:32 | 2019-04-26 11:32 |  |  | Approved |  | 2019-04-09 08:00 | 2019-04-09 18:00 | 2019-04-05 12:58
CHG0031152 | DigiPlex Stockholm 1 AB | Tap off connection | Normal | Closed | 2019-04-29 07:00 | 2019-04-30 18:00 |  | 2019-05-06 08:50 | 2019-05-06 08:50 |  |  | Approved |  | 2019-04-29 07:00 | 2019-04-30 18:00 | 2019-04-05 10:58
CHG0031151 | DigiPlex Norway AS | Bytte av filtere utenfor kundeareale | Normal | Closed | 2019-04-09 08:00 | 2019-04-10 16:00 |  | 2019-04-12 11:26 | 2019-04-12 11:26 |  |  | Approved | 05.04.2019 09:37:41 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 04.04.2019 17:35:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-10 09:01 | 2019-04-10 14:49 | 2019-04-04 13:50
CHG0031150 | DigiPlex Stockholm 1 AB | Cable Termination in landlord pod | Normal | Closed | 2019-04-08 08:00 | 2019-04-10 18:00 |  | 2019-04-26 11:31 | 2019-04-26 11:31 |  |  | Approved |  | 2019-04-08 08:00 | 2019-04-10 18:00 | 2019-04-03 09:36
CHG0031149 | DigiPlex Norway AS | Fibercabling from CCR-A and B to 02Mod04 | Normal | Closed | 2019-04-02 07:30 | 2019-04-25 16:00 |  | 2019-04-12 11:24 | 2019-04-12 11:24 |  |  | Approved | 01.04.2019 15:21:06 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 01.04.2019 09:09:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-02 07:30 | 2019-04-11 16:00 | 2019-04-01 09:03
CHG0031148 | DigiPlex Stockholm 1 AB | DH7.2 & DH7.3 Separation | Normal | Closed | 2019-04-04 08:00 | 2019-04-05 08:00 |  | 2019-04-26 11:33 | 2019-04-26 11:33 |  |  | Approved |  | 2019-04-04 08:00 | 2019-04-04 20:00 | 2019-03-29 15:45
CHG0031147 | DigiPlex Norway AS | Defect sensor on generator EF3 | Normal | Closed | 2019-03-31 10:00 | 2019-03-31 16:00 |  | 2019-04-08 19:02 | 2019-04-08 19:02 |  |  | Approved | 01.04.2019 10:31:18 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-04-01 09:00 | 2019-04-01 14:00 | 2019-03-29 10:33
CHG0031146 | DigiPlex Stockholm 1 AB | Cabel pulling | Normal | Closed | 2019-04-02 07:00 | 2019-04-05 18:00 |  | 2019-04-26 11:33 | 2019-04-26 11:33 |  |  | Approved |  | 2019-04-02 07:00 | 2019-04-05 17:00 | 2019-03-28 13:32
CHG0031145 | DigiPlex Stockholm 1 AB | BMS layout update | Normal | Closed | 2019-05-07 07:00 | 2019-05-08 17:00 |  | 2019-05-16 16:06 | 2019-05-16 16:06 |  |  | Approved |  | 2019-05-07 07:00 | 2019-05-08 17:00 | 2019-03-28 10:16
CHG0031143 | DigiPlex All | Firewall patch update | Normal | Closed | 2019-04-01 10:00 | 2019-04-02 16:00 |  | 2019-06-26 18:52 | 2019-06-26 18:52 |  | 2019-03-28 | Approved | 28.03.2019 09:01:03 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 28.03.2019 07:33:15 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-01 10:00 | 2019-05-22 16:00 | 2019-03-28 07:13
CHG0031140 | DigiPlex Stockholm 1 AB | Troax installations DH7.1.9A | Normal | Closed | 2019-03-27 07:00 | 2019-04-04 17:00 |  | 2019-04-25 14:27 | 2019-04-25 14:27 |  |  | Approved | 26.03.2019 22:02:01 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-28 09:00 | 2019-04-05 16:00 | 2019-03-26 14:42
CHG0031139 | DigiPlex Norway AS | E/F POD Nye kjølemaskiner. | Normal | Closed | 2019-03-27 09:15 | 2019-05-31 09:15 |  | 2019-06-20 09:09 | 2019-06-20 09:09 | Pål Rune Viken |  | Approved | 28.03.2019 09:08:03 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 26.03.2019 13:29:08 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-27 09:07 | 2019-05-31 09:08 | 2019-03-26 09:16
CHG0031138 | DigiPlex Stockholm 1 AB | Prepare landlord pod for cable installation | Normal | Closed | 2019-03-26 07:00 | 2019-03-26 19:00 |  | 2019-04-17 10:27 | 2019-04-17 10:27 |  |  | Approved | 22.03.2019 14:59:38 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-26 07:00 | 2019-03-26 19:00 | 2019-03-22 14:58
CHG0031137 | DigiPlex Rosenholm AS | Fibercabling from R01MOD01.2 to New customer Level2 | Normal | Closed | 2019-03-25 09:23 | 2019-04-05 09:23 |  | 2019-04-17 10:24 | 2019-04-17 10:24 |  |  | Approved | 25.03.2019 10:48:43 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 25.03.2019 09:20:01 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-27 10:52 | 2019-03-28 10:53 | 2019-03-22 09:27
CHG0031136 | DigiPlex Stockholm 1 AB |  | Normal | Canceled |  |  |  | 2019-03-22 15:30 | 2019-03-22 15:30 | Christian Eghult |  | Not Yet Requested |  |  |  | 2019-03-21 10:21
CHG0031135 | DigiPlex Norway AS | Feil på Chiller E | Normal | Canceled | 2019-03-21 08:49 | 2019-03-21 16:00 |  | 2019-04-09 11:08 | 2019-04-09 11:08 |  |  | Requested | 21.03.2019 10:06:40 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-03-21 08:50
CHG0031131 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-03-25 11:54 | 2019-03-29 16:00 |  | 2019-04-25 14:23 | 2019-04-25 14:23 |  |  | Approved |  | 2019-03-25 11:00 | 2019-03-29 16:00 | 2019-03-20 11:47
CHG0031130 | DigiPlex Rosenholm AS | DRAS Service på pumper | Normal | Closed | 2019-04-01 12:47 | 2019-04-05 12:47 |  | 2019-04-12 11:21 | 2019-04-12 11:21 |  |  | Approved | 19.03.2019 08:47:43 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-04-01 09:22 | 2019-04-05 09:22 | 2019-03-18 12:47
CHG0031129 | DigiPlex Norway AS | Service on the Fire alarm system | Normal | Closed | 2019-03-19 08:01 | 2019-03-20 16:00 |  | 2019-05-16 09:14 | 2019-05-16 09:14 | Geir Almquist |  | Approved | 19.03.2019 09:31:39 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 18.03.2019 14:25:09 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-19 08:15 | 2019-03-20 16:00 | 2019-03-18 11:38
CHG0031128 | DigiPlex Stockholm 1 AB | Gas Suppression System | Normal | Closed | 2019-03-18 08:00 | 2019-03-29 18:00 |  | 2019-04-25 14:27 | 2019-04-25 14:27 |  |  | Approved | 15.03.2019 17:12:50 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-04 07:00 | 2019-04-04 18:00 | 2019-03-15 14:26
CHG0031127 | DigiPlex Stockholm 1 AB | Fire Alarm Works | Normal | Canceled | 2019-03-21 12:29 | 2019-04-05 12:29 |  | 2019-04-25 08:03 | 2019-04-25 08:03 | Daniel Kolm |  | Requested | 15.03.2019 13:59:57 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-04-17 12:17 |  | 2019-03-15 12:41
CHG0031126 | DigiPlex Stockholm 1 AB | DH7 steel roof reinforcement | Normal | Closed | 2019-03-18 08:00 | 2019-03-29 17:00 |  | 2019-05-09 14:33 | 2019-05-09 14:33 |  |  | Approved |  | 2019-03-18 08:00 | 2019-03-29 16:00 | 2019-03-14 13:49
CHG0031125 | DigiPlex Norway AS | install new software in UPS A | Normal | Closed | 2019-03-18 08:34 | 2019-03-19 15:35 |  | 2019-05-16 09:23 | 2019-05-16 09:23 | Geir Almquist |  | Approved | 18.03.2019 10:10:08 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-03-18 09:17 | 2019-03-18 16:17 | 2019-03-14 12:36
CHG0031121 | DigiPlex Norway AS | TEST - Replace fan in CCU01 | Normal | Canceled |  |  |  | 2019-04-02 12:37 | 2019-03-27 14:10 | Frode Elden Kay |  | Not Yet Requested |  |  |  | 2019-03-13 15:11
CHG0031120 | DigiPlex Norway AS | Fibercabling from CCR-A and B to 03Mod03.4 | Normal | Closed | 2019-03-18 07:30 | 2019-05-27 16:00 |  | 2019-06-18 08:41 | 2019-06-18 08:41 |  |  | Approved | 18.03.2019 07:35:57 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-03-20 07:22 | 2019-06-06 15:30 | 2019-03-13 14:15
CHG0031118 | DigiPlex Stockholm 1 AB | Electrical installation in new customer module DH7.1.9A | Normal | Closed | 2019-03-13 07:00 | 2019-04-11 17:00 |  | 2019-05-06 08:52 | 2019-05-06 08:52 |  | 2019-03-14 | Approved |  | 2019-03-13 07:00 | 2019-04-29 15:00 | 2019-03-12 17:07
CHG0031117 | DigiPlex Rosenholm AS | DRAS 12M Inspeksjon av røranlegget | Normal | Closed | 2019-03-18 15:06 | 2019-03-22 15:06 |  | 2019-03-28 09:08 | 2019-03-28 09:08 |  |  | Approved | 13.03.2019 09:38:55 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-03-18 10:34 | 2019-03-22 10:34 | 2019-03-12 15:06
CHG0031115 | DigiPlex Rosenholm AS | DRAS Rep av feil etter service generatorer | Normal | Closed | 2019-03-13 09:48 | 2019-03-15 09:48 |  | 2019-03-21 10:11 | 2019-03-21 10:11 |  |  | Approved | 13.03.2019 12:37:30 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 12.03.2019 11:27:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-13 13:25 | 2019-03-18 13:25 | 2019-03-12 09:48
CHG0031114 | DigiPlex Norway AS | Refill Argonite gas bottles. | Normal | Closed | 2019-03-14 08:00 | 2019-03-14 16:00 |  | 2019-03-21 09:05 | 2019-03-21 09:05 |  |  | Approved | 13.03.2019 09:39:12 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-03-15 08:52 | 2019-03-15 14:00 | 2019-03-12 09:07
CHG0031113 | DigiPlex Norway AS | New car gate | Normal | Closed | 2019-03-12 14:59 | 2019-04-19 14:59 |  | 2019-05-31 09:10 | 2019-05-31 09:10 |  |  | Approved | 13.03.2019 13:20:16 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-03-12 10:11 | 2019-04-30 10:12 | 2019-03-11 15:04
CHG0031112 | DigiPlex Norway AS | 02PLT02, removal old cabinet and installing new. | Normal | Closed | 2019-03-10 14:14 | 2019-04-19 14:14 |  | 2019-03-14 12:26 | 2019-03-13 14:44 | Pål Rune Viken |  | Approved | 13.03.2019 13:18:07 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2019-03-08 14:16
CHG0031111 | DigiPlex Norway AS | 02MOD06.2, earthing customer rack. | Normal | Closed | 2019-03-11 13:41 | 2019-04-19 13:41 |  | 2019-04-17 10:26 | 2019-04-17 10:26 |  |  | Approved | 13.03.2019 13:15:50 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-03-24 10:45 | 2019-03-25 10:44 | 2019-03-07 13:43
CHG0031109 | DigiPlex Stockholm 1 AB | Install manifold | Normal | Canceled | 2019-03-07 07:00 | 2019-03-15 18:00 |  | 2019-03-19 14:57 | 2019-03-19 14:57 | Daniel Kolm |  | Rejected | 06.03.2019 14:53:33 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-03-06 12:54
CHG0031107 | DigiPlex Rosenholm AS | DRAS 6M service på CCUer | Normal | Closed | 2019-03-06 10:21 | 2019-03-29 10:21 |  | 2019-04-30 11:46 | 2019-04-30 11:46 |  |  | Approved | 05.03.2019 10:38:24 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 04.03.2019 15:32:57 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-06 09:46 | 2019-04-26 09:46 | 2019-03-04 10:21
CHG0031106 | DigiPlex Norway AS | Compressor fault on CCU | Normal | Closed | 2019-03-05 09:05 | 2019-03-05 16:00 |  | 2019-03-21 09:04 | 2019-03-21 09:04 |  |  | Approved | 05.03.2019 08:11:12 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 04.03.2019 15:33:46 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-05 08:56 | 2019-03-05 16:00 | 2019-03-04 08:43
CHG0031104 | DigiPlex Stockholm 1 AB | Project Rudolph Gas Suppression | Normal | Canceled | 2019-03-06 07:00 | 2019-04-12 19:00 |  | 2019-03-19 14:57 | 2019-03-19 14:57 | Daniel Kolm |  | Rejected |  |  |  | 2019-03-01 16:00
CHG0031103 | DigiPlex Stockholm 1 AB | UPS DH7-B - Commissioning of frame A2 and power modules | Normal | Closed | 2019-03-04 08:00 | 2019-03-04 17:00 |  | 2019-03-14 08:26 | 2019-03-14 08:26 |  |  | Approved |  | 2019-03-04 08:00 | 2019-03-04 16:45 | 2019-03-01 14:58
CHG0031100 | DigiPlex Stockholm 1 AB | Column inspection DH7 roof | Normal | Closed | 2019-03-05 08:00 | 2019-03-07 17:00 |  | 2019-03-28 14:42 | 2019-03-28 14:42 |  |  | Approved |  | 2019-03-05 12:14 | 2019-03-07 10:18 | 2019-02-28 11:28
CHG0031095 | DigiPlex Norway AS | Remount ventilation into -01SRAS | Normal | Closed | 2019-02-28 08:00 | 2019-03-01 16:00 |  | 2019-03-14 08:42 | 2019-03-14 08:42 |  |  | Approved | 28.02.2019 10:25:26 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-02-28 09:15 | 2019-03-01 09:15 | 2019-02-27 11:59
CHG0031094 | DigiPlex Norway AS | Mount fittings for radiator cooling. | Normal | Closed | 2019-02-28 08:00 | 2019-03-01 16:00 |  | 2019-03-07 07:30 | 2019-03-07 07:30 |  |  | Approved | 28.02.2019 10:27:03 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2019-03-01 09:08 | 2019-03-01 09:08 | 2019-02-27 11:54
CHG0031091 | DigiPlex Norway AS | PM av UPS'er i E og F | Normal | Closed | 2019-02-27 08:00 | 2019-03-08 16:00 |  | 2019-04-12 11:24 | 2019-04-12 11:24 |  |  | Approved | 28.02.2019 10:23:20 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-02-27 08:01 | 2019-03-08 16:00 | 2019-02-26 14:30
CHG0031088 | DigiPlex Norway AS | Low pressure on CCU. | Normal | Closed | 2019-02-27 08:00 | 2019-02-27 16:00 |  | 2019-03-21 09:04 | 2019-03-21 09:04 |  |  | Approved | 28.02.2019 10:28:19 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 26.02.2019 16:03:04 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-02-26 13:48
CHG0031087 | DigiPlex Norway AS | Oppgradering av Software på UPS D6 med kjøring av generator | Normal | Closed | 2019-02-27 08:10 | 2019-02-27 16:11 |  | 2019-04-11 13:09 | 2019-04-11 13:09 |  |  | Approved | 28.02.2019 08:51:26 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-02-27 08:40 | 2019-02-27 15:40 | 2019-02-26 13:30
CHG0031086 | DigiPlex Norway AS | Oppdatering av software i UPS C5 IKKE D5 | Normal | Closed | 2019-02-27 08:50 | 2019-02-27 15:50 |  | 2019-04-11 13:07 | 2019-04-11 13:07 |  |  | Approved | 28.02.2019 08:50:59 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2019-02-27 08:51 | 2019-02-27 16:00 | 2019-02-26 10:51
CHG0031085 | DigiPlex Rosenholm AS | Antistatic cleaning | Normal | Closed | 2019-02-28 08:00 | 2019-03-01 16:00 |  | 2019-03-07 08:51 | 2019-03-07 08:51 |  |  | Approved | 26.02.2019 11:36:10 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 26.02.2019 10:06:16 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-28 10:00 | 2019-03-01 15:00 | 2019-02-26 09:59
CHG0031083 | DigiPlex Stockholm 1 AB | Plug the Aspiration System | Normal | Closed | 2019-02-26 08:00 | 2019-02-26 17:00 |  | 2019-03-28 14:39 | 2019-03-28 14:39 |  |  | Approved | 25.02.2019 16:08:58 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-26 14:58 | 2019-02-26 14:58 | 2019-02-25 15:21
CHG0031082 | DigiPlex Norway AS | Antistatic cleaning | Normal | Closed | 2019-02-27 08:00 | 2019-02-28 16:00 |  | 2019-03-07 07:29 | 2019-03-07 07:29 |  |  | Approved | 26.02.2019 12:13:52 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 26.02.2019 10:03:52 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-27 08:00 | 2019-02-27 16:00 | 2019-02-25 14:17
CHG0031081 | DigiPlex Stockholm 1 AB | FerraPod Security Cages | Normal | Closed | 2019-02-27 07:00 | 2019-05-03 17:00 |  | 2019-08-22 14:45 | 2019-08-22 14:45 |  |  | Approved |  | 2019-02-27 07:00 | 2019-05-31 09:20 | 2019-02-25 11:18
CHG0031080 | DigiPlex Rosenholm AS | DRAS, Årlig service på aspirasjonsdetektorer. | Normal | Closed | 2019-06-20 10:43 | 2019-06-21 10:43 |  | 2019-08-01 09:51 | 2019-08-01 09:51 |  |  | Approved | 26.02.2019 12:13:16 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 25.02.2019 13:44:21 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-06-21 10:40 | 2019-06-21 10:40 | 2019-02-25 10:44
CHG0031079 | DigiPlex Rosenholm AS | DRAS Årlig sjekk av detektorer - Eltek | Normal | Closed | 2019-03-21 10:26 | 2019-03-22 10:26 |  | 2019-03-28 09:12 | 2019-03-28 09:12 |  |  | Approved | 26.02.2019 12:12:15 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 25.02.2019 10:35:01 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-22 10:32 | 2019-03-22 10:32 | 2019-02-25 10:26
CHG0031078 | DigiPlex Stockholm 1 AB | Yearly scheduled maintenance fire alarm and fire suppression system | Normal | Closed | 2019-03-25 08:00 | 2019-03-26 17:00 |  | 2019-03-28 14:52 | 2019-03-28 14:52 |  |  | Approved | 22.03.2019 14:56:29 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-25 09:28 | 2019-03-26 12:10 | 2019-02-25 09:11
CHG0031077 | DigiPlex Norway AS | ITV kamera (1-0168) Main door | Normal | Closed | 2019-02-25 10:00 | 2019-02-25 12:00 |  | 2019-03-21 10:12 | 2019-03-21 10:12 |  |  | Approved | 26.02.2019 12:11:42 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-02-26 12:30 | 2019-02-26 14:00 | 2019-02-21 14:40
CHG0031076 | DigiPlex Stockholm 1 AB | Modify Door Closer | Normal | Closed | 2019-03-05 08:00 | 2019-03-05 17:00 |  | 2019-04-25 14:25 | 2019-04-25 14:25 |  |  | Approved |  | 2019-03-05 12:13 | 2019-04-12 16:00 | 2019-02-20 17:32
CHG0031075 | DigiPlex Norway AS | Generator EF4 stopped during running of EF-generator | Normal | Closed | 2019-02-21 10:21 | 2019-02-22 10:21 |  | 2019-03-04 09:48 | 2019-03-04 09:48 | Alexander Olsen |  | Approved | 21.02.2019 08:45:41 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 20.02.2019 16:29:08 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-21 10:00 | 2019-02-21 16:00 | 2019-02-19 08:52
CHG0031073 | DigiPlex Rosenholm AS | R02MOD01.1, new cagemodule. | Normal | Closed | 2019-02-17 08:36 | 2019-04-05 08:36 |  | 2019-05-16 09:08 | 2019-05-16 09:08 |  |  | Approved | 15.02.2019 21:35:23 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 15.02.2019 18:07:09 - sgh_syscom (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-15 08:36 | 2019-05-13 12:00 | 2019-02-15 08:40
CHG0031072 | DigiPlex Norway AS | 03MOD03.4, new cagemodule. | Normal | Closed | 2019-02-14 14:48 | 2019-03-29 14:48 |  | 2019-05-01 22:13 | 2019-05-01 22:13 |  |  | Approved | 15.02.2019 11:27:03 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-02-14 14:48 | 2019-04-01 16:00 | 2019-02-14 14:49
CHG0031071 | DigiPlex Stockholm 1 AB | Sounder/Beacon moving | Normal | Closed | 2019-02-15 13:00 | 2019-02-15 18:00 |  | 2019-03-28 14:39 | 2019-03-28 14:39 |  |  | Approved |  | 2019-02-15 14:55 | 2019-02-15 14:56 | 2019-02-14 14:44
CHG0031070 | DigiPlex Norway AS | Core drilling 00STR 01 | Normal | Closed | 2019-02-15 11:54 | 2019-03-15 11:54 |  | 2019-03-21 09:08 | 2019-03-21 09:08 |  |  | Approved | 15.02.2019 11:30:18 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-02-15 11:54 | 2019-03-15 11:54 | 2019-02-14 11:56
CHG0031069 | DigiPlex Rosenholm AS | VMWare platform migration DNAS & DRAS week 9 & 10 2019 | Normal | Closed | 2019-02-25 10:00 | 2019-03-07 17:00 |  | 2019-08-01 09:52 | 2019-08-01 09:52 |  | 2019-02-14 | Approved | 18.02.2019 13:00:09 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 14.02.2019 08:51:43 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-25 09:19 | 2019-06-28 09:19 | 2019-02-14 08:35
CHG0031068 | DigiPlex Rosenholm AS | Completion of switch and cabling IT rack DRAS L2E | Normal | Closed | 2019-02-19 10:00 | 2019-02-19 11:00 |  | 2019-03-28 14:51 | 2019-03-28 14:51 |  | 2019-02-14 | Approved | 14.02.2019 14:39:51 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 14.02.2019 08:49:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-02-14 08:19
CHG0031067 | DigiPlex Rosenholm AS | DRAS Minor service på generatorene | Normal | Closed | 2019-02-25 12:57 | 2019-03-01 12:58 |  | 2019-03-14 08:24 | 2019-03-14 08:24 |  |  | Approved | 14.02.2019 15:05:53 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-02-25 10:31 | 2019-03-01 10:31 | 2019-02-13 12:58
CHG0031064 | DigiPlex Norway AS | Aurskog Power skal bytte 4 starbatterier på gennerator 5 | Normal | Closed | 2019-02-18 08:00 | 2019-02-18 16:00 |  | 2019-04-11 13:02 | 2019-04-11 13:02 |  |  | Approved | 15.02.2019 10:33:08 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-02-18 09:22 | 2019-02-18 14:23 | 2019-02-13 11:48
CHG0031063 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2019-02-18 09:52 | 2019-02-22 09:52 |  | 2019-03-14 08:37 | 2019-03-14 08:37 |  |  | Approved |  | 2019-02-18 09:00 | 2019-03-22 10:29 | 2019-02-13 09:51
CHG0031062 | DigiPlex Norway AS | Change batteries on UPS D6 | Normal | Closed | 2019-02-14 10:53 | 2019-02-14 10:53 |  | 2019-03-14 08:49 | 2019-03-14 08:49 |  |  | Approved | 14.02.2019 09:14:11 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 12.02.2019 16:33:13 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-14 12:00 | 2019-02-14 14:00 | 2019-02-12 10:53
CHG0031061 | DigiPlex Norway AS | PODPLT03 replace LL board. | Normal | Closed | 2019-02-13 08:00 | 2019-03-01 10:12 |  | 2019-04-12 11:32 | 2019-04-12 11:32 |  |  | Approved | 13.02.2019 12:56:15 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-02-13 08:06 | 2019-05-01 10:07 | 2019-02-12 10:14
CHG0031060 | DigiPlex Norway AS | Change Sec controller in 03 | Normal | Closed | 2019-02-13 10:53 | 2019-02-13 10:53 |  | 2019-03-14 08:41 | 2019-03-14 08:41 |  |  | Approved | 12.02.2019 10:44:36 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-02-08 09:32 | 2019-03-08 13:00 | 2019-02-11 22:35
CHG0031059 | DigiPlex Stockholm 1 AB | Moving sirens and beacons | Normal | Closed | 2019-02-12 07:49 | 2019-02-15 07:49 |  | 2019-03-28 14:38 | 2019-03-28 14:38 |  |  | Approved | 11.02.2019 09:18:56 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-15 14:57 | 2019-02-15 14:57 | 2019-02-11 07:54
CHG0031055 | DigiPlex Norway AS | New 50 pair kobber kabel mellom CCR-A og CCR-B | Emergency | Closed | 2019-02-08 08:00 | 2019-02-08 18:00 |  | 2019-02-15 18:39 | 2019-02-15 18:39 |  |  | Approved | 08.02.2019 20:53:15 - pviken (Approval history) Group approval for CAB Approval NO approved by user Pål Rune Viken (CAB approval). 08.02.2019 08:53:36 - fekay (Approval history) Group approval for eCAB Approval approved by user Frode Elden Kay (eCAB approval). | 2019-02-08 09:00 | 2019-02-13 11:00 | 2019-02-08 07:35
CHG0031054 | DigiPlex Rosenholm AS | DRAS. Rep av CCUer etter service | Normal | Closed | 2019-02-25 10:11 | 2019-04-12 10:12 |  | 2019-05-01 22:14 | 2019-05-01 22:14 |  |  | Approved | 07.02.2019 13:05:17 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 07.02.2019 12:52:30 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-25 09:48 | 2019-04-26 09:48 | 2019-02-07 10:12
CHG0031053 | DigiPlex All | Rollout of iPhone management and security protection | Normal | Implement | 2019-02-11 11:00 | 2019-02-14 16:00 |  | 2019-05-29 10:27 |  |  |  | Approved | 07.02.2019 09:13:02 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 07.02.2019 08:12:39 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-02-06 16:03
CHG0031052 | DigiPlex Norway AS | Gapit integration DNAS | Normal | Implement | 2019-02-07 15:24 | 2019-03-29 15:24 |  | 2019-05-23 10:23 |  |  |  | Approved | 08.02.2019 09:43:08 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 06.02.2019 15:39:46 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2019-02-06 15:27
CHG0031051 | DigiPlex Rosenholm AS | DRAS. Rep etter årskontroll slukkesystem | Normal | Closed | 2019-02-11 12:36 | 2019-02-12 12:36 |  | 2019-04-09 11:04 | 2019-04-09 11:04 |  |  | Approved | 07.02.2019 10:42:20 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 07.02.2019 08:19:23 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-11 21:15 | 2019-04-08 21:16 | 2019-02-06 12:36
CHG0031050 | DigiPlex Norway AS | Parametere i ladesyklusen skal forandres på alle UPS'ene i E og F | Normal | Closed | 2019-02-08 08:00 | 2019-02-08 16:00 |  | 2019-04-11 12:56 | 2019-04-11 12:56 |  |  | Approved | 08.02.2019 08:52:55 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 08.02.2019 08:41:55 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-08 08:16 | 2019-02-08 14:16 | 2019-02-06 10:41
CHG0031049 | DigiPlex Norway AS | Fiber cabling from CCR-A and B to -01Mod02.2 | Normal | Closed | 2019-02-07 07:00 | 2019-02-22 16:00 |  | 2019-02-14 08:57 | 2019-02-14 08:57 |  |  | Approved | 06.02.2019 10:15:15 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 05.02.2019 15:12:47 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-11 07:30 | 2019-02-13 14:00 | 2019-02-05 10:01
CHG0031048 | DigiPlex Stockholm 1 AB | Global Site Setup | Normal | Closed | 2019-02-04 07:00 | 2019-04-30 17:00 |  | 2019-04-25 14:26 | 2019-04-25 14:26 |  |  | Approved | 01.02.2019 09:09:22 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-31 14:53 | 2019-02-04 14:53 | 2019-01-31 16:20
CHG0031047 | DigiPlex Stockholm 1 AB | General Construction Phase RAMS | Normal | Closed | 2019-02-04 07:00 | 2019-05-31 17:00 |  | 2019-08-22 14:42 | 2019-08-22 14:42 |  |  | Approved | 01.02.2019 09:06:04 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-04 07:00 | 2019-07-05 09:30 | 2019-01-31 16:07
CHG0031045 | DigiPlex Norway AS | TEST Change Syscom | Normal | Canceled |  |  |  | 2019-01-28 09:15 | 2019-01-28 09:15 | Eivind Sandnes |  | Requested |  |  |  | 2019-01-28 09:15
CHG0031042 | DigiPlex Rosenholm AS | Sjekk/rep av alle feielister | Normal | Closed | 2019-01-28 10:11 | 2019-02-08 10:12 |  | 2019-02-13 11:09 | 2019-02-13 11:09 |  |  | Approved | 01.02.2019 09:06:30 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 25.01.2019 10:47:46 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-02-04 08:50 | 2019-02-05 08:50 | 2019-01-25 10:12
CHG0031040 | DigiPlex Stockholm 1 AB | Scaffolding for project Rudolph | Normal | Closed | 2019-01-28 07:00 | 2019-05-03 17:00 |  | 2019-05-16 16:08 | 2019-05-16 16:08 |  |  | Approved | 24.01.2019 14:24:26 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-28 07:00 | 2019-05-12 17:00 | 2019-01-24 12:16
CHG0031037 | DigiPlex Rosenholm AS | Lasttest av generatorer | Normal | Closed | 2019-01-28 09:41 | 2019-02-28 09:41 |  | 2019-03-07 07:58 | 2019-03-07 07:58 |  |  | Approved | 25.01.2019 09:44:07 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). | 2019-02-11 10:29 | 2019-02-28 10:09 | 2019-01-24 09:39
CHG0031035 | DigiPlex Fet AS | Move Fibre DFAS 2, Access to man hole for fibre DFAS 1 | Normal | Closed | 2019-01-25 15:18 | 2019-01-26 15:18 |  | 2019-03-14 08:34 | 2019-03-14 08:34 |  | 2019-01-23 | Approved | 24.01.2019 08:03:52 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 23.01.2019 15:23:29 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-24 13:09 | 2019-03-05 13:10 | 2019-01-23 15:10
CHG0031034 | DigiPlex Norway AS | Rense filtere i pumpe P1 til P6 | Normal | Closed | 2019-01-29 08:18 | 2019-01-30 15:18 |  | 2019-10-04 14:28 | 2019-10-04 14:28 | Geir Almquist |  | Approved | 01.02.2019 09:06:06 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-09-04 14:26 | 2019-10-04 14:26 | 2019-01-23 14:40
CHG0031033 | DigiPlex Stockholm 1 AB | East facade isolation change | Normal | Closed | 2019-01-24 13:25 | 2019-02-28 13:25 |  | 2019-03-21 14:45 | 2019-03-21 14:45 |  |  | Approved | 23.01.2019 08:45:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-24 09:43 | 2019-03-14 09:44 | 2019-01-22 14:05
CHG0031032 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Canceled |  |  |  | 2019-01-21 14:24 |  |  |  | Approved |  |  |  | 2019-01-21 10:55
CHG0031031 | DigiPlex Rosenholm AS | Fylling av diesel | Normal | Closed | 2019-01-22 08:36 | 2019-02-08 08:37 |  | 2019-02-04 14:49 | 2019-02-01 09:22 |  |  | Approved | 21.01.2019 14:27:21 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 21.01.2019 14:25:17 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-29 12:58 | 2019-01-29 12:58 | 2019-01-21 08:38
CHG0031029 | DigiPlex Rosenholm AS | Omdøpe kortlesere | Normal | Closed | 2019-01-20 10:46 | 2019-02-01 10:46 |  | 2019-02-02 08:56 | 2019-02-02 08:56 |  |  | Approved | 21.01.2019 07:32:51 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 18.01.2019 11:29:15 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-21 12:56 | 2019-02-01 12:56 | 2019-01-18 10:48
CHG0031028 | DigiPlex Stockholm 1 AB | Remove Lights for Project Rudolph | Normal | Closed | 2019-01-21 09:41 | 2019-01-25 09:41 |  | 2019-03-14 08:35 | 2019-03-14 08:35 |  |  | Approved |  | 2019-01-22 14:40 | 2019-01-24 14:40 | 2019-01-17 10:04
CHG0031027 | DigiPlex Norway AS | Move the perimeter fence | Normal | Closed | 2019-01-17 08:18 | 2019-01-31 08:18 |  | 2019-02-01 09:21 | 2019-02-01 09:21 |  | 2019-01-17 | Approved | 21.01.2019 07:31:16 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 17.01.2019 09:58:57 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-17 11:33 | 2019-01-23 11:34 | 2019-01-17 08:17
CHG0031026 | DigiPlex Norway AS | Firmware update on pumps k1-k6 | Normal | Closed | 2019-01-16 09:40 | 2019-01-16 12:00 |  | 2019-01-25 10:51 | 2019-01-25 10:51 |  |  | Approved | 16.01.2019 09:49:22 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 16.01.2019 09:47:20 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-16 09:40 | 2019-01-16 11:26 | 2019-01-16 09:38
CHG0031024 | DigiPlex Stockholm 1 AB | Introdcution of new I/O into OS51 | Normal | Closed | 2019-01-16 09:00 | 2019-01-16 16:00 |  | 2019-01-18 11:35 | 2019-01-18 11:35 |  |  | Approved | 15.01.2019 16:52:40 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-16 14:18 | 2019-01-16 14:19 | 2019-01-15 16:44
CHG0031023 | DigiPlex Norway AS | Refurbishment of 02MOD04 | Normal | Closed | 2019-01-17 10:00 | 2019-02-22 08:36 |  | 2019-02-27 08:14 | 2019-02-27 08:14 |  |  | Approved | 17.01.2019 09:17:54 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 15.01.2019 16:55:23 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-17 10:00 | 2019-02-01 10:10 | 2019-01-15 08:39
CHG0031022 | DigiPlex Fet AS | Reinstall DFAS switches A2-3 | Emergency | Closed | 2019-01-14 15:00 | 2019-01-15 13:00 |  | 2019-02-01 09:17 | 2019-02-01 09:17 |  |  | Approved | 15.01.2019 11:23:56 - atorp (Approval history) Group approval for CAB Approval NO approved by user Atle Torp (CAB approval). 15.01.2019 09:25:53 - dobraekken (Approval history) Group approval for eCAB Approval approved by user Dag Oscar Brækken (eCAB approval). | 2019-01-15 11:00 | 2019-01-24 12:00 | 2019-01-14 15:47
CHG0031021 | DigiPlex Norway AS | Module Specialist cleaning | Normal | Closed | 2019-01-16 08:00 | 2019-01-17 18:00 |  | 2019-02-01 09:26 | 2019-02-01 09:26 |  |  | Approved | 15.01.2019 11:43:20 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-01-16 08:00 | 2019-01-17 18:00 | 2019-01-14 08:45
CHG0031020 | DigiPlex Rosenholm AS | Module Specialist cleaning | Normal | Closed | 2019-01-18 08:00 | 2019-01-18 18:00 |  | 2019-02-01 09:14 | 2019-02-01 09:14 |  |  | Approved | 15.01.2019 08:47:04 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2019-01-18 08:00 | 2019-01-18 18:00 | 2019-01-14 08:40
CHG0031017 | DigiPlex Stockholm 1 AB | Change of fuse in switch panel North Corridor | Normal | Closed | 2019-01-14 08:00 | 2019-01-14 10:00 |  | 2019-01-17 14:39 | 2019-01-17 14:39 |  |  | Approved | 11.01.2019 13:11:35 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-14 08:00 | 2019-01-14 10:00 | 2019-01-11 13:04
CHG0031015 | DigiPlex Rosenholm AS | Fiber cabling from CCR-B to R01MOD04.3, and Cat6 cabling from CCR-A to R01MOD04.3 (AVS1105) | Normal | Closed | 2019-01-14 13:42 | 2019-01-25 13:42 |  | 2019-01-24 14:22 | 2019-01-24 14:22 |  |  | Approved | 11.01.2019 15:03:02 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 11.01.2019 13:46:32 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-15 07:00 | 2019-01-21 13:30 | 2019-01-10 15:01
CHG0031013 | DigiPlex Norway AS | 02MOD04, BMS works. | Normal | Closed | 2019-01-14 12:00 | 2019-02-01 12:00 |  | 2019-02-18 09:35 | 2019-02-18 09:35 |  |  | Approved | 11.01.2019 13:00:59 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-01-14 12:00 | 2019-02-01 10:06 | 2019-01-10 12:02
CHG0031010 | DigiPlex Norway AS | battery fault UPS D6 | Normal | Canceled |  |  |  | 2019-01-21 07:27 |  |  |  | Approved | 14.01.2019 09:00:25 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2019-01-09 14:27
CHG0031008 | DigiPlex Stockholm 1 AB | Level 3 remedial work | Normal | Closed | 2019-01-10 07:00 | 2019-01-18 17:00 |  | 2019-02-05 15:14 | 2019-02-05 15:14 |  |  | Approved | 09.01.2019 09:54:22 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-13 08:51 | 2019-01-25 13:03 | 2019-01-08 15:48
CHG0031007 | DigiPlex Norway AS | Fault on chiller C compressor 1 | Normal | Closed | 2019-01-09 08:00 | 2019-01-11 15:00 |  | 2019-02-18 13:42 | 2019-02-18 13:42 |  |  | Approved | 09.01.2019 09:25:13 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 09.01.2019 09:23:16 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-11 13:18 | 2019-01-18 13:18 | 2019-01-08 14:48
CHG0031005 | DigiPlex Stockholm 1 AB | DH7-B UPS Frame A2 replacement | Normal | Closed | 2019-01-21 07:00 | 2019-01-24 18:00 |  | 2019-02-01 09:22 | 2019-02-01 09:22 |  |  | Approved |  | 2019-01-21 08:00 | 2019-01-24 16:50 | 2019-01-08 13:59
CHG0031004 | DigiPlex Norway AS | Fix faults after annual fire system check | Normal | Closed | 2019-01-22 08:00 | 2019-01-24 16:00 |  | 2019-03-07 07:31 | 2019-03-07 07:31 |  |  | Approved | 08.01.2019 16:06:43 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2019-01-22 10:06 | 2019-01-22 10:07 | 2019-01-07 14:40
CHG0031002 | DigiPlex Fet AS | Graving av grøft | Normal | Closed | 2019-01-14 08:00 | 2019-01-16 15:00 |  | 2019-02-13 11:02 | 2019-02-13 11:02 |  |  | Approved | 04.01.2019 10:57:06 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 04.01.2019 09:55:12 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-14 12:49 | 2019-02-07 12:49 | 2019-01-04 09:46
CHG0031001 | DigiPlex Fet AS | Ombygging av +AM=433.331 | Normal | Closed | 2019-01-06 08:00 | 2019-01-06 12:00 |  | 2019-01-14 07:56 | 2019-01-14 07:56 |  |  | Approved | 04.01.2019 14:34:13 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 04.01.2019 09:52:03 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-06 11:57 | 2019-01-06 11:57 | 2019-01-04 09:16
CHG0031000 | DigiPlex Rosenholm AS | DRAS: Årlig service på adgangssystemet | Normal | Closed | 2019-01-18 10:13 | 2019-01-18 10:14 |  | 2019-01-25 10:50 | 2019-01-25 10:50 |  |  | Approved | 04.01.2019 08:55:54 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 04.01.2019 08:51:20 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-18 08:30 | 2019-01-18 08:30 | 2019-01-03 10:14
CHG0030999 | DigiPlex Rosenholm AS | DRAS: Årlig service av lekkasje deteksjon | Normal | Closed | 2019-01-07 08:42 | 2019-01-16 08:43 |  | 2019-01-16 09:51 | 2019-01-16 09:51 |  |  | Approved | 04.01.2019 08:54:25 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 03.01.2019 09:24:22 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-07 11:44 | 2019-01-09 09:00 | 2019-01-03 08:43
CHG0030998 | DigiPlex Norway AS | Fiber cabling from CCR-A | Normal | Closed | 2019-01-06 07:00 | 2019-01-18 16:00 |  | 2019-01-18 11:32 | 2019-01-18 11:32 |  |  | Approved | 04.01.2019 09:16:04 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 02.01.2019 14:29:52 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-08 07:00 | 2019-01-16 15:00 | 2019-01-02 12:16
CHG0030997 | DigiPlex Stockholm 1 AB | Vents to void space | Normal | Closed | 2019-01-14 13:35 | 2019-02-08 13:35 |  | 2019-03-14 08:40 | 2019-03-14 08:40 |  |  | Approved | 04.01.2019 10:02:27 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-15 14:37 | 2019-02-06 14:37 | 2018-12-21 13:37
CHG0030996 | DigiPlex Stockholm 1 AB | Re-paint floor in cooridor and MMR1B | Normal | Closed | 2019-01-07 13:32 | 2019-01-08 13:33 |  | 2019-01-16 10:02 | 2019-01-16 10:02 |  |  | Approved | 21.12.2018 13:47:59 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-07 14:08 | 2019-01-10 14:08 | 2018-12-21 13:33
CHG0030994 | DigiPlex Stockholm 1 AB | New roller shutters | Normal | Closed | 2019-01-07 14:49 | 2019-01-18 14:49 |  | 2019-02-27 08:12 | 2019-02-27 08:12 |  |  | Approved | 18.12.2018 07:51:46 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-20 08:48 | 2019-01-31 11:08 | 2018-12-17 14:50
CHG0030992 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2018-12-17 08:23 | 2018-12-31 08:24 |  | 2019-01-04 08:57 | 2019-01-04 08:57 |  |  | Approved |  | 2018-12-17 08:24 | 2019-01-03 14:18 | 2018-12-17 08:22
CHG0030991 | DigiPlex Norway AS | Annual check of the Fire Alarm and Fire Suppression system | Normal | Closed | 2018-12-17 08:00 | 2018-12-18 16:00 |  | 2019-01-04 09:02 | 2019-01-04 09:02 |  |  | Approved | 17.12.2018 10:11:10 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 17.12.2018 09:52:39 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-17 09:00 | 2018-12-18 15:00 | 2018-12-16 20:45
CHG0030990 | DigiPlex Fet AS | Adding new channel | Normal | Closed | 2018-12-17 08:07 | 2018-12-31 15:07 |  | 2019-01-07 07:22 | 2019-01-07 07:22 |  |  | Approved | 17.12.2018 09:18:56 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-12-17 13:25 | 2019-01-03 13:26 | 2018-12-14 10:27
CHG0030989 | DigiPlex Stockholm 1 AB | Protection for gas valves | Normal | Closed | 2019-01-07 07:00 | 2019-01-11 17:00 |  | 2019-02-02 08:51 | 2019-02-02 08:51 |  |  | Approved | 13.12.2018 13:09:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-09 13:33 | 2019-01-18 13:34 | 2018-12-13 12:41
CHG0030987 | DigiPlex Norway AS | Demontering av 1 stk retningsbestemt antenne Tak (Broadnet) | Normal | Closed | 2018-12-17 12:00 | 2018-12-21 09:07 |  | 2018-12-20 08:48 | 2018-12-20 08:48 |  |  | Approved | 13.12.2018 11:38:11 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 13.12.2018 11:01:41 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-19 12:00 | 2018-12-19 12:15 | 2018-12-13 09:11
CHG0030986 | DigiPlex Stockholm 1 AB | Installation of barriers | Normal | Closed | 2018-12-17 07:00 | 2018-12-21 17:00 |  | 2019-01-14 07:53 | 2019-01-14 07:53 |  |  | Approved | 13.12.2018 10:53:27 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-17 16:22 | 2018-12-20 16:22 | 2018-12-13 08:08
CHG0030985 | DigiPlex Stockholm 1 AB | Hot Water Tanks | Normal | Closed | 2019-01-08 07:00 | 2019-01-18 17:00 |  | 2019-02-02 08:58 | 2019-02-02 08:58 |  |  | Approved |  | 2018-12-17 09:15 | 2019-01-30 13:00 | 2018-12-12 11:04
CHG0030984 | DigiPlex Rosenholm AS | Vask av gulv og vegger i PLT10 med kulvert | Normal | Closed | 2018-12-13 14:22 | 2018-12-21 14:22 |  | 2019-01-04 08:58 | 2019-01-04 08:58 |  |  | Approved | 13.12.2018 11:03:23 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 12.12.2018 08:59:22 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-18 08:49 | 2018-12-18 08:49 | 2018-12-11 14:22
CHG0030983 | DigiPlex Stockholm 1 AB | Review BMS graphics | Normal | Closed | 2018-12-17 07:00 | 2018-12-19 17:00 |  | 2019-01-18 11:34 | 2019-01-18 11:34 |  |  | Approved |  | 2018-12-17 15:21 | 2018-12-19 15:21 | 2018-12-11 12:32
CHG0030982 | DigiPlex Fet AS | Ombygging av 434.213 Vanntavle | Normal | Closed | 2018-12-12 08:00 | 2018-12-21 09:43 |  | 2019-01-07 07:22 | 2019-01-07 07:22 |  |  | Approved | 13.12.2018 11:49:07 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 11.12.2018 14:49:29 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 11.12.2018 10:55:17 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-11 13:21 | 2018-12-12 13:22 | 2018-12-11 09:55
CHG0030981 | DigiPlex Norway AS | Ta ned og flytte tap-off bokser i 02Mod04 til 02Mod03 | Normal | Closed | 2018-12-07 09:37 | 2018-12-07 16:00 |  | 2019-04-17 10:25 | 2019-04-17 10:25 |  |  | Approved | 10.12.2018 12:00:39 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 07.12.2018 11:02:30 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 07.12.2018 10:47:44 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-03-31 11:34 | 2019-04-05 13:00 | 2018-12-07 09:34
CHG0030980 | DigiPlex Norway AS | UPS Symmetra maintenance | Normal | Closed | 2018-12-10 08:00 | 2018-12-11 16:00 |  | 2019-01-04 08:59 | 2019-01-04 08:59 |  |  | Approved | 07.12.2018 11:02:32 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 07.12.2018 10:48:27 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-10 08:00 | 2018-12-11 15:00 | 2018-12-07 09:05
CHG0030979 | DigiPlex Norway AS | Fiber cabling from 03Mod01.3 to CCR-B and CCR-C (Century Link AVS) | Normal | Closed | 2018-12-09 15:33 | 2018-12-20 15:33 |  | 2018-12-21 13:44 | 2018-12-21 13:44 |  |  | Approved | 12.12.2018 11:57:09 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 12.12.2018 08:53:22 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-18 07:00 | 2018-12-20 13:30 | 2018-12-06 15:35
CHG0030978 | DigiPlex Fet AS | DFAS network modification for OSL20 project | Normal | Closed | 2018-12-06 13:00 | 2018-12-06 14:00 |  | 2019-02-01 09:16 | 2019-02-01 09:16 |  | 2018-12-06 | Approved | 11.12.2018 14:46:44 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 06.12.2018 09:05:20 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-06 13:00 | 2018-12-07 13:00 | 2018-12-05 19:28
CHG0030977 | DigiPlex Norway AS | Shutdown discontinued servers DNAS & DRAS | Normal | Closed | 2018-12-09 10:00 | 2018-12-09 12:00 |  | 2019-03-28 14:50 | 2019-03-28 14:50 |  | 2018-12-06 | Approved | 10.12.2018 11:57:32 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 06.12.2018 08:45:04 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-13 09:00 | 2019-01-18 15:00 | 2018-12-05 18:23
CHG0030976 | DigiPlex Stockholm 1 AB | Modifications to Safe Mode Software, BMS | Normal | Closed | 2019-01-14 08:05 | 2019-01-18 08:05 |  | 2019-03-14 08:36 | 2019-03-14 08:36 |  |  | Approved |  | 2019-01-14 14:41 | 2019-01-17 14:41 | 2018-12-05 08:06
CHG0030975 | DigiPlex Rosenholm AS | Gulvplate i vareinngang må byttes | Normal | Closed | 2018-12-10 08:26 | 2018-12-21 08:26 |  | 2019-03-14 08:21 | 2019-03-14 08:21 |  |  | Approved | 05.12.2018 08:34:45 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 05.12.2018 07:19:23 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 04.12.2018 10:50:45 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-10 15:11 | 2019-03-07 15:11 | 2018-12-04 08:28
CHG0030973 | DigiPlex Norway AS | 3m service of Humidifiers, DNAS | Normal | Closed | 2018-12-04 11:15 | 2018-12-14 11:15 |  | 2018-12-21 13:46 | 2018-12-21 13:46 |  |  | Approved | 10.12.2018 10:02:39 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 04.12.2018 10:51:36 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2018-12-03 11:15
CHG0030972 | DigiPlex Norway AS | Annual water leak detection system maintenance | Normal | Closed | 2018-12-02 08:00 | 2018-12-13 16:00 |  | 2018-12-13 13:25 | 2018-12-13 13:25 |  |  | Approved | 03.12.2018 09:32:02 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-12-03 11:34 | 2018-12-07 11:33 | 2018-11-30 15:10
CHG0030971 | DigiPlex Norway AS | Fiber cabling from CCR-A2 to 02Mod07.2 (AVS1115) | Normal | Closed | 2018-12-04 07:00 | 2018-12-14 16:00 |  | 2018-12-21 13:43 | 2018-12-21 13:43 |  |  | Approved | 03.12.2018 09:50:06 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-12-18 07:00 | 2018-12-20 13:30 | 2018-11-30 15:03
CHG0030970 | DigiPlex Stockholm 1 AB | DH8 Roof Fence | Normal | Closed | 2018-12-03 12:17 | 2018-12-21 12:17 |  | 2019-02-13 11:10 | 2019-02-13 11:10 |  |  | Approved |  | 2018-12-09 13:01 | 2019-01-18 13:01 | 2018-11-30 12:48
CHG0030968 | DigiPlex Rosenholm AS | Relocating pipe VVS 1 | Normal | Closed | 2018-12-03 14:12 | 2018-12-27 14:12 |  | 2018-12-18 09:19 | 2018-12-18 09:19 |  |  | Approved | 07.12.2018 11:26:03 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). 07.12.2018 11:24:51 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 03.12.2018 10:13:39 - albjornstad (Approval history) Group approval for Change-Technical assess group rejected by user Anders Bjørnstad (Technical approvals norway). | 2018-12-03 09:15 | 2018-12-14 09:15 | 2018-11-29 14:15
CHG0030967 | DigiPlex Rosenholm AS | Cardreader STO03. | Normal | Closed | 2018-12-03 13:55 | 2018-12-27 13:55 |  | 2019-01-08 12:06 | 2019-01-08 12:06 |  |  | Approved | 03.12.2018 09:26:26 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-12-03 08:18 | 2019-01-04 08:18 | 2018-11-29 13:58
CHG0030966 | DigiPlex Fet AS | Trekking og terminering av fiber | Normal | Closed | 2018-11-29 08:00 | 2018-12-02 13:13 |  | 2018-12-13 13:12 | 2018-12-13 13:12 |  |  | Approved | 29.11.2018 13:47:19 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 29.11.2018 07:40:08 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-03 14:23 | 2018-12-03 14:23 | 2018-11-28 13:43
CHG0030963 | DigiPlex Fet AS | Inntransport og påplassetting av dataromskjølere | Normal | Closed | 2018-11-29 07:00 | 2018-11-29 16:00 |  | 2018-12-13 13:26 | 2018-12-13 13:26 |  |  | Approved | 28.11.2018 09:31:25 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 28.11.2018 09:21:47 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-04 13:44 | 2018-12-04 13:44 | 2018-11-28 08:40
CHG0030962 | DigiPlex Copenhagen 1 ApS | 3M test av batterier | Standard | Canceled |  |  |  | 2018-12-11 13:38 |  |  |  | Approved |  |  |  | 2018-11-27 12:26
CHG0030961 | DigiPlex Norway AS | Measure phase distribution in critical switchboards, 00 MOD 05 | Normal | Canceled |  |  |  | 2019-01-03 08:28 |  |  |  | Not Yet Requested |  |  |  | 2018-11-27 10:05
CHG0030960 | DigiPlex Fet AS | AHU Offices | Normal | Closed | 2018-11-29 08:00 | 2018-11-29 16:00 |  | 2018-12-19 12:19 | 2018-12-19 12:19 |  | 2018-11-29 | Approved | 28.11.2018 09:22:34 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 27.11.2018 12:32:49 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 27.11.2018 09:11:11 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-29 14:21 | 2018-11-29 14:21 | 2018-11-27 09:10
CHG0030959 | DigiPlex Norway AS | Software update on generator C controller | Normal | Closed | 2018-11-26 12:18 | 2018-11-29 12:18 |  | 2018-12-20 09:17 | 2018-12-20 09:16 |  | 2018-12-20 | Approved | 26.11.2018 14:12:12 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 26.11.2018 14:10:13 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-27 08:00 | 2018-11-29 12:30 | 2018-11-26 12:19
CHG0030956 | DigiPlex Rosenholm AS | Service på generatorer DRAS | Normal | Closed | 2018-11-26 08:48 | 2018-11-30 08:48 |  | 2018-12-06 09:10 | 2018-12-06 09:10 |  |  | Approved | 26.11.2018 08:58:33 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 26.11.2018 08:50:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2018-11-26 08:48
CHG0030951 | DigiPlex Norway AS |  | Normal | Canceled |  |  |  | 2018-11-22 14:47 |  |  |  | Not Yet Requested |  |  |  | 2018-11-22 14:45
CHG0030949 | DigiPlex Norway AS | SAT of CCU Level 3 | Normal | Closed | 2018-11-23 08:00 | 2018-11-26 16:00 |  | 2019-01-07 07:27 | 2019-01-07 07:27 |  |  | Approved | 23.11.2018 08:50:45 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 22.11.2018 21:54:46 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-23 20:53 | 2018-11-29 20:53 | 2018-11-22 13:50
CHG0030948 | DigiPlex Norway AS |  | Normal | Canceled |  |  |  | 2018-11-22 11:18 |  |  |  | Not Yet Requested |  |  |  | 2018-11-22 11:15
CHG0030947 | DigiPlex Norway AS | ISAT 03MOD03 | Normal | Closed | 2018-11-26 17:20 | 2018-12-14 17:20 |  | 2019-01-07 07:28 | 2019-01-07 07:28 |  |  | Approved | 27.11.2018 12:18:32 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 22.11.2018 12:51:50 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 22.11.2018 07:35:33 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-26 20:44 | 2018-12-13 20:45 | 2018-11-21 17:23
CHG0030945 | DigiPlex Stockholm 1 AB | Re-tiling shower room | Normal | Closed | 2019-01-08 07:00 | 2019-01-11 17:00 |  | 2019-02-02 08:59 | 2019-02-02 08:59 |  |  | Approved | 22.11.2018 07:34:08 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-29 07:45 | 2019-01-25 12:58 | 2018-11-21 13:08
CHG0030944 | DigiPlex Rosenholm AS | 12M Full skala test brannalarm anlegg DRAS | Normal | Closed | 2018-12-19 13:29 | 2018-12-20 13:30 |  | 2019-01-04 08:57 | 2019-01-04 08:57 |  |  | Approved | 26.11.2018 10:16:50 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-12-19 08:50 | 2018-12-19 08:50 | 2018-11-20 13:32
CHG0030943 | DigiPlex Fet AS | Innheising av aggregat | Normal | Closed | 2018-12-03 07:00 | 2018-12-03 16:00 |  | 2018-12-19 12:17 | 2018-12-19 12:17 |  | 2018-12-19 | Approved | 27.11.2018 12:31:37 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 20.11.2018 09:27:22 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-03 13:34 | 2018-12-03 13:34 | 2018-11-19 13:39
CHG0030941 | DigiPlex Norway AS | 3M test av batterier | Standard | Canceled |  |  |  | 2018-11-19 12:17 |  |  |  | Approved |  |  |  | 2018-11-19 09:23
CHG0030940 | DigiPlex Rosenholm AS | 3M test av batterier | Standard | Closed | 2018-11-21 15:10 | 2018-11-23 15:10 |  | 2018-11-29 09:12 | 2018-11-29 09:12 |  |  | Approved |  | 2018-11-21 15:00 | 2018-11-21 08:55 | 2018-11-19 09:21
CHG0030939 | DigiPlex Rosenholm AS | Service på pumper DRAS | Normal | Closed | 2018-12-03 12:39 | 2018-12-04 12:40 |  | 2018-12-13 13:27 | 2018-12-13 13:27 |  |  | Approved | 29.11.2018 09:35:48 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 29.11.2018 07:38:51 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2018-11-19 09:15
CHG0030938 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Canceled |  |  |  | 2018-12-17 09:33 |  |  |  | Approved |  |  |  | 2018-11-19 08:52
CHG0030937 | DigiPlex Fet AS | Splitting av G4-skinne | Normal | Closed | 2018-11-26 08:32 | 2018-11-30 08:32 |  | 2019-01-07 07:22 | 2019-01-07 07:22 |  |  | Approved | 27.11.2018 12:25:58 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-26 13:20 | 2018-12-14 13:20 | 2018-11-19 08:36
CHG0030936 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Canceled |  |  |  | 2018-11-19 13:54 | 2018-11-19 13:54 | Frode Elden Kay |  | Approved |  |  |  | 2018-11-19 08:36
CHG0030935 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Canceled |  |  |  | 2018-11-19 13:53 | 2018-11-19 13:53 | Frode Elden Kay |  | Approved |  |  |  | 2018-11-19 08:35
CHG0030934 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Canceled |  |  |  | 2018-11-19 13:53 | 2018-11-19 13:53 | Frode Elden Kay |  | Approved |  |  |  | 2018-11-19 08:35
CHG0030933 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Standard | Closed | 2018-11-19 13:54 | 2018-11-30 13:54 |  | 2018-12-13 13:28 | 2018-12-13 13:28 |  |  | Approved |  | 2018-11-19 13:55 | 2018-11-30 11:48 | 2018-11-19 08:33
CHG0030932 | DigiPlex Fet AS | Montering av nye brytere | Normal | Closed | 2018-11-19 08:22 | 2018-11-23 08:22 |  | 2019-01-23 08:46 | 2019-01-23 08:46 |  |  | Approved | 29.11.2018 09:27:59 - System (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 28.11.2018 09:31:58 - pbakke (Approval history) Group approval for Change-Technical assess group approved by user Patrick Bakke (Technical approvals norway). 28.11.2018 09:28:01 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 27.11.2018 12:30:17 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). | 2019-01-15 11:40 | 2019-01-15 11:40 | 2018-11-19 08:30
CHG0030930 | DigiPlex Stockholm 1 AB | DS1 HV & LV annual switchboard preventive maintenance - Day 2 | Normal | Closed | 2018-11-17 07:00 | 2018-11-17 18:00 |  | 2018-11-22 15:06 | 2018-11-22 15:06 |  |  | Approved | 16.11.2018 19:24:37 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-17 08:00 | 2018-11-17 14:15 | 2018-11-16 15:22
CHG0030929 | DigiPlex Norway AS | CAC installation | Normal | Canceled | 2018-11-19 12:10 | 2018-11-20 12:10 |  | 2018-11-20 09:26 |  |  |  | Rejected | 19.11.2018 08:29:48 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-11-16 12:23
CHG0030927 | DigiPlex Stockholm 1 AB | DS1 HV & LV annual switchboard preventive maintenance - Day 1 | Normal | Closed | 2018-11-16 07:00 | 2018-11-16 18:00 |  | 2018-11-22 15:05 | 2018-11-22 15:05 |  |  | Approved | 16.11.2018 07:22:35 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-16 07:20 | 2018-11-16 16:00 | 2018-11-15 17:06
CHG0030926 | DigiPlex Norway AS | Annual generator D maintenance. | Normal | Closed | 2018-11-19 08:00 | 2018-11-22 16:00 |  | 2018-12-13 13:28 | 2018-12-13 13:28 |  |  | Approved | 16.11.2018 14:49:31 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 16.11.2018 07:27:47 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-19 13:00 | 2018-11-22 16:00 | 2018-11-15 15:21
CHG0030925 | DigiPlex Rosenholm AS | Re-innstallere doseringskammer | Normal | Closed | 2018-12-11 14:48 | 2018-12-21 14:48 |  | 2018-12-18 08:45 | 2018-12-18 08:45 |  |  | Approved | 05.12.2018 15:18:41 - pviken (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 05.12.2018 10:38:56 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 05.12.2018 07:20:23 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 04.12.2018 11:01:53 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 04.12.2018 10:53:16 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-10 08:26 | 2018-12-12 08:26 | 2018-11-15 14:49
CHG0030924 | DigiPlex Fet AS | Excavation for DFAS 2 | Normal | Closed | 2018-11-15 10:18 | 2019-02-13 16:01 |  | 2019-05-13 15:38 | 2019-05-13 15:38 |  |  | Approved | 15.11.2018 10:26:45 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 15.11.2018 10:21:26 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-18 09:41 | 2019-03-29 09:41 | 2018-11-15 09:31
CHG0030922 | DigiPlex Stockholm 1 AB | DH1 UPS B1 & B2 yearly preventive maintenance | Normal | Closed | 2018-11-24 08:00 | 2018-11-25 17:00 |  | 2018-12-06 16:11 | 2018-12-06 16:11 |  |  | Approved | 14.11.2018 07:14:37 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-24 08:00 | 2018-11-24 16:40 | 2018-11-13 16:29
CHG0030920 | DigiPlex Norway AS | Access ifbm modulvask | Normal | Closed | 2018-11-16 09:00 | 2018-11-16 11:00 |  | 2019-02-02 08:58 | 2019-02-02 08:58 |  |  | Approved | 15.11.2018 09:29:22 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 14.11.2018 07:12:11 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2019-01-15 10:00 | 2019-01-15 12:00 | 2018-11-13 14:42
CHG0030919 | DigiPlex Norway AS | New hatch for shaft. | Normal | Closed | 2018-11-14 14:03 | 2018-12-07 14:03 |  | 2018-12-20 09:50 | 2018-12-20 09:50 | Pål Rune Viken | 2018-12-20 | Approved | 15.11.2018 09:17:03 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 14.11.2018 08:54:03 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 14.11.2018 07:11:42 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-18 09:45 | 2018-11-30 09:45 | 2018-11-13 14:06
CHG0030918 | DigiPlex Norway AS | Installation of Cold aisle containment (CAC) in 02MOD06.3 | Normal | Closed | 2018-11-19 07:39 | 2018-11-23 13:39 |  | 2019-01-07 07:29 | 2019-01-07 07:29 |  |  | Approved | 16.11.2018 12:43:27 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 16.11.2018 12:30:35 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 15.11.2018 09:46:48 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). 14.11.2018 07:13:41 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-19 20:57 | 2018-11-23 20:57 | 2018-11-13 13:39
CHG0030916 | DigiPlex Fet AS | AHU Offices | Normal | Canceled | 2018-11-29 07:00 | 2018-11-29 16:00 |  | 2018-11-27 09:02 |  |  |  | Approved | 14.11.2018 08:55:34 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2018-11-13 08:44
CHG0030915 | DigiPlex Stockholm 1 AB | HV/B-feed - Planned power outage | Normal | Closed | 2018-11-13 07:00 | 2018-11-13 17:00 |  | 2018-11-15 14:35 | 2018-11-15 14:35 |  |  | Approved |  | 2018-11-13 07:07 | 2018-11-13 13:06 | 2018-11-12 17:59
CHG0030914 | DigiPlex Stockholm 1 AB | OASIS ATP BMS investigation | Normal | Closed | 2018-11-14 10:00 | 2018-11-14 10:00 |  | 2018-11-22 15:09 | 2018-11-22 15:09 |  |  | Approved |  | 2018-11-14 09:53 | 2018-11-14 09:53 | 2018-11-12 10:00
CHG0030913 | DigiPlex Fet AS | Oppheising luftkjølte kondensatorer | Normal | Closed | 2018-11-14 07:00 | 2018-11-15 16:00 |  | 2018-11-21 07:10 | 2018-11-21 07:10 |  |  | Approved | 13.11.2018 11:16:20 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-11-15 09:04 | 2018-11-16 09:04 | 2018-11-12 08:35
CHG0030912 | DigiPlex Norway AS | Yearly CCU CW service, DNAS | Normal | Closed | 2018-11-12 13:15 | 2018-11-23 13:16 |  | 2018-12-17 09:24 | 2018-12-17 09:24 |  |  | Approved | 12.11.2018 09:28:56 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-11-12 11:40 | 2018-12-14 11:40 | 2018-11-09 13:16
CHG0030911 | DigiPlex Norway AS | Level3 BMS Commissioning. 3rd visit. | Normal | Closed | 2018-11-12 12:32 | 2018-12-28 12:32 |  | 2019-01-08 12:03 | 2019-01-08 12:03 |  |  | Approved | 12.11.2018 12:19:58 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-12 20:42 | 2018-12-28 20:42 | 2018-11-09 12:35
CHG0030910 | DigiPlex Fet AS | Kjerneboring for vanntilførsel | Normal | Closed | 2018-11-09 08:00 | 2018-11-15 16:00 |  | 2019-01-07 07:23 | 2019-01-07 07:23 |  |  | Approved | 12.11.2018 09:21:06 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 09.11.2018 12:37:33 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-09 13:17 | 2018-12-17 13:17 | 2018-11-08 22:04
CHG0030909 | DigiPlex Stockholm 1 AB | Fire Stopping South Corridor | Normal | Closed | 2018-11-14 07:00 | 2018-11-14 13:00 |  | 2018-12-06 16:08 | 2018-12-06 16:08 |  |  | Approved |  | 2018-11-14 09:48 | 2018-11-14 09:48 | 2018-11-08 11:58
CHG0030908 | DigiPlex Stockholm 1 AB | DH1 UPS A1 & A2 yearly preventive maintenance | Normal | Closed | 2018-11-10 08:00 | 2018-11-11 17:00 |  | 2018-11-15 14:35 | 2018-11-15 14:35 |  |  | Approved | 09.11.2018 12:38:14 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-10 08:00 | 2018-11-10 17:45 | 2018-11-08 11:50
CHG0030904 | DigiPlex Norway AS | DNAS - Øke alarmtid på enkelte dører med mye trafikk | Normal | Closed | 2018-11-08 13:29 | 2018-11-09 13:29 |  | 2018-11-12 07:34 | 2018-11-12 07:34 |  |  | Approved | 09.11.2018 12:38:44 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-11-08 14:36 | 2018-11-09 14:36 | 2018-11-06 13:29
CHG0030903 | DigiPlex Rosenholm AS | 12M Service på UPS DRAS | Normal | Closed | 2018-11-27 12:34 | 2018-11-30 12:34 |  | 2018-12-05 16:50 | 2018-12-05 16:50 |  |  | Approved | 07.11.2018 12:43:48 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-11-06 12:37
CHG0030902 | DigiPlex Fet AS | Pipe works in technical room | Normal | Closed | 2018-11-07 08:00 | 2018-11-30 16:00 |  | 2019-01-07 07:24 | 2019-01-07 07:24 |  |  | Approved | 07.11.2018 12:49:59 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-11-07 13:14 | 2018-11-30 13:15 | 2018-11-06 11:11
CHG0030901 | DigiPlex Norway AS | 2 service på Chillere 2018 | Normal | Closed | 2018-11-12 08:00 | 2018-11-16 16:00 |  | 2019-02-13 12:17 | 2019-02-13 12:17 |  |  | Approved | 07.11.2018 14:23:55 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-12 10:58 | 2018-11-16 10:58 | 2018-11-06 10:29
CHG0030900 | DigiPlex Stockholm 1 AB | Updated BMS RAMS | Normal | Canceled | 2018-11-12 07:00 | 2018-11-16 19:00 |  | 2018-11-09 13:16 |  |  |  | Requested | 06.11.2018 10:10:52 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2018-11-05 11:42
CHG0030899 | DigiPlex Stockholm 1 AB | DH7 UPS B1-B3 yearly preventive maintenance | Normal | Closed | 2018-11-07 08:00 | 2018-11-08 17:00 |  | 2018-11-09 13:06 | 2018-11-09 13:06 |  |  | Approved | 06.11.2018 10:10:28 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-07 07:40 | 2018-11-07 16:07 | 2018-11-05 11:47
CHG0030898 | DigiPlex Fet AS | Inntransport og påplassetting av dataromskjølere | Normal | Closed | 2018-11-06 08:00 | 2018-11-09 16:00 |  | 2018-12-13 13:15 | 2018-12-13 13:15 |  |  | Approved | 06.11.2018 10:04:20 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-12-04 13:43 | 2018-12-04 13:43 | 2018-11-05 09:31
CHG0030897 | DigiPlex Fet AS | Montere fundament/rammeverk | Normal | Closed | 2018-11-05 07:00 | 2018-11-09 16:00 |  | 2018-12-13 13:28 | 2018-12-13 13:28 |  |  | Approved | 05.11.2018 09:57:21 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-11-14 13:42 | 2018-11-14 13:42 | 2018-11-03 18:32
CHG0030896 | DigiPlex Fet AS | Kjerneboring for vannforsyning til Munthers | Normal | Closed | 2018-11-02 07:00 | 2018-11-06 17:00 |  | 2019-01-07 07:23 | 2019-01-07 07:23 |  |  | Approved | 05.11.2018 09:59:13 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-11-02 13:12 | 2018-11-06 13:12 | 2018-11-02 15:33
CHG0030895 | DigiPlex Stockholm 1 AB | Metal cladding on DH8 wall | Normal | Closed | 2018-11-05 13:12 | 2018-11-16 13:12 |  | 2019-01-18 11:33 | 2019-01-18 11:33 |  |  | Approved |  | 2018-11-28 07:47 | 2018-12-18 11:25 | 2018-11-02 13:13
CHG0030894 | DigiPlex Stockholm 1 AB | DH7 UPS A1-A3 yearly preventive maintenance | Normal | Closed | 2018-11-05 08:00 | 2018-11-06 17:00 |  | 2019-04-30 10:42 | 2018-11-09 13:05 |  |  | Approved |  | 2018-11-05 08:52 | 2018-11-06 12:13 | 2018-11-02 12:41
CHG0030893 | DigiPlex Stockholm 1 AB | DH7 UPS A1-A3 yearly maintenance | Normal | Canceled |  |  |  | 2018-11-06 12:20 |  |  |  | Not Yet Requested |  |  |  | 2018-11-02 12:36
CHG0030892 | DigiPlex Norway AS | Annual maintenance CCTV | Normal | Closed | 2018-11-12 08:00 | 2018-11-14 16:00 |  | 2018-11-15 09:11 | 2018-11-15 09:11 |  |  | Approved | 06.11.2018 10:41:16 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-12 08:00 | 2018-11-14 15:30 | 2018-11-02 10:34
CHG0030891 | DigiPlex Norway AS | Fiber cabling from CCR-A and B to 00Mod01.5 and -01Mod06.2 (AVS7568) | Normal | Closed | 2018-11-06 10:33 | 2018-11-16 16:00 |  | 2019-02-04 15:46 | 2018-11-21 07:09 |  |  | Approved | 06.11.2018 10:40:00 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-09 07:00 | 2018-11-14 15:30 | 2018-11-02 10:36
CHG0030890 | DigiPlex Fet AS | DFAS. Test and replace batteries in UPS A-side and B-side. | Normal | Closed | 2018-11-05 12:00 | 2018-11-09 12:00 |  | 2019-04-25 09:36 | 2019-04-25 09:36 |  |  | Approved | 02.11.2018 14:40:28 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 02.11.2018 14:25:29 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-05 09:11 | 2018-11-09 09:11 | 2018-11-02 10:44
CHG0030889 | DigiPlex Fet AS | Loose circuit breaker connection - DFAS +A1=462.1206 A-Side | Emergency | Closed | 2018-11-02 13:00 | 2018-11-02 13:10 |  | 2018-11-12 07:25 | 2018-11-12 07:25 |  |  | Approved | 02.11.2018 13:18:17 - atorp (Approval history) Group approval for CAB Approval NO approved by user Atle Torp (CAB approval). 02.11.2018 10:19:10 - dobraekken (Approval history) Group approval for eCAB Approval approved by user Dag Oscar Brækken (eCAB approval). | 2018-11-02 13:00 | 2018-11-02 13:22 | 2018-11-02 09:32
CHG0030886 | DigiPlex Norway AS | 02MOD04, new floor. | Normal | Closed | 2018-11-01 10:31 | 2018-12-31 10:31 |  | 2019-02-27 08:12 | 2019-02-27 08:12 |  |  | Approved | 06.11.2018 10:38:56 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-01 10:09 | 2019-01-18 10:09 | 2018-11-01 10:34
CHG0030885 | DigiPlex Norway AS | Test of Smart Grid remote start signal | Normal | Closed | 2018-11-05 12:00 | 2018-11-05 14:00 |  | 2018-11-05 15:18 | 2018-11-05 15:18 | Jonny Ulfsryggen |  | Approved | 05.11.2018 09:46:15 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-05 12:15 | 2018-11-05 15:15 | 2018-11-01 10:31
CHG0030884 | DigiPlex Rosenholm AS | Remote test of Smart Grid | Normal | Closed | 2018-11-05 09:00 | 2018-11-05 10:00 |  | 2018-11-12 07:26 | 2018-11-12 07:26 |  |  | Approved | 05.11.2018 09:44:52 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-11-05 08:54 | 2018-11-05 09:30 | 2018-11-01 10:21
CHG0030883 | DigiPlex Fet AS | Flytting av 24v power for aspirasjonssentraler | Normal | Closed | 2018-10-29 07:00 | 2018-11-01 17:00 |  | 2018-12-13 13:17 | 2018-12-13 13:17 |  |  | Approved | 01.11.2018 14:05:18 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 01.11.2018 12:56:52 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-01 12:01 | 2018-11-01 12:01 | 2018-11-01 09:15
CHG0030882 | DigiPlex Copenhagen 1 ApS | Oil change on Chiller 1-3 | Normal | Closed | 2018-11-01 10:58 | 2018-12-16 10:58 |  | 2019-03-14 08:38 | 2019-03-14 08:38 |  |  | Approved | 15.11.2018 09:18:00 - aolsen (Approval history) User approval for Tommy Solberg deleted since it no longer matches approval rule Approve if CAB isn't required NO. 15.11.2018 09:18:00 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 31.10.2018 13:25:08 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 31.10.2018 12:25:16 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-05 13:48 | 2019-01-08 13:49 | 2018-10-31 10:58
CHG0030881 | DigiPlex Fet AS | DFAS. Hulltaking for kjølerør | Normal | Closed | 2018-11-01 07:00 | 2018-11-02 17:00 |  | 2018-12-13 13:14 | 2018-12-13 13:14 |  |  | Approved | 02.11.2018 10:44:37 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 31.10.2018 12:28:48 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-12 13:38 | 2018-11-12 13:38 | 2018-10-31 10:08
CHG0030880 | DigiPlex Norway AS | Change KAC to module | Emergency | Closed | 2018-10-30 14:24 | 2018-10-30 14:24 |  | 2018-11-15 09:10 | 2018-11-15 09:10 |  |  | Approved | 30.10.2018 18:13:49 - pviken (Approval history) Group approval for CAB Approval NO approved by user Pål Rune Viken (CAB approval). 30.10.2018 15:02:51 - fekay (Approval history) Group approval for eCAB Approval approved by user Frode Elden Kay (eCAB approval). | 2018-10-30 13:45 | 2018-10-30 14:00 | 2018-10-30 14:24
CHG0030878 | DigiPlex Norway AS | FW Upgrade + new battery strings - UPS F | Normal | Closed | 2018-11-05 12:21 | 2018-12-31 12:21 |  | 2019-01-23 08:59 | 2019-01-23 08:59 |  |  | Approved | 01.11.2018 11:46:29 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 30.10.2018 14:30:18 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-05 09:22 | 2018-12-20 09:22 | 2018-10-30 12:20
CHG0030877 | DigiPlex Norway AS | Move Critical load C from C-string to F-string | Normal | Closed | 2018-10-31 11:50 | 2018-11-02 11:50 |  | 2018-11-15 09:09 | 2018-11-15 09:09 |  |  | Approved | 31.10.2018 09:24:27 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 30.10.2018 14:29:36 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-10-31 12:39 | 2018-11-06 12:39 | 2018-10-30 11:34
CHG0030876 | DigiPlex Stockholm 1 AB | Dette er bare en test | Normal | Canceled |  |  |  | 2018-10-30 10:09 |  |  |  | Requested | 30.10.2018 10:08:13 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2018-10-30 10:08
CHG0030875 | DigiPlex Stockholm 1 AB | DH7.1 Additional sensors | Normal | Closed | 2018-10-31 09:44 | 2019-01-14 09:44 |  | 2019-01-24 14:23 | 2019-01-24 14:23 |  |  | Approved | 30.10.2018 09:45:06 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-10-31 13:21 | 2019-01-09 13:33 | 2018-10-30 09:40
CHG0030874 | DigiPlex Stockholm 1 AB | DH7.1 Additional sensors | Normal | Canceled | 2018-10-31 21:03 | 2018-11-02 21:03 |  | 2018-10-30 10:11 |  |  |  | Approved | 30.10.2018 09:19:51 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2018-10-29 21:28
CHG0030873 | DigiPlex Stockholm 1 AB | DH7.1 Additional sensors | Normal | Canceled | 2018-10-31 21:03 | 2018-11-02 21:03 |  | 2018-10-30 10:10 |  |  |  | Not Yet Requested |  |  |  | 2018-10-29 21:22
CHG0030873 | DigiPlex Stockholm 1 AB | DH7.1 Additional sensors | Normal | Canceled | 2018-10-31 21:03 | 2018-11-02 21:03 |  | 2018-10-30 10:10 |  |  |  | Not Yet Requested |  |  |  | 2018-10-29 21:21
CHG0030871 | DigiPlex Rosenholm AS | Lekkasjesøking av kjølekretsene | Normal | Closed | 2018-11-05 12:45 | 2018-11-09 12:45 |  | 2018-12-06 09:14 | 2018-12-06 09:14 |  |  | Approved | 30.10.2018 08:11:37 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 30.10.2018 07:39:38 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). |  |  | 2018-10-29 12:46
CHG0030870 | DigiPlex Fet AS | DFAS. Montering av kjølerør | Normal | Closed | 2018-11-01 07:00 | 2018-11-02 17:00 |  | 2019-11-11 11:44 | 2019-11-11 11:44 | Kristin Ohnstad |  | Approved | 29.10.2018 11:40:54 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2019-11-01 08:54 | 2019-11-02 08:55 | 2018-10-26 17:58
CHG0030869 | DigiPlex Rosenholm AS | Fiber cabling from CCR-B to Mod02 for CGI AVS1024 | Normal | Closed | 2018-10-29 08:00 | 2018-11-02 16:00 |  | 2018-11-12 07:31 | 2018-11-12 07:31 |  |  | Approved | 29.10.2018 09:13:30 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-31 07:00 | 2018-10-31 12:00 | 2018-10-26 15:48
CHG0030868 | DigiPlex Norway AS | PODPLT01 Changeover pumps, installation new board. | Normal | Closed | 2018-10-29 09:53 | 2018-11-09 09:53 |  | 2018-12-05 16:50 | 2018-12-05 16:50 |  |  | Approved | 29.10.2018 09:12:32 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-28 13:22 | 2018-11-02 13:22 | 2018-10-26 10:05
CHG0030866 | DigiPlex Norway AS | DNAS site inspection. | Normal | Canceled | 2018-10-26 07:30 | 2019-06-28 10:30 |  | 2019-06-20 09:11 | 2019-06-20 09:11 | Pål Rune Viken |  | Approved | 29.10.2018 09:09:53 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-10-25 10:34
CHG0030865 | DigiPlex Norway AS | Change power block in UPS A | Normal | Closed | 2018-10-25 09:00 | 2018-10-26 16:00 |  | 2018-10-28 17:17 | 2018-10-28 17:17 |  |  | Approved | 25.10.2018 11:35:28 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 25.10.2018 10:48:27 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-10-25 13:08 | 2018-10-26 13:08 | 2018-10-23 12:27
CHG0030863 | DigiPlex Stockholm 1 AB | Autonomous Control Description | Normal | Canceled | 2018-11-12 13:20 | 2018-11-16 13:20 |  | 2018-10-23 16:40 |  |  |  | Approved |  |  |  | 2018-10-22 13:39
CHG0030862 | DigiPlex Stockholm 1 AB | Autonomous Control Description | Normal | Canceled | 2018-11-12 12:59 | 2018-11-16 12:59 |  | 2018-10-23 16:38 |  |  |  | Rejected |  |  |  | 2018-10-22 13:07
CHG0030861 | DigiPlex Rosenholm AS | Service på CCUer | Normal | Closed | 2018-10-29 12:19 | 2018-11-23 12:19 |  | 2018-12-06 09:14 | 2018-12-06 09:14 |  | 2018-10-25 | Approved | 24.10.2018 08:18:45 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 23.10.2018 08:53:26 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-10-30 14:20 |  | 2018-10-22 12:20
CHG0030860 | DigiPlex Fet AS | DFAS. Flytting av et forsyningsskap | Normal | Closed | 2018-10-23 10:34 | 2018-11-02 10:34 |  | 2018-11-12 07:32 | 2018-11-12 07:32 |  |  | Approved | 29.10.2018 11:40:04 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 23.10.2018 09:07:48 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-01 12:04 | 2018-11-01 12:04 | 2018-10-22 10:39
CHG0030859 | DigiPlex Fet AS | DFAS. Montering av føringsveier, kabler og strømskinner | Normal | Closed | 2018-10-23 10:07 | 2018-11-09 10:07 |  | 2019-01-07 07:21 | 2019-01-07 07:21 |  |  | Approved | 29.10.2018 11:41:52 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 23.10.2018 09:06:41 - kohnstad (Approval history) Group approval for Change Management rejected by user Kristin Ohnstad (Change Management approvals norway). | 2018-10-23 13:10 | 2019-01-04 13:10 | 2018-10-22 10:24
CHG0030858 | DigiPlex Norway AS | Install CAC in 02MOD08 and -01MOD09 | Normal | Closed | 2018-10-29 10:15 | 2018-11-09 10:15 |  | 2019-01-11 12:35 | 2019-01-11 12:35 |  | 2019-01-11 | Approved | 24.10.2018 08:17:42 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-31 10:40 | 2018-11-23 11:57 | 2018-10-22 10:13
CHG0030857 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Normal | Closed | 2018-10-22 08:07 | 2018-10-26 14:07 |  | 2018-11-14 07:26 | 2018-11-14 07:26 |  |  | Approved | 19.10.2018 15:32:26 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 19.10.2018 15:01:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-10-22 13:44 | 2018-10-26 13:44 | 2018-10-19 14:08
CHG0030856 | DigiPlex Fet AS | DFAS. Inntransport av Munters-aggregater | Normal | Closed | 2018-10-29 07:00 | 2018-11-01 17:00 |  | 2018-12-13 13:16 | 2018-12-13 13:16 |  |  | Approved | 22.10.2018 06:06:58 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-10-29 14:34 | 2018-12-02 14:34 | 2018-10-19 12:44
CHG0030855 | DigiPlex Stockholm 1 AB | Completion of Snags – Anord HV PODS | Normal | Closed | 2018-11-17 12:38 | 2018-11-17 12:38 |  | 2018-12-06 14:48 | 2018-12-06 14:48 |  | 2018-12-06 | Approved | 23.10.2018 09:43:32 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-17 09:49 | 2018-11-17 09:49 | 2018-10-19 12:38
CHG0030854 | DigiPlex Norway AS | Access ifbm modulvask | Normal | Closed | 2018-10-26 08:35 | 2018-10-26 14:35 |  | 2018-11-12 07:31 | 2018-11-12 07:31 |  |  | Approved | 24.10.2018 08:14:23 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 22.10.2018 16:15:55 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-11-02 09:48 | 2018-11-02 11:48 | 2018-10-19 10:34
CHG0030853 | DigiPlex Norway AS | UPS CY MMU 2 fault | Emergency | Closed | 2018-10-18 10:32 | 2018-10-18 16:00 |  | 2018-10-28 17:12 | 2018-10-28 17:12 |  | 2018-10-25 | Approved | 18.10.2018 12:33:49 - pviken (Approval history) Group approval for CAB Approval approved by user Pål Rune Viken (CAB approval). 18.10.2018 10:39:01 - fekay (Approval history) Group approval for eCAB Approval approved by user Frode Elden Kay (eCAB approval). | 2018-10-18 12:00 | 2018-10-18 14:00 | 2018-10-18 10:33
CHG0030852 | DigiPlex Norway AS | UPS CY MMU2 fault | Normal | Canceled | 2018-10-18 08:09 | 2018-10-19 16:00 |  | 2018-10-19 12:47 | 2018-10-19 12:47 | Frode Elden Kay |  | Rejected | 19.10.2018 12:46:18 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-10-18 08:10
CHG0030851 | DigiPlex Stockholm 1 AB | Remote access to the HBT servers. | Normal | Closed | 2018-12-10 14:15 | 2018-12-11 14:15 |  | 2019-01-18 11:36 | 2019-01-18 11:36 |  |  | Approved | 06.12.2018 14:46:45 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-12-11 15:20 | 2018-12-14 15:20 | 2018-10-16 18:29
CHG0030850 | DigiPlex Stockholm 1 AB | Tidy up PMS installation DH6 | Normal | Closed | 2018-10-16 14:42 | 2018-10-18 14:42 |  | 2018-11-12 07:27 | 2018-11-12 07:27 |  |  | Approved | 16.10.2018 15:51:26 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). 16.10.2018 09:31:49 - kohnstad (Approval history) Group approval for Change Management approved by user Kristin Ohnstad (Change Management approvals norway). | 2018-10-16 15:41 | 2018-10-17 15:41 | 2018-10-15 14:45
CHG0030848 | DigiPlex Norway AS | Level3 BMS Commissioning. 2nd visit. | Normal | Closed | 2018-10-15 12:26 | 2018-11-30 12:26 |  | 2019-01-07 07:27 | 2019-01-07 07:27 |  |  | Approved | 15.10.2018 10:41:55 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-10-15 20:48 | 2018-11-30 20:48 | 2018-10-12 12:29
CHG0030847 | DigiPlex Rosenholm AS | Adding new seal to MOD08 roof | Normal | Closed | 2018-10-22 10:51 | 2018-10-26 10:51 |  | 2018-11-01 09:40 | 2018-11-01 09:40 |  |  | Approved | 17.10.2018 11:55:12 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). |  |  | 2018-10-12 10:55
CHG0030843 | DigiPlex Stockholm 1 AB | Cabling new BMS sensors in DH7.1 | Normal | Closed | 2018-10-11 21:45 | 2018-10-12 21:45 |  | 2018-11-12 07:27 | 2018-11-12 07:27 |  |  | Approved |  | 2018-10-11 22:57 | 2018-10-19 22:57 | 2018-10-10 21:46
CHG0030842 | DigiPlex Fet AS | DFAS. Inntransport av Munters-aggregater | Normal | Canceled | 2018-10-29 07:40 | 2018-11-01 16:41 |  | 2018-10-22 07:02 |  |  |  | Requested | 22.10.2018 06:07:36 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2018-10-10 10:00
CHG0030841 | DigiPlex Rosenholm AS | Rep av lekkasje i MOD10 IK101 | Normal | Closed | 2018-10-16 12:32 | 2018-10-16 12:32 |  | 2018-11-15 09:13 | 2018-11-15 09:13 |  |  | Approved | 09.10.2018 13:05:01 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-16 12:50 | 2018-10-16 12:50 | 2018-10-09 12:32
CHG0030840 | DigiPlex Stockholm 1 AB | Install smoke detection DH7.1.7 Munters and connect Fire damper panel cameron storage | Normal | Closed | 2018-10-10 15:54 | 2018-10-12 15:54 |  | 2018-11-09 13:08 | 2018-11-09 13:08 |  |  | Approved |  | 2018-10-10 15:54 | 2018-10-11 14:36 | 2018-10-08 15:55
CHG0030839 | DigiPlex Norway AS | Bytte av batterier i E-pod | Normal | Closed | 2018-10-08 11:00 | 2018-12-21 16:00 |  | 2019-04-11 13:03 | 2019-04-11 13:03 |  |  | Approved | 08.10.2018 09:20:03 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-10-08 08:19 | 2018-12-21 08:20 | 2018-10-08 09:13
CHG0030838 | DigiPlex Norway AS | Fuel leak | Normal | Closed | 2018-10-17 10:53 | 2018-10-18 10:53 |  | 2018-10-25 08:18 | 2018-10-25 08:18 |  |  | Approved | 17.10.2018 11:50:32 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-17 14:39 | 2018-10-19 14:39 | 2018-10-08 08:45
CHG0030837 | DigiPlex Stockholm 1 AB | Fire stopping | Normal | Closed | 2018-10-08 07:00 | 2018-10-24 17:00 |  | 2018-12-06 16:08 | 2018-12-06 16:08 |  |  | Approved |  | 2018-11-05 09:52 | 2018-11-06 09:52 | 2018-10-05 15:44
CHG0030836 | DigiPlex Stockholm 1 AB | BMS concert control integration | Normal | Closed | 2018-11-12 07:00 | 2018-11-16 17:00 |  | 2018-11-22 15:07 | 2018-11-22 15:07 |  |  | Approved |  | 2018-11-12 09:53 | 2018-11-16 09:53 | 2018-10-05 13:29
CHG0030835 | DigiPlex Norway AS | DNAS. Kontroll av ojetrykk | Normal | Closed | 2018-10-08 08:00 | 2018-10-09 16:00 |  | 2018-11-22 11:14 | 2018-11-22 11:14 | Geir Almquist |  | Approved | 05.10.2018 12:31:37 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-10-08 08:00 | 2018-10-09 16:00 | 2018-10-05 12:22
CHG0030834 | DigiPlex Fet AS | DFAS. Nye kabel og skinnertraseer | Normal | Closed | 2018-11-26 08:05 | 2018-12-14 08:05 |  | 2019-01-07 07:21 | 2019-01-07 07:21 |  |  | Approved | 09.10.2018 12:21:55 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-11-26 13:05 | 2019-01-14 13:05 | 2018-10-04 13:50
CHG0030833 | DigiPlex Fet AS | DFAS. Nye transformatorer | Normal | Closed | 2018-10-22 08:04 | 2018-11-25 08:04 |  | 2018-12-05 16:51 | 2018-12-05 16:51 |  |  | Approved | 09.10.2018 12:20:51 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-10-29 14:24 | 2018-11-02 14:23 | 2018-10-04 13:38
CHG0030831 | DigiPlex Norway AS | Switch DNAS L3 connection to site core netwrok | Normal | Closed | 2018-10-15 09:00 | 2018-10-15 15:00 |  | 2018-11-02 07:19 | 2018-11-02 07:19 |  |  | Approved | 09.10.2018 13:03:47 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-26 07:18 | 2018-10-26 13:01 | 2018-10-04 08:43
CHG0030830 | DigiPlex Norway AS | Oppussing 00PLT01 | Normal | Closed | 2018-10-03 11:54 | 2018-10-19 10:54 |  | 2019-01-25 10:52 | 2019-01-25 10:52 |  |  | Approved | 08.10.2018 09:05:56 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-10-03 09:07 | 2018-10-29 09:08 | 2018-10-03 10:57
CHG0030829 | DigiPlex All | On prem AD - Azure AD separation | Normal | Closed | 2018-10-08 09:00 | 2018-10-22 13:00 |  | 2018-11-02 07:18 | 2018-11-02 07:18 |  |  | Approved | 09.10.2018 13:03:14 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-08 09:00 | 2018-10-24 15:00 | 2018-10-03 08:32
CHG0030828 | DigiPlex Norway AS | FW Upgrade + new battery strings - UPS E | Normal | Closed | 2018-10-03 08:01 | 2018-12-31 15:15 |  | 2019-01-23 09:02 | 2019-01-23 09:02 |  |  | Approved | 02.10.2018 15:47:12 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-10-03 11:43 | 2018-12-14 11:43 | 2018-10-02 15:08
CHG0030827 | DigiPlex Stockholm 1 AB | Remove all swarf on existing steelwork to compound fence | Normal | Closed | 2018-11-07 14:26 | 2018-11-09 14:26 |  | 2018-12-06 16:09 | 2018-12-06 16:09 |  |  | Approved |  | 2018-11-09 09:50 | 2018-11-09 09:50 | 2018-10-02 14:28
CHG0030825 | DigiPlex Norway AS | Filter replacements AHUs, DNAS | Normal | Closed | 2018-10-08 08:00 | 2018-10-08 16:45 |  | 2018-10-15 17:00 | 2018-10-15 17:00 |  |  | Approved | 08.10.2018 09:44:32 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-10-08 13:17 | 2018-10-08 13:17 | 2018-10-02 10:45
CHG0030823 | DigiPlex Stockholm 1 AB | Installing the new window | Normal | Closed | 2018-10-03 13:02 | 2018-10-03 13:02 |  | 2018-10-04 09:49 | 2018-10-04 09:49 |  |  | Approved |  | 2018-10-03 08:15 | 2018-10-03 08:15 | 2018-09-27 13:12
CHG0030822 | DigiPlex Fet AS | DFAS. Server & storage firmware / system software upgrade | Normal | Closed | 2018-10-29 09:00 | 2018-11-02 16:00 |  | 2019-01-25 10:53 | 2019-01-25 10:53 |  |  | Approved | 05.10.2018 12:36:46 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-10-29 09:06 | 2018-11-07 09:06 | 2018-09-27 09:30
CHG0030821 | DigiPlex Rosenholm AS | DRAS 12M service på Eltek brannsentraler | Normal | Closed | 2018-10-03 14:14 | 2018-10-04 14:14 |  | 2018-10-10 17:03 | 2018-10-10 17:03 |  |  | Approved | 27.09.2018 14:55:38 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-09-26 14:14
CHG0030820 | DigiPlex Norway AS | UPS B fault | Normal | Closed | 2018-09-26 09:32 | 2018-09-28 16:00 |  | 2018-10-25 08:15 | 2018-10-25 08:15 |  |  | Approved | 27.09.2018 15:06:19 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-26 09:48 | 2018-09-28 09:48 | 2018-09-25 10:02
CHG0030818 | DigiPlex Stockholm 1 AB | DH7.1.9 Istallation cable ladders and fire proofing | Normal | Closed | 2018-09-27 15:00 | 2018-10-05 15:00 |  | 2018-10-25 14:35 | 2018-10-25 14:35 |  |  | Approved |  | 2018-09-27 13:34 | 2018-10-15 08:40 | 2018-09-24 15:02
CHG0030814 | DigiPlex Norway AS | Fiber cabling from CCR-A, B and C to Level3 for Digiplex | Normal | Closed | 2018-09-30 07:00 | 2018-10-19 13:05 |  | 2018-11-12 07:29 | 2018-11-12 07:29 |  |  | Approved | 27.09.2018 14:02:11 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-01 07:04 | 2018-11-05 15:00 | 2018-09-24 13:09
CHG0030813 | DigiPlex Fet AS | DFAS genset service | Normal | Closed | 2018-10-15 08:31 | 2018-10-26 08:31 |  | 2018-11-14 07:22 | 2018-11-14 07:22 |  |  | Approved | 24.09.2018 10:51:52 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-10-15 09:10 | 2018-10-26 09:10 | 2018-09-24 08:35
CHG0030812 | DigiPlex Norway AS | Annual maintenance on generator EF | Normal | Closed | 2018-09-24 07:26 | 2018-10-05 16:00 |  | 2018-10-25 08:11 | 2018-10-25 08:11 |  |  | Approved | 24.09.2018 08:17:00 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-24 09:43 | 2018-10-05 09:43 | 2018-09-24 07:27
CHG0030811 | DigiPlex Norway AS | CCR-A: New rack feed. | Normal | Closed | 2018-09-24 14:16 | 2018-10-05 14:16 |  | 2018-10-16 08:28 | 2018-10-16 08:28 |  |  | Approved | 24.09.2018 13:01:51 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-25 08:30 | 2018-09-25 13:00 | 2018-09-20 14:19
CHG0030809 | DigiPlex Norway AS | Move Critical load C from F string back to C string | Normal | Closed | 2018-09-19 14:00 | 2018-09-19 15:00 |  | 2018-09-19 17:01 | 2018-09-19 17:01 |  |  | Approved | 19.09.2018 13:54:17 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-19 14:00 | 2018-09-19 15:19 | 2018-09-19 13:23
CHG0030808 | DigiPlex Rosenholm AS | Feilsøking på Deep Sea panelet | Normal | Closed | 2018-09-24 08:14 | 2018-09-28 08:14 |  | 2018-09-27 08:40 | 2018-09-27 08:40 |  |  | Approved | 19.09.2018 13:40:50 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-09-19 08:15
CHG0030807 | DigiPlex Norway AS | 03MOD01 new coolingcircuit. | Normal | Closed | 2018-09-18 07:08 | 2018-09-28 15:08 |  | 2018-11-01 09:11 | 2018-11-01 09:11 |  | 2018-11-01 | Approved | 18.09.2018 13:28:31 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-09-18 08:20 | 2018-10-05 08:21 | 2018-09-17 15:11
CHG0030806 | DigiPlex Norway AS | Level 3 BMS | Normal | Closed | 2018-09-24 07:22 | 2018-10-26 14:22 |  | 2019-01-07 07:28 | 2019-01-07 07:28 |  |  | Approved | 18.09.2018 10:30:10 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-24 20:49 | 2018-10-26 20:49 | 2018-09-17 14:25
CHG0030805 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Normal | Closed | 2018-09-18 08:00 | 2018-09-28 14:12 |  | 2018-10-10 16:51 | 2018-10-10 16:51 |  |  | Approved | 17.09.2018 14:16:03 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-09-18 13:16 | 2018-09-28 13:16 | 2018-09-17 14:12
CHG0030803 | DigiPlex Rosenholm AS | Annual inspection of Electric boards | Normal | Closed | 2018-09-19 08:00 | 2018-09-21 16:00 |  | 2018-10-03 08:42 | 2018-10-03 08:42 |  |  | Approved | 17.09.2018 12:45:23 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-19 08:00 | 2018-09-21 16:00 | 2018-09-17 11:46
CHG0030802 | DigiPlex Norway AS | Reterminate fiberpanel on existing cabel in 02Mod08 | Normal | Closed | 2018-09-19 08:00 | 2018-09-28 16:00 |  | 2018-09-27 09:06 | 2018-09-27 09:06 |  |  | Approved | 17.09.2018 12:43:14 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-21 08:00 | 2018-09-21 12:00 | 2018-09-17 11:03
CHG0030801 | DigiPlex Stockholm 1 AB | DH1 - Reinstate gas suppression system | Normal | Closed | 2018-09-14 23:45 | 2018-09-15 00:15 |  | 2018-09-19 20:11 | 2018-09-19 20:11 |  |  | Approved |  | 2018-09-14 23:45 | 2018-09-15 00:15 | 2018-09-15 00:34
CHG0030800 | DigiPlex Fet AS | test | Normal | Canceled | 2018-09-21 14:18 | 2018-09-25 14:18 |  | 2018-09-20 08:09 |  |  |  | Requested |  |  |  | 2018-09-14 14:24
CHG0030799 | DigiPlex Norway AS | Pump bearing fault | Normal | Closed | 2018-09-13 14:00 | 2018-09-21 16:00 |  | 2018-10-04 14:58 | 2018-10-04 14:58 |  |  | Approved | 03.10.2018 09:20:45 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-20 09:00 | 2018-09-20 16:00 | 2018-09-13 14:00
CHG0030797 | DigiPlex Rosenholm AS | ISAT - Test to confirm operation of equipment located in R02MOD01 | Normal | Closed | 2018-09-13 13:04 | 2018-10-15 16:00 |  | 2018-11-12 07:30 | 2018-11-12 07:30 |  |  | Approved | 24.09.2018 14:27:06 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-10-17 11:47 | 2018-10-17 11:47 | 2018-09-13 13:11
CHG0030796 | DigiPlex Norway AS | Upgrading BMS | Normal | Closed | 2018-09-17 11:42 | 2018-10-01 11:42 |  | 2019-02-15 19:03 | 2019-02-15 19:03 |  |  | Approved | 17.09.2018 08:58:51 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-17 10:00 | 2018-09-28 16:01 | 2018-09-13 11:41
CHG0030795 | DigiPlex Stockholm 1 AB | Fire sealing grooves between precast concrete beams in Fallow Space | Normal | Closed | 2018-09-24 15:40 | 2018-10-05 15:40 |  | 2018-12-06 16:11 | 2018-12-06 16:11 |  |  | Approved |  | 2018-09-26 09:46 | 2018-10-03 09:46 | 2018-09-12 15:42
CHG0030794 | DigiPlex Stockholm 1 AB | Concrete survey in Fallow Space | Normal | Closed | 2018-09-17 15:34 | 2018-09-21 15:34 |  | 2018-10-02 08:50 | 2018-10-02 08:50 |  |  | Approved |  | 2018-09-17 16:44 | 2018-09-21 16:44 | 2018-09-12 15:40
CHG0030793 | DigiPlex Norway AS | Fiber cabling from CCR-B to 03Mod01.3 for euNetworks | Normal | Closed | 2018-09-18 07:30 | 2018-09-28 16:00 |  | 2018-09-27 09:06 | 2018-09-27 09:06 |  |  | Approved | 12.09.2018 11:53:40 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-19 07:00 | 2018-09-21 12:00 | 2018-09-12 08:00
CHG0030792 | DigiPlex All | Cancel Subscription to ePermit | Normal | Closed | 2018-12-01 17:22 | 2018-12-01 17:22 |  | 2019-01-04 09:00 | 2019-01-04 09:00 |  |  | Approved | 20.09.2018 12:51:51 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-12-01 09:00 | 2018-12-01 09:00 | 2018-09-11 16:15
CHG0030791 | DigiPlex Stockholm 1 AB | BMS Commissioning | Normal | Closed | 2018-09-19 09:30 | 2018-09-21 17:00 |  | 2018-09-28 10:43 | 2018-09-28 10:43 |  |  | Approved |  | 2018-09-19 16:52 | 2018-09-21 16:52 | 2018-09-11 16:01
CHG0030790 | DigiPlex Fet AS | DFAS. Faulkty switches: Defect fan A1 SW-029 and replace faulty A1 switch-025 | Emergency | Canceled | 2018-09-14 11:00 | 2018-09-14 13:00 |  | 2018-10-15 13:59 |  |  | 2018-10-11 | Requested | 11.09.2018 14:06:19 - dobraekken (Approval history) Group approval for eCAB Approval approved by user Dag Oscar Brækken (eCAB approval). | 2018-09-14 10:00 | 2018-09-14 06:36 | 2018-09-11 13:28
CHG0030789 | DigiPlex Norway AS | Server decommissioning DNAS 00PLT01 | Normal | Closed | 2018-09-14 09:00 | 2018-09-21 13:00 |  | 2018-09-27 08:12 | 2018-09-27 08:12 | Karl Audun Lad |  | Approved | 12.09.2018 11:54:28 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-09-11 13:18
CHG0030788 | DigiPlex Fet AS | DFAS. A2.3 new openings in the outer walls. | Normal | Closed | 2018-09-20 11:12 | 2018-10-15 11:12 |  | 2019-01-04 12:53 | 2019-01-04 12:53 |  |  | Approved | 11.09.2018 14:03:57 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-09-11 11:13 | 2018-12-16 12:45 | 2018-09-11 10:04
CHG0030785 | DigiPlex Norway AS | Level 3 Elektro/small power. | Normal | Closed | 2018-09-07 07:13 | 2018-11-30 15:13 |  | 2019-01-07 07:28 | 2019-01-07 07:28 |  |  | Approved | 10.09.2018 11:44:02 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-07 20:54 | 2019-01-04 20:54 | 2018-09-06 15:15
CHG0030784 | DigiPlex Stockholm 1 AB | Commssion smoke detection Fallow space | Normal | Closed | 2018-09-06 09:49 | 2018-09-06 09:49 |  | 2018-10-02 08:51 | 2018-10-02 08:51 |  |  | Approved |  | 2018-09-06 16:43 | 2018-09-06 16:43 | 2018-09-05 09:50
CHG0030783 | DigiPlex Rosenholm AS | DRAS, Repair of existing light. | Normal | Closed | 2018-09-05 07:35 | 2018-09-28 16:35 |  | 2018-10-11 15:34 | 2018-10-11 15:34 |  | 2018-10-11 | Approved | 05.09.2018 08:21:56 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-09-19 08:09 | 2018-09-19 08:09 | 2018-09-04 16:36
CHG0030782 | DigiPlex Norway AS | 00MOD05, New fireproof cable pipe for new cables. | Normal | Closed | 2018-09-05 07:59 | 2018-09-21 15:59 |  | 2018-10-11 07:55 | 2018-10-11 07:52 |  |  | Approved | 05.09.2018 08:55:52 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-10 10:37 | 2018-10-04 10:38 | 2018-09-04 16:02
CHG0030779 | DigiPlex Norway AS | 03MOD01.3, new cable tray. | Normal | Closed | 2018-09-05 07:01 | 2018-10-05 16:54 |  | 2018-11-14 07:23 | 2018-11-14 07:23 |  |  | Approved | 05.09.2018 08:58:54 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-05 14:18 | 2018-11-09 14:18 | 2018-09-04 08:55
CHG0030778 | DigiPlex Stockholm 1 AB | Dismounting scafolding platform DH7 | Normal | Closed | 2018-09-07 17:03 | 2018-09-10 17:09 |  | 2018-10-04 09:53 | 2018-10-04 09:53 |  |  | Approved |  | 2018-09-07 14:23 | 2018-09-11 14:24 | 2018-09-03 17:10
CHG0030776 | DigiPlex Norway AS | Annual check of electrical panels | Normal | Closed | 2018-09-10 09:40 | 2018-09-14 10:02 |  | 2018-10-03 08:41 | 2018-10-03 08:41 |  | 2018-09-06 | Approved | 07.09.2018 14:20:40 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-09-10 08:00 | 2018-09-14 16:00 | 2018-09-03 12:03
CHG0030774 | DigiPlex Norway AS | Move leak detection unit. | Normal | Canceled |  |  |  | 2018-10-03 09:25 | 2018-10-03 09:25 | Frode Elden Kay |  | Requested |  |  |  | 2018-08-31 13:57
CHG0030771 | DigiPlex Rosenholm AS | Sjekk av doseringsanlegg/vannverdier og bytte av filtre. | Normal | Closed | 2018-09-05 11:32 | 2018-09-05 11:33 |  | 2018-09-27 08:39 | 2018-09-27 08:39 |  |  | Approved | 31.08.2018 12:01:53 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-08-31 11:33
CHG0030769 | DigiPlex Norway AS | Craning VVS pipes for Level 3. | Normal | Closed | 2018-08-30 07:01 | 2018-09-14 15:42 |  | 2018-09-20 09:09 | 2018-09-20 09:09 |  |  | Approved | 29.08.2018 15:47:37 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-08-30 08:01 | 2018-08-31 15:56 | 2018-08-29 15:45
CHG0030768 | DigiPlex Stockholm 1 AB | Software Modifications - BMS | Normal | Canceled | 2018-09-17 15:31 | 2018-09-21 15:31 |  | 2018-09-14 08:36 |  |  |  | Requested |  |  |  | 2018-08-29 15:36
CHG0030767 | DigiPlex Norway AS | Core drilling Level 3 | Normal | Closed | 2018-08-28 07:47 | 2018-10-12 10:47 |  | 2018-11-01 09:13 | 2018-11-01 09:13 |  | 2018-11-01 | Approved | 27.08.2018 15:19:50 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-08-28 08:27 | 2018-10-12 08:27 | 2018-08-27 10:49
CHG0030766 | DigiPlex Norway AS | Replace door leading into 00COR02. | Normal | Closed | 2018-08-27 12:44 | 2018-09-07 10:44 |  | 2018-12-05 15:28 | 2018-12-05 15:28 |  |  | Approved | 28.08.2018 09:07:40 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-08-27 10:47
CHG0030765 | DigiPlex Norway AS | Access ifbm modulvask | Normal | Closed | 2018-08-28 10:20 | 2018-08-28 12:21 |  | 2018-09-18 16:40 | 2018-09-18 16:40 |  |  | Approved | 28.08.2018 09:13:41 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-29 09:00 | 2018-08-29 11:00 | 2018-08-24 14:21
CHG0030764 | DigiPlex Norway AS | Move critical C to critical F | Normal | Closed | 2018-08-24 10:17 | 2018-08-24 13:00 |  | 2018-09-06 09:25 | 2018-09-06 09:25 |  |  | Approved | 24.08.2018 10:05:14 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-24 13:19 | 2018-08-24 14:00 | 2018-08-24 10:04
CHG0030763 | DigiPlex Stockholm 1 AB | Fire stopping in DH6 corridors | Normal | Closed | 2018-08-30 13:29 | 2018-08-30 13:29 |  | 2018-10-02 08:51 | 2018-10-02 08:51 |  |  | Approved |  | 2018-08-30 16:40 | 2018-08-30 16:40 | 2018-08-23 13:31
CHG0030762 | DigiPlex Stockholm 1 AB | Fire stopping of openings | Normal | Closed | 2018-08-30 13:24 | 2018-08-30 13:24 |  | 2018-10-02 08:51 | 2018-10-02 08:51 |  |  | Approved |  | 2018-08-30 16:39 | 2018-08-30 16:40 | 2018-08-23 13:27
CHG0030761 | DigiPlex Stockholm 1 AB | To replace the PMS network cabling installed to the tap offs for DH7.2 | Normal | Closed | 2018-09-18 13:12 | 2018-09-21 13:12 |  | 2018-10-02 08:52 | 2018-10-02 08:52 |  |  | Approved |  | 2018-09-18 16:38 | 2018-09-21 16:39 | 2018-08-23 13:18
CHG0030760 | DigiPlex Norway AS | One of the gas bottles in 00PLT02 have dropped below 300b | Normal | Closed | 2018-08-27 09:30 | 2018-08-27 16:00 |  | 2018-09-06 09:25 | 2018-09-06 09:25 |  |  | Approved | 23.08.2018 11:28:25 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-08-27 10:00 | 2018-08-27 10:20 | 2018-08-23 10:17
CHG0030759 | DigiPlex Stockholm 1 AB | PMS system update | Normal | Canceled | 2018-09-18 07:29 | 2018-09-22 07:29 |  | 2018-08-30 14:43 |  |  |  | Requested |  |  |  | 2018-08-23 07:36
CHG0030758 | DigiPlex Rosenholm AS | Opprydding og fjerning av gamle kabler. | Normal | Closed | 2018-08-22 08:43 | 2018-08-31 16:00 |  | 2018-09-14 12:08 | 2018-09-14 12:08 |  |  | Approved | 22.08.2018 08:50:42 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-08-16 10:34 | 2018-08-27 10:33 | 2018-08-22 08:49
CHG0030757 | DigiPlex Norway AS | Fan failure on CCU1. | Normal | Closed | 2018-08-21 08:30 | 2018-08-21 16:00 |  | 2018-08-23 07:58 | 2018-08-23 07:58 |  |  | Approved | 21.08.2018 08:35:09 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-21 09:00 | 2018-08-21 13:45 | 2018-08-21 08:22
CHG0030756 | DigiPlex Norway AS | Annual maintenance on all Active Power UPS's | Normal | Closed | 2018-09-10 08:00 | 2018-09-17 16:00 |  | 2018-10-17 09:32 | 2018-10-17 09:32 |  | 2018-10-17 | Approved | 21.08.2018 07:59:55 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-09-18 09:04 | 2018-09-25 09:04 | 2018-08-17 13:47
CHG0030755 | DigiPlex Norway AS | Temporary move Critical load CSSB1B from B-string to F-string | Normal | Closed | 2018-09-24 08:00 | 2018-09-28 16:00 |  | 2018-10-15 17:00 | 2018-10-15 17:00 |  |  | Approved | 20.09.2018 15:07:11 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-09-24 13:14 | 2018-09-28 13:14 | 2018-08-17 14:00
CHG0030754 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting | Normal | Closed | 2018-08-20 08:03 | 2018-08-31 08:03 |  | 2018-08-30 08:32 | 2018-08-30 08:32 |  |  | Approved | 17.08.2018 11:29:19 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-08-20 09:40 | 2018-08-28 09:40 | 2018-08-17 08:03
CHG0030753 | DigiPlex Rosenholm AS | Feilsøking på PMS, Gate way og nettanalysatorer | Normal | Closed | 2018-08-15 14:39 | 2018-09-16 16:00 |  | 2018-09-28 11:25 | 2018-09-28 11:25 |  |  | Approved | 15.08.2018 14:51:29 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-08-15 11:15 | 2018-10-16 11:15 | 2018-08-15 14:41
CHG0030752 | DigiPlex Rosenholm AS | Modbus kabel fra Nortronik / Eltek sentralen. | Normal | Closed | 2018-08-15 14:34 | 2018-08-24 16:00 |  | 2018-09-14 10:58 | 2018-09-14 10:58 |  |  | Approved | 15.08.2018 14:46:28 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-08-15 10:39 | 2018-08-24 10:39 | 2018-08-15 14:38
CHG0030751 | DigiPlex Norway AS | Annual maintenance on access control | Normal | Closed | 2018-08-20 08:00 | 2018-08-31 16:00 |  | 2018-10-25 08:14 | 2018-10-25 08:14 |  | 2018-10-25 | Approved | 15.08.2018 12:53:52 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-08-20 09:20 | 2018-09-28 09:20 | 2018-08-15 12:35
CHG0030749 | DigiPlex Rosenholm AS | Installing new BMS | Normal | Closed | 2018-08-16 20:03 | 2018-09-21 20:04 |  | 2018-10-15 17:02 | 2018-10-15 17:02 |  | 2018-10-11 | Approved | 14.08.2018 08:20:31 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-08-27 10:35 | 2018-08-30 10:37 | 2018-08-13 20:07
CHG0030748 | DigiPlex Stockholm 1 AB | Commission new fire alarm release buttons | Normal | Closed | 2018-08-16 13:10 | 2018-08-16 13:10 |  | 2018-10-02 08:53 | 2018-10-02 08:53 |  |  | Approved |  | 2018-08-16 16:27 | 2018-08-16 16:27 | 2018-08-13 13:11
CHG0030747 | DigiPlex Stockholm 1 AB | Construction of new access road to our DS2 site | Normal | Closed | 2018-08-20 11:12 | 2018-09-10 11:12 |  | 2018-10-04 14:34 | 2018-10-04 14:34 |  |  | Approved |  | 2018-09-03 13:32 | 2018-09-17 14:21 | 2018-08-13 11:17
CHG0030746 | DigiPlex Norway AS | Genset A Commissioning and start up. | Normal | Closed | 2018-08-13 14:05 | 2018-09-14 14:05 |  | 2018-08-30 08:35 | 2018-08-30 08:35 |  |  | Approved | 14.08.2018 13:26:50 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-13 08:31 | 2018-08-27 08:32 | 2018-08-10 14:07
CHG0030745 | DigiPlex Stockholm 1 AB | DH1 - Reinstate gas suppression system | Normal | Canceled | 2018-08-10 10:51 | 2018-08-10 10:51 |  | 2018-08-31 08:09 |  |  |  | Approved |  |  |  | 2018-08-10 10:51
CHG0030744 | DigiPlex Norway AS | UPS A BMS. | Normal | Closed | 2018-08-12 07:41 | 2018-09-14 15:41 |  | 2018-09-18 16:45 | 2018-09-18 16:45 |  |  | Approved | 14.08.2018 13:35:31 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-13 13:17 | 2018-08-31 13:17 | 2018-08-09 15:43
CHG0030741 | DigiPlex Rosenholm AS | 3M test av batterier | Normal | Closed | 2018-08-27 11:35 | 2018-08-31 11:35 |  | 2018-09-14 10:54 | 2018-09-14 10:54 |  |  | Approved | 07.08.2018 12:01:25 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-28 10:59 | 2018-08-28 10:59 | 2018-08-07 11:35
CHG0030740 | DigiPlex Norway AS | Need to change 3 gas bottles in 00PLT02 | Normal | Closed | 2018-08-08 09:00 | 2018-08-08 16:00 |  | 2018-08-23 07:57 | 2018-08-23 07:57 |  |  | Approved | 07.08.2018 13:41:05 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-08 09:03 | 2018-08-08 16:00 | 2018-08-07 10:45
CHG0030739 | DigiPlex Norway AS | Inspection of Hafslund Power Meters by Infratek | Normal | Closed | 2018-08-07 10:00 | 2018-08-07 16:00 |  | 2018-08-23 07:57 | 2018-08-23 07:57 |  |  | Approved | 07.08.2018 08:30:34 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-08-07 10:00 | 2018-08-07 12:00 | 2018-08-07 08:26
CHG0030738 | DigiPlex Norway AS | Level 3 Remtech works. | Normal | Closed | 2018-08-07 07:01 | 2018-10-05 14:48 |  | 2019-01-07 07:31 | 2019-01-07 07:31 |  |  | Approved | 07.08.2018 10:06:10 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-07 20:51 | 2019-01-04 20:51 | 2018-08-06 14:50
CHG0030735 | DigiPlex Fet AS | DFAS - Relocation of OPS office, office -rig | Normal | Closed | 2018-08-06 14:25 | 2018-08-07 14:25 | Karl Audun Lad | 2018-09-06 14:08 | 2018-09-06 14:08 |  | 2018-08-03 | Approved | 07.08.2018 06:04:32 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-06 14:26 | 2018-08-06 14:26 | 2018-08-03 14:14
CHG0030734 | DigiPlex Rosenholm AS | Major service on generators | Normal | Closed | 2018-08-13 09:58 | 2018-08-24 09:59 |  | 2018-08-23 09:08 | 2018-08-23 09:08 |  |  | Approved | 06.08.2018 14:49:28 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-15 14:05 | 2018-08-22 08:54 | 2018-08-02 09:59
CHG0030733 | DigiPlex Rosenholm AS | Service av frekvensomformere til DC pumper | Normal | Closed | 2018-08-20 14:29 | 2018-08-21 14:29 |  | 2018-08-23 09:07 | 2018-08-23 09:07 |  |  | Approved | 06.08.2018 10:50:12 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-22 08:53 | 2018-08-22 08:53 | 2018-08-01 14:30
CHG0030732 | DigiPlex Fet AS | Disconnection and relocating of the redundancy HV-line | Normal | Closed | 2018-08-06 13:21 | 2018-08-17 13:21 |  | 2018-09-20 09:20 | 2018-09-20 09:20 |  | 2018-09-20 | Approved | 15.08.2018 06:06:08 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-15 10:17 | 2018-08-17 10:16 | 2018-08-01 09:18
CHG0030731 | DigiPlex Fet AS | Removal of BMS, Munters, PMS systems | Normal | Closed | 2018-08-06 13:05 | 2018-08-11 13:05 |  | 2018-09-20 09:19 | 2018-09-20 09:19 |  | 2018-09-20 | Approved | 15.08.2018 06:07:45 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-08 10:15 | 2018-09-10 10:15 | 2018-08-01 09:14
CHG0030730 | DigiPlex Fet AS | Fire detection system | Normal | Closed | 2018-08-06 13:08 | 2018-08-17 13:08 |  | 2018-09-18 16:38 | 2018-09-18 16:38 |  |  | Approved | 15.08.2018 06:05:03 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-12 10:10 | 2018-09-13 10:11 | 2018-08-01 09:11
CHG0030729 | DigiPlex Fet AS | Disconnecting the backbone network | Normal | Closed | 2018-08-06 13:09 | 2018-08-10 13:09 |  | 2018-09-18 16:37 | 2018-09-18 16:37 |  |  | Approved | 15.08.2018 06:07:11 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-15 10:23 | 2018-08-17 10:23 | 2018-08-01 09:07
CHG0030728 | DigiPlex Fet AS | Removal of Emergency light system | Normal | Closed | 2018-08-06 13:10 | 2018-08-10 13:10 |  | 2018-09-18 16:37 | 2018-09-18 16:37 |  |  | Approved | 15.08.2018 06:03:07 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-08 10:14 | 2018-08-10 10:14 | 2018-08-01 09:00
CHG0030727 | DigiPlex Fet AS | Shutting down feed | Normal | Closed | 2018-08-06 13:11 | 2018-08-10 13:11 |  | 2018-09-20 09:18 | 2018-09-20 09:18 |  | 2018-09-20 | Approved | 15.08.2018 06:05:37 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-13 10:22 | 2018-08-14 10:22 | 2018-08-01 08:56
CHG0030726 | DigiPlex Fet AS | Reloction OPS office | Normal | Closed | 2018-08-06 08:01 | 2018-08-16 16:58 |  | 2018-09-20 09:17 | 2018-09-20 09:17 |  | 2018-09-20 | Approved | 07.08.2018 06:03:52 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-13 10:21 | 2018-08-17 10:21 | 2018-08-01 08:53
CHG0030725 | DigiPlex Fet AS | Temporarily relocate Guard station | Normal | Closed | 2018-08-12 13:13 | 2018-08-24 13:13 |  | 2018-09-18 16:45 | 2018-09-18 16:45 |  |  | Approved | 15.08.2018 06:06:49 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-08-29 10:18 | 2018-08-29 10:20 | 2018-08-01 08:49
CHG0030724 | DigiPlex Fet AS | Project William general | Normal | Implement | 2018-08-01 13:14 | 2019-02-01 13:14 |  | 2019-01-04 12:44 |  |  |  | Approved | 15.08.2018 06:08:22 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2018-08-01 08:42
CHG0030719 | DigiPlex Rosenholm AS | VVS 1 + VVS 3 New crane installation for pumps. | Normal | Closed | 2018-08-01 07:00 | 2018-09-28 08:54 |  | 2018-10-02 08:53 | 2018-10-02 08:53 |  |  | Approved | 31.07.2018 09:09:09 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-08-20 12:24 | 2018-08-28 12:24 | 2018-07-31 09:00
CHG0030718 | DigiPlex Stockholm 1 AB | Install pipe-in-pipe from existing MCWS | Normal | Closed | 2018-07-30 17:50 | 2018-08-02 17:50 |  | 2018-10-02 08:59 | 2018-10-02 08:59 |  |  | Approved |  | 2018-08-30 16:45 | 2018-08-17 16:45 | 2018-07-26 17:59
CHG0030716 | DigiPlex Norway AS | Prøvetagning av olje i Chillere | Normal | Closed | 2018-09-05 13:14 | 2018-09-05 13:14 |  | 2018-11-12 07:33 | 2018-11-12 07:33 |  |  | Approved | 04.09.2018 13:13:07 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-09-05 08:33 | 2018-09-05 16:00 | 2018-07-18 12:19
CHG0030715 | DigiPlex Norway AS | Yearly service of Fire Panels, DNAS | Standard | Canceled |  |  |  | 2018-10-04 14:54 |  |  |  | Approved |  |  |  | 2018-07-18 10:25
CHG0030714 | DigiPlex Rosenholm AS | P404 DRAS Desigo Insight Upgrade | Normal | Closed | 2018-07-23 11:53 | 2018-08-31 11:53 | Bjørn W Sætre | 2018-10-04 15:07 | 2018-10-04 15:07 |  |  | Approved | 11.07.2018 13:54:08 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-08-16 10:28 | 2018-08-22 10:32 | 2018-07-11 11:57
CHG0030711 | DigiPlex Stockholm 1 AB | DH7.2 PMS Network Replacement | Normal | Canceled | 2018-09-04 14:17 | 2018-09-07 14:17 |  | 2018-08-31 07:59 |  |  |  | Requested |  |  |  | 2018-07-09 14:17
CHG0030710 | DigiPlex Norway AS | Installasjon av stillas på fasade | Normal | Closed | 2018-07-10 10:52 | 2018-09-28 10:52 |  | 2019-02-15 18:59 | 2019-02-15 18:59 |  |  | Approved | 09.07.2018 14:06:03 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-10 10:12 | 2018-09-28 10:12 | 2018-07-09 10:53
CHG0030709 | DigiPlex Norway AS | Installasjon av utekraner for vask og renhold av uteområder. | Normal | Closed | 2018-07-10 10:45 | 2018-08-03 10:45 |  | 2018-09-18 16:46 | 2018-09-18 16:46 |  |  | Approved | 09.07.2018 14:07:24 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-24 13:08 | 2018-08-22 13:08 | 2018-07-09 10:50
CHG0030708 | DigiPlex Stockholm 1 AB | Installation of scaffolding to access the PICV's underneath the external gantry grating platform. | Normal | Closed | 2018-07-10 10:10 | 2018-07-23 10:10 |  | 2018-10-02 08:59 | 2018-10-02 08:59 |  |  | Approved |  | 2018-07-10 16:28 | 2018-07-23 16:28 | 2018-07-09 10:12
CHG0030707 | DigiPlex Stockholm 1 AB | Rerouting the discharge process water piping from DH1 &DH7 Munters' | Normal | Closed | 2018-07-10 15:52 | 2018-07-20 15:52 |  | 2018-09-28 11:31 | 2018-09-28 11:31 |  |  | Approved |  | 2018-07-10 16:21 | 2018-07-20 16:21 | 2018-07-06 15:53
CHG0030706 | DigiPlex Stockholm 1 AB | Replace existing MCWS ABS piping feeding the DH1 &DH7 Munters' humidifier by compression Cu piping. | Normal | Closed | 2018-07-09 15:40 | 2018-07-12 15:40 |  | 2018-10-02 09:00 | 2018-10-02 09:00 |  |  | Approved |  | 2018-07-09 16:46 | 2018-07-27 16:46 | 2018-07-06 15:41
CHG0030705 | DigiPlex Rosenholm AS | Fiber cabling from CCR room to Mod10 | Normal | Closed | 2018-07-10 08:00 | 2018-07-17 16:00 |  | 2018-07-16 13:30 | 2018-07-16 13:30 |  |  | Approved | 06.07.2018 10:07:17 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-07-12 07:30 | 2018-07-12 15:11 | 2018-07-06 10:04
CHG0030704 | DigiPlex Stockholm 1 AB | Remove unused power cable from North & South corridor to the Landlord POD | Normal | Closed | 2018-07-10 16:00 | 2018-07-10 16:00 |  | 2018-09-28 11:30 | 2018-09-28 11:30 |  |  | Approved |  | 2018-07-10 16:32 | 2018-07-12 16:32 | 2018-07-05 16:01
CHG0030703 | DigiPlex Stockholm 1 AB | Installation of temporary scaffolding to access the PICV's at the external gantry | Normal | Closed | 2018-07-09 14:28 | 2018-07-23 14:29 |  | 2018-08-30 08:34 | 2018-08-30 08:34 |  |  | Approved |  | 2018-07-09 14:26 | 2018-08-23 14:26 | 2018-07-05 14:29
CHG0030702 | DigiPlex Fet AS | Annual maintenance on fans and internal DX units | Normal | Closed | 2018-08-20 08:00 | 2018-08-24 16:00 |  | 2018-10-04 11:31 | 2018-10-04 11:31 | Patrick Bakke |  | Approved | 11.07.2018 13:53:29 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-08-19 06:33 | 2018-09-14 06:33 | 2018-07-05 13:27
CHG0030701 | DigiPlex Norway AS | Yearly Maintenance of F-gas Equipment (DX) | Normal | Closed | 2018-07-16 08:00 | 2018-08-03 16:00 |  | 2018-08-23 07:56 | 2018-08-23 07:56 |  |  | Approved | 06.07.2018 08:35:35 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-08-01 14:22 | 2018-08-03 14:22 | 2018-07-05 13:09
CHG0030700 | DigiPlex Fet AS | Annual maintenance on munters DX | Normal | Closed | 2018-08-20 08:00 | 2018-09-14 16:00 |  | 2018-10-03 13:21 | 2018-10-03 13:21 | Patrick Bakke |  | Approved | 05.07.2018 13:22:37 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-07-05 13:21
CHG0030698 | DigiPlex Rosenholm AS | DRAS-L2E RAMS-E08 Modbus kabel fra R02 MOD01 til FireWin sentral i R01 OFF01 | Normal | Closed | 2018-07-05 09:13 | 2018-07-13 16:00 |  | 2018-08-08 07:13 | 2018-08-08 07:13 |  |  | Approved | 05.07.2018 09:49:51 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-07-05 09:51 | 2018-07-12 09:51 | 2018-07-05 09:20
CHG0030697 | DigiPlex Norway AS | Reactive repair after monthly check of emergency lighting, DNAS | Normal | Closed | 2018-07-05 10:00 | 2018-07-20 16:00 |  | 2018-08-01 13:19 | 2018-08-01 13:19 |  |  | Approved | 05.07.2018 09:13:05 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-16 10:22 | 2018-07-20 10:22 | 2018-07-05 08:35
CHG0030696 | DigiPlex Norway AS | Parametiresation of KSB Pumps | Normal | Closed | 2018-07-05 08:18 | 2018-07-06 08:19 |  | 2018-07-08 10:30 | 2018-07-08 10:30 |  |  | Approved | 05.07.2018 08:20:37 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-05 12:23 | 2018-07-06 12:23 | 2018-07-04 20:33
CHG0030695 | DigiPlex Fet AS | Switch-010 replacement | Normal | Closed | 2018-07-05 11:00 | 2018-07-05 11:10 |  | 2018-09-13 09:15 | 2018-09-13 09:15 |  |  | Approved | 04.07.2018 15:10:45 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). |  |  | 2018-07-02 22:48
CHG0030694 | DigiPlex Norway AS | Remove old pipeinstallation from pumo pod by pump 3B | Normal | Closed | 2018-07-03 08:00 | 2018-08-10 18:18 |  | 2018-09-27 09:02 | 2018-09-27 09:02 |  |  | Approved | 03.07.2018 12:10:15 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-03 08:53 | 2018-08-10 15:53 | 2018-07-02 18:16
CHG0030693 | DigiPlex Norway AS | Pipeworks for Level 3 - Riser, fasade and roof | Normal | Closed | 2018-07-03 08:00 | 2018-08-29 18:09 |  | 2019-02-07 09:51 | 2019-02-07 09:51 |  | 2019-01-10 | Approved | 04.07.2018 14:01:03 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). 04.07.2018 10:25:42 - posullivan (Approval history) Pete O’Sullivan approved the task. Approval comments: 04/07/2018 08:25:42 - Pete O’Sullivan (Comments) Work Approved as described once a Hot Permit has been issued 04/07/2018 07:25:01 - Pete O’Sullivan (Comments) This Change Change involves Hot Working. There is no Hot Work Permit in the Change Request. Please complete a Finans Norge Hot Works Permit and add the names of the persons conducting the Hot Work to the Request after checking that they are on the Certified list previously supplied by ANOR 03.07.2018 10:39:36 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-03 20:41 | 2018-11-02 20:41 | 2018-07-02 18:11
CHG0030692 | DigiPlex Norway AS | ION meter in METR00/09B is defect - Replace meter | Emergency | Closed | 2018-07-02 08:30 | 2018-07-02 09:30 |  | 2018-07-08 10:25 | 2018-07-08 10:25 |  |  | Approved | 02.07.2018 15:19:20 - atorp (Approval history) Group approval for CAB Approval approved by user Atle Torp (eCAB approval). 02.07.2018 13:18:05 - fekay (Approval history) Group approval for eCAB Approval approved by user Frode Elden Kay (eCAB approval). | 2018-07-02 08:30 | 2018-07-02 09:30 | 2018-07-02 13:04
CHG0030690 | DigiPlex Stockholm 1 AB | DH 7.1 – Heat Load Test | Normal | Canceled | 2018-07-17 11:03 | 2018-07-17 11:04 |  | 2018-08-31 07:57 |  |  |  | Approved |  |  |  | 2018-06-29 11:02
CHG0030689 | DigiPlex Rosenholm AS | Flytting av kamera i COR 07 | Normal | Closed | 2018-07-02 10:23 | 2018-07-06 10:23 |  | 2018-07-06 07:55 | 2018-07-06 07:55 | Patrick Bakke |  | Approved | 02.07.2018 10:36:12 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-07-03 10:31 | 2018-07-06 07:54 | 2018-06-29 10:33
CHG0030688 | DigiPlex Rosenholm AS | New cable tray in modules. Relocating temp sensors. | Normal | Closed | 2018-07-02 18:16 | 2018-07-13 18:16 |  | 2018-10-16 08:28 | 2018-10-16 08:28 |  |  | Approved | 28.06.2018 23:48:28 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-07-08 07:31 | 2018-07-13 16:00 | 2018-06-28 18:17
CHG0030687 | DigiPlex Norway AS | New earth cable + earthing customer rack. | Normal | Closed | 2018-07-02 15:39 | 2018-07-13 15:39 |  | 2018-11-21 07:08 | 2018-11-21 07:08 |  |  | Approved | 03.07.2018 16:16:37 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). |  |  | 2018-06-28 15:41
CHG0030686 | DigiPlex Norway AS | Leveling floor. Painting works. Epoxy works. | Normal | Closed | 2018-07-02 14:32 | 2018-11-01 14:32 |  | 2018-11-01 09:12 | 2018-11-01 09:12 |  | 2018-11-01 | Approved | 03.07.2018 16:16:51 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-02 08:18 | 2018-11-01 08:18 | 2018-06-28 14:35
CHG0030685 | DigiPlex Norway AS | VVS works level 3. | Normal | Closed | 2018-07-02 12:16 | 2018-10-05 12:16 |  | 2019-01-07 07:30 | 2019-01-07 07:30 |  |  | Approved | 04.07.2018 14:01:14 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-07-02 20:59 | 2018-12-07 20:59 | 2018-06-28 12:18
CHG0030684 | DigiPlex Stockholm 1 AB | Installation of new fire escape button DH7.1.1B | Normal | Closed | 2018-08-13 07:23 | 2018-08-17 07:23 |  | 2018-08-30 14:50 | 2018-08-30 14:50 |  |  | Approved |  | 2018-08-16 09:10 | 2018-08-16 09:10 | 2018-06-28 07:24
CHG0030683 | DigiPlex Stockholm 1 AB | Addition of Jace controller to the network | Normal | Closed | 2018-07-09 00:09 | 2018-07-09 00:10 |  | 2019-04-12 11:21 | 2019-04-12 11:21 |  | 2018-06-28 | Approved |  | 2018-07-09 14:51 | 2018-07-09 14:52 | 2018-06-28 00:10
CHG0030682 | DigiPlex Norway AS | Thermal imaging of busbars and tapoff boxes | Normal | Closed | 2018-07-02 08:00 | 2018-07-04 16:00 |  | 2018-08-30 09:18 | 2018-08-30 09:18 |  |  | Approved | 02.07.2018 10:29:34 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-07-04 08:29 | 2018-07-04 08:31 | 2018-06-27 22:12
CHG0030680 | DigiPlex Stockholm 1 AB | Install new Drainage and water supply Loading Bay | Normal | Closed | 2018-06-28 07:43 | 2018-07-06 07:43 |  | 2018-09-28 11:29 | 2018-09-28 11:29 |  |  | Approved |  | 2018-06-28 16:34 | 2018-08-17 16:34 | 2018-06-27 07:43
CHG0030679 | DigiPlex Fet AS | DFAS. A2-3. Annual service of UPS's. | Normal | Canceled | 2018-09-03 06:51 | 2018-09-07 06:51 |  | 2019-07-17 14:13 |  |  |  | Approved | 27.06.2018 08:02:38 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-06-27 06:55
CHG0030678 | DigiPlex Fet AS | DFAS. A2-2. Annual service of UPS's | Normal | Closed | 2018-08-20 06:45 | 2018-08-24 06:45 |  | 2018-10-11 15:36 | 2018-10-11 15:36 |  | 2018-10-11 | Approved | 27.06.2018 08:00:57 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-20 10:12 | 2018-08-24 10:12 | 2018-06-27 06:49
CHG0030677 | DigiPlex Norway AS | Kranløft av 2 stykk brakker | Normal | Closed | 2018-06-27 16:06 | 2018-06-29 16:06 |  | 2018-06-28 10:54 | 2018-06-28 10:54 |  |  | Approved | 27.06.2018 11:09:43 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-06-27 08:29 | 2018-06-27 15:29 | 2018-06-26 16:08
CHG0030676 | DigiPlex Norway AS | VVS for Level 3. | Normal | Canceled | 2018-06-27 15:45 | 2018-10-26 15:45 |  | 2018-07-04 11:27 |  |  |  | Rejected | 27.06.2018 12:54:20 - galmquist (Approval history) Group approval for Change-Technical assess group rejected by user Geir Almquist (Technical approvals norway). |  |  | 2018-06-26 15:50
CHG0030675 | DigiPlex Rosenholm AS | SAT - 350 Data Hall Computer Room Cooling System | Normal | Closed | 2018-06-26 13:31 | 2018-07-08 16:00 |  | 2018-08-08 07:13 | 2018-08-08 07:13 |  |  | Approved | 28.06.2018 08:24:18 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-06-26 09:47 | 2018-07-08 09:48 | 2018-06-26 13:38
CHG0030674 | DigiPlex Rosenholm AS | SAT - 360.002 Ventilation | Normal | Closed | 2018-06-26 11:19 | 2018-10-15 16:00 |  | 2018-11-12 07:23 | 2018-11-12 07:23 |  |  | Approved | 26.06.2018 15:21:35 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-10-15 11:35 | 2018-10-15 11:36 | 2018-06-26 11:27
CHG0030673 | DigiPlex Stockholm 1 AB | Installation new door DH7.1.1B | Normal | Closed | 2018-06-27 21:10 | 2018-08-10 21:10 |  | 2018-06-28 07:45 | 2018-06-28 07:45 |  |  | Approved |  | 2018-06-27 06:57 | 2018-06-27 06:57 | 2018-06-25 21:12
CHG0030672 | DigiPlex Rosenholm AS | Module Specialist cleaning | Normal | Closed | 2018-07-02 08:00 | 2018-07-04 18:00 |  | 2018-08-24 10:24 | 2018-08-24 10:24 |  |  | Approved | 26.06.2018 12:48:46 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-07-02 09:15 | 2018-07-04 09:15 | 2018-06-25 15:03
CHG0030671 | DigiPlex Norway AS | Module Specialist cleaning | Normal | Closed | 2018-07-02 08:00 | 2018-07-04 18:00 |  | 2018-08-24 10:24 | 2018-08-24 10:24 |  |  | Approved | 26.06.2018 10:30:37 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-07-02 09:17 | 2018-07-04 09:17 | 2018-06-25 13:43
CHG0030670 | DigiPlex Stockholm 1 AB | Change metal covers for the glas facade | Normal | Closed | 2018-07-02 12:30 | 2018-07-23 12:33 |  | 2018-09-28 11:28 | 2018-09-28 11:28 |  |  | Approved |  | 2018-07-03 16:20 | 2018-07-04 16:20 | 2018-06-25 12:39
CHG0030669 | DigiPlex Stockholm 1 AB | Re-commission Process water system | Normal | Closed | 2018-07-12 11:31 | 2018-07-19 11:31 |  | 2018-08-30 14:57 | 2018-08-30 14:57 |  |  | Approved |  | 2018-07-12 16:17 | 2018-07-19 16:17 | 2018-06-25 11:31
CHG0030668 | DigiPlex Norway AS | Install generator 5 for switchboards E and F | Normal | Closed | 2018-06-26 13:41 | 2018-06-26 13:41 |  | 2018-06-28 07:47 | 2018-06-28 07:47 |  |  | Approved | 22.06.2018 13:55:41 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-26 09:33 | 2018-06-26 09:33 | 2018-06-22 13:41
CHG0030667 | DigiPlex Norway AS | Power up Switchboards on A-string and new UPS A | Normal | Closed | 2018-06-25 08:00 | 2018-06-26 16:00 |  | 2018-07-08 10:27 | 2018-07-08 10:27 |  |  | Approved | 22.06.2018 12:52:58 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-06-25 12:13 | 2018-06-26 12:13 | 2018-06-22 09:13
CHG0030666 | DigiPlex Norway AS | Demontere 2 Broadnet antenner på taket. | Normal | Closed | 2018-06-24 10:00 | 2018-06-24 12:00 |  | 2018-06-28 10:17 | 2018-06-28 10:17 |  |  | Approved | 22.06.2018 08:28:23 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-25 10:45 | 2018-06-25 11:45 | 2018-06-21 08:43
CHG0030665 | DigiPlex Stockholm 1 AB | Electrical work new customer cage DH7.1.1B | Normal | Closed | 2018-06-25 03:12 | 2018-07-06 03:12 |  | 2018-08-16 14:38 | 2018-08-16 14:38 |  |  | Approved |  | 2018-06-25 11:58 | 2018-07-06 11:58 | 2018-06-21 03:15
CHG0030661 | DigiPlex Fet AS | Test of breaker 432.231 - XQ10 | Normal | Closed | 2018-08-21 13:31 | 2018-08-21 16:00 |  | 2018-09-27 08:42 | 2018-09-27 08:40 |  |  | Approved | 20.06.2018 11:53:37 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-06-19 13:31
CHG0030658 | DigiPlex Norway AS | Install firewin publisher in reception. | Normal | Closed | 2018-06-21 09:39 | 2018-06-22 16:00 |  | 2018-10-25 08:19 | 2018-10-25 08:19 |  |  | Approved | 19.06.2018 10:10:29 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-22 10:46 | 2018-10-17 10:43 | 2018-06-19 09:42
CHG0030657 | DigiPlex Fet AS | Installation of Firewin in DFAS reception. | Normal | Closed | 2018-06-20 09:37 | 2018-06-21 16:00 |  | 2018-08-23 07:56 | 2018-08-23 07:56 |  |  | Approved | 19.06.2018 09:53:20 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-21 08:39 | 2018-06-21 08:39 | 2018-06-19 09:36
CHG0030656 | DigiPlex Rosenholm AS | VESDA service | Normal | Closed | 2018-06-28 08:41 | 2018-06-28 08:41 |  | 2018-08-01 13:20 | 2018-08-01 13:20 |  |  | Approved | 19.06.2018 09:02:29 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-06-28 08:05 | 2018-06-28 08:05 | 2018-06-19 08:43
CHG0030655 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting, DNAS - June | Normal | Closed | 2018-06-18 10:00 | 2018-06-29 16:00 |  | 2018-07-08 10:29 | 2018-07-08 10:29 |  |  | Approved | 19.06.2018 09:01:38 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-06-18 14:18 | 2018-06-29 14:18 | 2018-06-18 08:23
CHG0030654 | DigiPlex Norway AS | Vask under datagulv i korridorerog CCR C , vask av plant rooms | Normal | Closed | 2018-06-18 08:00 | 2018-07-06 16:00 |  | 2018-08-24 10:03 | 2018-08-24 10:03 | Rune Jansen |  | Approved | 15.06.2018 12:43:57 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-06-15 12:33
CHG0030653 | DigiPlex Stockholm 1 AB | Additional Roof Support Installation | Normal | Closed | 2018-06-20 15:13 | 2018-06-29 15:13 |  | 2018-10-11 15:05 | 2018-10-11 15:05 |  | 2018-10-11 | Approved |  | 2018-06-25 16:22 | 2018-07-11 16:23 | 2018-06-14 15:13
CHG0030652 | DigiPlex Stockholm 1 AB | Compressor Compartment Panelling Works | Normal | Closed | 2018-06-20 14:15 | 2018-06-24 14:15 |  | 2018-09-28 10:47 | 2018-09-28 10:47 |  |  | Approved |  | 2018-06-20 16:41 | 2018-06-25 16:41 | 2018-06-14 14:18
CHG0030650 | DigiPlex Rosenholm AS | Installere leak detection i COR07 | Normal | Closed | 2018-06-22 08:56 | 2018-06-29 08:56 |  | 2018-11-15 09:06 | 2018-11-15 09:06 |  |  | Approved | 19.06.2018 08:19:13 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-22 10:18 | 2018-09-26 10:18 | 2018-06-14 08:57
CHG0030647 | DigiPlex Norway AS | Severe network outage DNAS | Emergency | Closed | 2018-06-12 11:00 | 2018-06-12 11:30 |  | 2018-06-28 07:55 | 2018-06-28 07:55 |  | 2018-06-14 | Approved | 15.06.2018 09:15:53 - pviken (Approval history) Group approval for CAB Approval approved by user Pål Rune Viken (eCAB approval). 13.06.2018 09:07:18 - fekay (Approval history) Group approval for eCAB Approval approved by user Frode Elden Kay (eCAB approval). | 2018-06-12 11:00 | 2018-06-12 11:40 | 2018-06-12 07:57
CHG0030646 | DigiPlex Norway AS | To carry out commissioning of UPS A and Modifications to BMS in UPS A and B Control Panels | Normal | Closed | 2018-06-18 11:56 | 2018-08-31 11:56 |  | 2018-09-03 11:36 | 2018-09-03 11:36 |  |  | Approved | 13.06.2018 09:18:36 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-07-02 09:30 | 2018-08-27 09:31 | 2018-06-11 11:58
CHG0030644 | DigiPlex Norway AS | Switch upgrade SW020 and SW014 | Normal | Closed | 2018-06-11 10:36 | 2018-06-11 12:00 |  | 2018-07-10 10:14 | 2018-07-10 10:14 |  |  | Approved | 11.06.2018 10:41:06 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-06-11 08:42 | 2018-06-11 08:42 | 2018-06-11 10:36
CHG0030643 | DigiPlex Stockholm 1 AB | Remove and reinstate block paving for crane piles | Normal | Closed | 2018-06-13 07:23 | 2018-06-27 07:23 |  | 2018-09-03 11:37 | 2018-09-03 11:37 |  |  | Approved |  | 2018-06-13 16:14 | 2018-07-06 16:14 | 2018-06-08 07:32
CHG0030642 | DigiPlex Rosenholm AS | Nye kamera, node og nye kortlesere | Normal | Closed | 2018-06-08 07:00 | 2018-06-15 16:00 |  | 2018-09-14 10:57 | 2018-09-14 10:57 |  |  | Approved | 08.06.2018 11:32:24 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-06-07 10:32 | 2018-08-30 10:32 | 2018-06-07 11:53
CHG0030641 | DigiPlex Stockholm 1 AB | For the crane to sit on the pile foundation the block paving needs to be removed | Normal | Closed | 2018-06-13 10:46 | 2018-06-26 10:46 |  | 2018-09-28 10:46 | 2018-09-28 10:46 |  |  | Approved |  | 2018-06-13 16:25 | 2018-06-26 16:25 | 2018-06-07 10:55
CHG0030640 | DigiPlex Norway AS | Temporary feed to SBSB1C | Emergency | Closed | 2018-05-28 10:09 | 2018-05-28 16:09 |  | 2018-06-14 10:26 | 2018-06-14 10:26 |  | 2018-06-14 | Approved | 07.06.2018 11:51:26 - pviken (Approval history) Group approval for CAB Approval approved by user Pål Rune Viken (eCAB approval). 07.06.2018 10:08:35 - aolsen (Approval history) Group approval for eCAB Approval approved by user Alexander Olsen (eCAB approval). | 2018-05-28 10:09 | 2018-05-28 16:09 | 2018-06-07 09:46
CHG0030639 | DigiPlex Rosenholm AS | SAT - 494.06-KS03 og -KS04 No Break bus bar load test , 493.03-KS01 og -KS02 Short Break bus bar load test | Normal | Closed | 2018-06-07 08:28 | 2018-06-22 08:28 |  | 2018-06-28 07:44 | 2018-06-28 07:44 |  |  | Approved | 07.06.2018 15:28:01 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-06-07 09:35 | 2018-06-13 09:36 | 2018-06-07 08:41
CHG0030638 | DigiPlex Stockholm 1 AB | This is no change request, we need to use the fire hydrant water supply for the screeding activity in the Fallow Space | Normal | Closed | 2018-06-11 07:44 | 2018-06-29 07:44 |  | 2018-08-23 07:55 | 2018-08-23 07:55 |  |  | Approved |  | 2018-06-11 16:26 | 2018-06-29 16:26 | 2018-06-07 07:54
CHG0030637 | DigiPlex Stockholm 1 AB | Create a ventilation path in the Fallow Space through the hatches in the roof giving fresh air. | Normal | Closed | 2018-06-11 07:18 | 2018-06-29 07:18 |  | 2018-09-28 10:46 | 2018-09-28 10:46 |  |  | Approved |  | 2018-06-11 16:19 | 2018-06-29 16:19 | 2018-06-07 07:42
CHG0030636 | DigiPlex Rosenholm AS | DRAS-L2E RAMS-E09 Feilsøke Vern H3 rev 1 | Normal | Closed | 2018-06-07 07:00 | 2018-06-07 19:00 |  | 2018-06-28 08:00 | 2018-06-28 08:00 |  |  | Approved | 06.06.2018 11:02:37 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-06-07 11:07 | 2018-06-07 11:07 | 2018-06-06 10:57
CHG0030635 | DigiPlex Rosenholm AS | Feilsøke vern i H3 | Normal | Closed | 2018-06-06 10:00 | 2018-06-06 19:00 |  | 2018-07-25 11:40 | 2018-07-25 11:40 |  |  | Approved | 05.06.2018 15:53:15 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Bjørnstad (Technical approvals norway). | 2018-06-06 08:06 | 2018-06-06 08:06 | 2018-06-05 15:48
CHG0030634 | DigiPlex Rosenholm AS | Isolate B-side on short break board | Normal | Closed | 2018-06-06 09:31 | 2018-06-08 15:10 |  | 2018-06-28 08:04 | 2018-06-28 08:04 |  |  | Approved | 06.06.2018 08:24:30 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-06 09:08 | 2018-06-08 09:08 | 2018-06-05 15:13
CHG0030633 | DigiPlex Rosenholm AS | 12M service av ADC | Normal | Closed | 2018-06-06 13:47 | 2018-08-31 13:47 |  | 2018-08-08 09:04 | 2018-08-08 09:04 |  |  | Approved | 05.06.2018 13:30:23 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-06 08:51 | 2018-08-02 08:51 | 2018-06-04 13:47
CHG0030632 | DigiPlex Rosenholm AS | Bytte av defekt vannregulator til Adiabaticen til ADC4 | Normal | Closed | 2018-06-06 13:24 | 2018-06-15 13:24 |  | 2018-06-28 08:04 | 2018-06-28 08:04 |  |  | Approved | 06.06.2018 08:25:56 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-11 08:28 | 2018-06-11 08:28 | 2018-06-04 13:24
CHG0030630 | DigiPlex Norway AS | Core switch reboot | Emergency | Closed | 2018-06-04 14:00 | 2018-06-04 14:15 |  | 2018-06-28 09:06 | 2018-06-28 09:06 |  | 2018-06-28 | Approved | 15.06.2018 09:15:12 - pviken (Approval history) Group approval for CAB Approval approved by user Pål Rune Viken (eCAB approval). 04.06.2018 13:37:37 - fekay (Approval history) Group approval for eCAB Approval approved by user Frode Elden Kay (eCAB approval). | 2018-06-04 14:00 | 2018-06-14 10:31 | 2018-06-04 11:43
CHG0030629 | DigiPlex Norway AS | Replacement of Hafslund Power Meters | Normal | Closed | 2018-06-04 08:00 | 2018-06-04 16:00 |  | 2018-06-07 07:26 | 2018-06-07 07:26 |  |  | Approved | 04.06.2018 13:34:16 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-06-04 08:00 | 2018-06-04 16:00 | 2018-06-04 07:39
CHG0030628 | DigiPlex Stockholm 1 AB | Add one Munters for DH7.1 | Normal | Closed | 2018-06-12 17:30 | 2018-06-22 17:30 |  | 2018-10-11 15:02 | 2018-10-11 15:02 |  | 2018-10-11 | Approved |  | 2018-06-13 14:43 | 2018-06-22 14:43 | 2018-05-29 17:40
CHG0030627 | DigiPlex Rosenholm AS | Connection of the new R02 Mod 01 BMS system | Normal | Closed | 2018-05-30 07:00 | 2018-09-21 16:00 |  | 2018-10-04 15:11 | 2018-10-04 15:11 |  |  | Approved | 29.05.2018 15:58:22 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-06-26 10:33 | 2018-06-29 10:34 | 2018-05-29 15:56
CHG0030626 | DigiPlex Rosenholm AS | Relocate card readers in R01MOD10 to new cage door inside R01MOD02. | Normal | Closed | 2018-05-30 07:40 | 2018-06-08 12:40 |  | 2018-08-23 08:00 | 2018-08-23 08:00 |  |  | Approved | 29.05.2018 13:18:53 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-06-03 07:28 | 2018-06-07 07:29 | 2018-05-29 12:41
CHG0030625 | DigiPlex Rosenholm AS | RAMS BA01 Implementering av nye effektbrytere til eksisterende Schneider electric iOn PMS | Normal | Closed | 2018-05-29 10:12 | 2018-06-08 16:00 |  | 2018-09-14 10:53 | 2018-09-14 10:53 |  |  | Approved | 29.05.2018 10:41:30 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-29 10:35 | 2018-06-08 10:36 | 2018-05-29 10:28
CHG0030624 | DigiPlex Rosenholm AS | Service av pumper | Normal | Closed | 2018-06-08 07:30 | 2018-07-31 17:00 |  | 2018-06-28 09:14 | 2018-06-28 09:14 |  | 2018-06-28 | Approved | 04.06.2018 07:46:48 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-08 08:27 | 2018-06-11 08:27 | 2018-05-29 10:38
CHG0030622 | DigiPlex Rosenholm AS | Isolate part of CW C-string | Normal | Closed | 2018-05-30 09:49 | 2018-05-31 09:49 |  | 2018-06-16 22:11 | 2018-06-16 22:11 |  |  | Approved | 29.05.2018 15:42:21 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-05-30 09:08 | 2018-06-11 09:08 | 2018-05-29 09:50
CHG0030618 | DigiPlex Rosenholm AS | Rep av ccuer | Normal | Closed | 2018-05-31 08:00 | 2018-06-01 14:15 |  | 2018-11-14 07:25 | 2018-11-14 07:25 |  |  | Approved | 28.05.2018 14:22:03 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-05-31 10:17 | 2018-10-18 10:17 | 2018-05-28 14:15
CHG0030617 | DigiPlex Norway AS | To carry out commissioning of BMS connections to new Pumps | Normal | Closed | 2018-05-28 09:47 | 2018-06-29 09:47 |  | 2018-09-03 11:36 | 2018-09-03 11:36 |  |  | Approved | 04.06.2018 07:51:08 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-05 07:38 | 2018-06-28 07:38 | 2018-05-28 09:52
CHG0030616 | DigiPlex Norway AS | To carry out commissioning of BMS connections to new Pumps | Normal | Canceled | 2018-05-28 08:00 | 2018-06-06 18:00 |  | 2018-06-13 09:41 |  |  |  | Rejected | 05.06.2018 13:35:59 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). | 2018-05-28 08:00 | 2018-06-06 18:00 | 2018-05-28 08:48
CHG0030614 | DigiPlex Rosenholm AS | Ommbygging av R02 | Normal | Closed | 2018-05-25 14:41 | 2018-10-15 16:00 |  | 2020-01-09 12:36 | 2020-01-09 12:36 | Kristin Ohnstad |  | Approved | 29.05.2018 13:58:52 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-25 08:56 | 2018-10-15 08:57 | 2018-05-25 14:48
CHG0030613 | DigiPlex Rosenholm AS | DRAS L2E RAMS-S01 OFF 01 Kontroll av adgangssystem | Normal | Closed | 2018-05-27 08:00 | 2018-06-01 16:00 |  | 2018-09-14 11:00 | 2018-09-14 11:00 |  |  | Approved | 25.05.2018 14:18:04 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-25 10:30 | 2018-05-27 10:31 | 2018-05-25 14:11
CHG0030612 | DigiPlex Rosenholm AS | Ny kortleser til lager i service korridor R1 STO 03 | Normal | Canceled | 2018-06-04 13:32 | 2018-08-31 13:32 |  | 2018-10-31 15:44 |  |  |  | Approved | 05.06.2018 13:41:38 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-05-25 13:32
CHG0030609 | DigiPlex Rosenholm AS | DRAS L2E RAMS-E07 Montering av ny stikkontakt for rense anlegg | Normal | Closed | 2018-05-27 07:00 | 2018-08-31 14:00 |  | 2018-09-28 10:42 | 2018-09-28 10:42 |  |  | Approved | 25.05.2018 13:26:13 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). |  |  | 2018-05-25 11:09
CHG0030605 | DigiPlex Stockholm 1 AB | Connect temp DB to LL POD | Normal | Closed | 2018-05-28 14:50 | 2018-05-28 17:49 |  | 2018-06-26 17:50 | 2018-06-26 17:50 | Daniel Kolm |  | Approved |  |  |  | 2018-05-24 14:58
CHG0030604 | DigiPlex Rosenholm AS | DRAS L2E RAMS-R01 Påsveising nye avstikk COR 07 | Normal | Closed | 2018-05-27 08:00 | 2018-05-30 16:01 |  | 2018-06-16 22:17 | 2018-06-16 22:17 |  |  | Approved | 29.05.2018 09:44:38 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-27 09:10 | 2018-06-08 09:10 | 2018-05-23 16:27
CHG0030602 | DigiPlex Norway AS | 6 monthly ION service | Normal | Closed | 2018-05-23 09:00 | 2018-05-25 16:00 |  | 2018-06-07 09:10 | 2018-06-07 09:10 |  | 2018-06-07 | Approved | 23.05.2018 11:16:01 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-23 09:00 | 2018-05-25 16:00 | 2018-05-23 08:26
CHG0030601 | DigiPlex Stockholm 1 AB | Install the New GLP Loading bay | Normal | Closed | 2018-06-05 08:07 | 2018-06-05 08:10 |  | 2018-06-26 17:52 | 2018-06-26 17:52 | Daniel Kolm |  | Approved |  | 2018-06-05 17:51 | 2018-06-08 17:51 | 2018-05-23 08:10
CHG0030599 | DigiPlex Stockholm 1 AB | .his is only a test done with CTS | Normal | Canceled | 2018-05-23 15:07 | 2018-05-29 15:07 |  | 2018-05-23 09:46 |  |  |  | Requested |  |  |  | 2018-05-22 15:11
CHG0030598 | DigiPlex Rosenholm AS | Rep av gen 4.3 | Normal | Closed | 2018-05-22 08:41 | 2018-05-23 08:41 |  | 2018-06-13 10:00 | 2018-06-13 10:00 |  |  | Approved | 22.05.2018 08:44:16 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-22 08:30 | 2018-05-23 08:31 | 2018-05-22 08:41
CHG0030597 | DigiPlex Stockholm 1 AB | Access control and CCTV installations | Normal | Closed | 2018-05-17 17:18 | 2018-05-25 17:18 |  | 2018-07-11 10:56 | 2018-07-11 10:56 |  |  | Approved |  | 2018-05-20 15:46 | 2018-05-25 15:47 | 2018-05-16 17:19
CHG0030596 | DigiPlex Norway AS | Move UPS D5 from D- to C-string | Normal | Closed | 2018-06-25 08:00 | 2018-06-29 16:00 |  | 2018-08-27 14:18 | 2018-08-27 14:18 |  |  | Approved | 20.06.2018 15:16:29 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). 18.05.2018 09:15:09 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-08-02 14:14 | 2018-08-03 14:16 | 2018-05-16 14:26
CHG0030595 | DigiPlex Norway AS | Move Critical load C from SB1C to CSSB1E and Shortbreak load A and C to raw mains SB1A | Normal | Closed | 2018-05-22 08:00 | 2018-05-25 16:00 |  | 2018-06-28 09:32 | 2018-06-28 09:32 |  |  | Approved | 18.05.2018 11:49:45 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). |  |  | 2018-05-16 11:09
CHG0030594 | DigiPlex Rosenholm AS | Utsparinger 1 etg for ny feed til 2 etg R02-MOD 01 | Normal | Closed | 2018-05-16 09:03 | 2018-05-23 17:00 |  | 2018-08-08 07:14 | 2018-08-08 07:14 |  |  | Approved | 16.05.2018 09:09:51 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-16 09:54 | 2018-05-23 09:54 | 2018-05-16 09:06
CHG0030593 | DigiPlex Fet AS | DFAS Genset service A2-4 | Normal | Closed | 2018-06-21 07:50 | 2018-06-21 07:50 |  | 2018-08-01 13:16 | 2018-08-01 13:16 |  | 2018-06-28 | Approved | 16.05.2018 08:33:49 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-21 07:14 | 2018-06-21 07:14 | 2018-05-16 07:52
CHG0030592 | DigiPlex Fet AS | DFAS Genset service A2-3 | Normal | Closed | 2018-06-21 07:48 | 2018-06-21 07:48 |  | 2018-08-01 13:17 | 2018-08-01 13:17 |  | 2018-06-28 | Approved | 16.05.2018 08:33:10 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-21 07:10 | 2018-06-21 07:10 | 2018-05-16 07:49
CHG0030591 | DigiPlex Fet AS | DFAS Genset service A2-2 | Normal | Closed | 2018-06-20 07:46 | 2018-06-20 07:46 |  | 2018-08-01 13:17 | 2018-08-01 13:17 |  | 2018-06-28 | Approved | 16.05.2018 08:35:13 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-20 07:11 | 2018-06-20 07:11 | 2018-05-16 07:45
CHG0030590 | DigiPlex Fet AS | DFAS Genset service A2-1 | Normal | Closed | 2018-06-20 07:42 | 2018-06-20 07:42 |  | 2018-06-28 11:00 | 2018-06-28 11:00 |  | 2018-06-28 | Approved | 16.05.2018 08:32:23 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-20 13:42 | 2018-06-20 13:42 | 2018-05-16 07:42
CHG0030589 | DigiPlex Fet AS | DFAS Genset service A1-4 | Normal | Closed | 2018-06-19 07:37 | 2018-06-19 07:37 |  | 2018-08-01 13:17 | 2018-08-01 13:17 |  | 2018-06-28 | Approved | 16.05.2018 08:30:41 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-19 07:13 | 2018-06-19 07:13 | 2018-05-16 07:37
CHG0030588 | DigiPlex Fet AS | DFAS Genset service A1-3 | Normal | Closed | 2018-06-19 07:34 | 2018-06-19 07:34 |  | 2018-08-01 13:18 | 2018-08-01 13:18 |  | 2018-06-28 | Approved | 16.05.2018 08:29:51 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-19 07:12 | 2018-06-19 07:12 | 2018-05-16 07:34
CHG0030587 | DigiPlex Fet AS | DFAS Genset service A1-2 | Normal | Closed | 2018-06-18 07:30 | 2018-06-18 07:30 |  | 2018-08-01 13:18 | 2018-08-01 13:18 |  | 2018-06-28 | Approved | 16.05.2018 08:27:49 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-18 07:12 | 2018-06-18 07:12 | 2018-05-16 07:28
CHG0030586 | DigiPlex Fet AS | DFAS Genset service A1-1 | Normal | Closed | 2018-06-18 07:24 | 2018-06-18 07:24 |  | 2018-06-28 11:02 | 2018-06-28 11:02 |  | 2018-06-28 | Approved | 16.05.2018 08:26:55 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-18 13:07 | 2018-06-18 13:07 | 2018-05-16 07:26
CHG0030585 | DigiPlex Norway AS | Fiber cabling from CCR-A and CCR-B to -01Mod08.4 | Normal | Closed | 2018-05-22 07:22 | 2018-06-20 07:22 |  | 2018-06-16 22:10 | 2018-06-16 22:10 |  |  | Approved | 16.05.2018 08:57:25 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-22 15:00 | 2018-06-11 16:00 | 2018-05-16 07:26
CHG0030583 | DigiPlex Rosenholm AS | RAMS B02 hulltakinger og branntetting COR 07 | Normal | Closed | 2018-05-18 07:00 | 2018-06-01 17:00 |  | 2018-07-25 11:39 | 2018-07-25 11:39 |  |  | Approved | 15.05.2018 15:10:25 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-15 08:03 | 2018-07-24 08:03 | 2018-05-15 13:43
CHG0030582 | DigiPlex Rosenholm AS | RAMS B01 hulltakinger og branntetting PLT01 | Normal | Closed | 2018-05-16 07:00 | 2018-06-01 17:00 |  | 2018-07-25 11:39 | 2018-07-25 11:39 |  |  | Approved | 15.05.2018 14:48:39 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-15 08:02 | 2018-07-24 08:02 | 2018-05-15 13:39
CHG0030581 | DigiPlex Rosenholm AS | DRAS-L2E RAMS-R04 PLT09 Tilkobling Mitco doseringanlegg Rev.1 | Normal | Closed | 2018-05-22 07:00 | 2018-05-25 17:00 |  | 2018-06-28 08:07 | 2018-06-28 08:07 |  |  | Approved | 15.05.2018 14:38:51 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-22 09:26 | 2018-05-25 09:27 | 2018-05-15 09:50
CHG0030580 | DigiPlex Rosenholm AS | DRAS-L2E RAMS-R03 PLT08 Tilkobling Mitco doseringanlegg Rev.1 | Normal | Closed | 2018-05-22 07:00 | 2018-05-25 17:00 |  | 2018-06-28 08:08 | 2018-06-28 08:08 |  |  | Approved | 15.05.2018 14:37:03 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). |  | 2018-05-22 09:24 | 2018-05-15 09:49
CHG0030579 | DigiPlex Rosenholm AS | DRAS-L2E RAMS-R02 Rørføring kjølerør fra COR 07 til WhiteSpace | Normal | Closed | 2018-05-28 07:00 | 2018-06-08 17:00 |  | 2018-06-28 08:09 | 2018-06-28 08:09 |  |  | Approved | 25.05.2018 13:43:16 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). |  | 2018-05-28 09:38 | 2018-05-15 09:44
CHG0030578 | DigiPlex Fet AS | DFAS UPS service A2-1 | Normal | Closed | 2018-06-18 06:07 | 2018-06-22 06:07 |  | 2018-08-01 13:18 | 2018-08-01 13:18 |  | 2018-06-28 | Approved | 16.05.2018 08:37:02 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-18 07:13 | 2018-06-22 07:13 | 2018-05-15 06:09
CHG0030566 | DigiPlex Rosenholm AS | Planlegging og igangkjøring av innstallasjon for doseringsanlegg for rensing av kjølekretser | Normal | Closed | 2018-05-14 12:19 | 2018-05-25 12:19 |  | 2018-07-08 10:23 | 2018-07-08 10:23 |  |  | Approved | 11.05.2018 13:01:06 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-14 08:25 | 2018-06-25 08:25 | 2018-05-11 12:20
CHG0030565 | DigiPlex Rosenholm AS | New cable way over rack. Earthing customer racks. | Normal | Closed | 2018-05-14 07:11 | 2018-06-15 11:11 |  | 2018-09-14 10:52 | 2018-09-14 10:52 |  |  | Approved | 11.05.2018 11:51:30 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-06-12 08:47 | 2018-06-13 08:47 | 2018-05-11 11:12
CHG0030564 | DigiPlex Rosenholm AS | Mounting new cage wall with cardreaders and new camera. | Normal | Closed | 2018-05-14 07:09 | 2018-06-15 11:09 |  | 2018-09-03 11:35 | 2018-09-03 11:35 |  |  | Approved | 11.05.2018 11:55:29 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-06-06 08:41 | 2018-06-15 08:42 | 2018-05-11 11:11
CHG0030563 | DigiPlex Stockholm 1 AB | Repair Mians Water supply | Normal | Closed | 2018-05-14 22:17 | 2018-05-18 22:17 |  | 2018-07-11 10:56 | 2018-07-11 10:56 |  |  | Approved |  | 2018-06-14 15:56 | 2018-05-17 15:56 | 2018-05-10 22:19
CHG0030562 | DigiPlex Rosenholm AS | Disconnecting old batteries and UPS’s. | Normal | Closed | 2018-05-14 07:01 | 2018-06-15 15:58 |  | 2018-08-30 09:40 | 2018-08-30 09:40 | Pål Rune Viken |  | Approved | 11.05.2018 08:30:36 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). |  |  | 2018-05-09 16:01
CHG0030561 | DigiPlex Fet AS | DFAS UPS Service A1-3 | Normal | Closed | 2018-06-15 11:56 | 2018-06-18 11:56 |  | 2018-06-28 11:01 | 2018-06-28 11:01 |  | 2018-06-28 | Approved | 16.05.2018 08:22:37 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-15 13:40 | 2018-06-18 13:40 | 2018-05-09 11:57
CHG0030560 | DigiPlex Fet AS | DFAS UPS Service A1-2 | Normal | Closed | 2018-06-11 11:49 | 2018-06-15 11:49 |  | 2018-06-28 11:04 | 2018-06-28 11:04 |  | 2018-06-28 | Approved | 16.05.2018 08:18:42 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-11 13:12 | 2018-06-15 13:12 | 2018-05-09 11:43
CHG0030559 | DigiPlex Stockholm 1 AB | Cooring holes | Normal | Closed | 2018-05-11 11:17 | 2018-05-11 11:17 |  | 2018-07-02 23:33 | 2018-07-02 23:32 |  |  | Approved |  | 2018-04-11 15:46 | 2018-05-11 15:46 | 2018-05-09 11:18
CHG0030557 | DigiPlex Rosenholm AS | Fiber cabling from CCR-A and CCR-B to Level2 | Normal | Closed | 2018-05-15 08:00 | 2018-06-29 16:00 |  | 2018-07-18 14:32 | 2018-07-18 14:32 |  |  | Approved | 11.05.2018 08:32:54 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-22 07:30 | 2018-06-19 15:00 | 2018-05-09 08:16
CHG0030556 | DigiPlex Fet AS | DFAS UPS service A1-1 | Normal | Closed | 2018-06-05 06:56 | 2018-06-11 06:57 |  | 2018-06-28 10:58 | 2018-06-28 10:58 |  | 2018-06-28 | Approved | 09.05.2018 08:51:15 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-06 13:10 | 2018-06-11 13:10 | 2018-05-09 06:55
CHG0030555 | DigiPlex Stockholm 1 AB | Modication of existing Ventilationsystem Loading Bay | Normal | Closed | 2018-05-09 14:58 | 2018-05-18 14:59 |  | 2018-07-02 23:33 | 2018-07-02 23:33 |  |  | Approved |  | 2018-05-09 17:59 | 2018-06-18 17:59 | 2018-05-08 15:08
CHG0030554 | DigiPlex Stockholm 1 AB | Install ventilation ductwork DH7 corridors | Normal | Closed | 2018-05-09 14:56 | 2018-05-18 14:56 |  | 2018-07-11 10:57 | 2018-07-11 10:57 |  |  | Approved |  | 2018-05-09 15:57 | 2018-05-18 15:57 | 2018-05-08 14:56
CHG0030553 | DigiPlex Norway AS | Install new temp/hum sensors underfloor in cold aisle | Normal | Closed | 2018-05-08 12:49 | 2018-05-08 12:49 |  | 2018-08-08 08:52 | 2018-08-08 08:52 |  |  | Approved | 08.05.2018 12:52:02 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-05-08 09:33 | 2018-05-08 09:33 | 2018-05-08 12:49
CHG0030548 | DigiPlex Fet AS | Pulling new fiber and remounting electrical feed to barrack. | Normal | Closed | 2018-05-08 07:01 | 2018-05-18 10:06 |  | 2018-06-16 22:09 | 2018-06-16 22:09 |  |  | Approved | 07.05.2018 11:35:24 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-05-28 09:14 | 2018-05-30 09:14 | 2018-05-07 10:08
CHG0030547 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting, DNAS | Normal | Closed | 2018-05-07 12:13 | 2018-05-25 12:13 |  | 2018-06-07 07:27 | 2018-06-07 07:27 |  |  | Approved | 04.05.2018 12:27:06 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-05-21 08:00 | 2018-05-25 16:00 | 2018-05-04 12:17
CHG0030546 | DigiPlex Norway AS | Test of "chocolate box" | Normal | Closed | 2018-05-04 14:39 | 2018-05-04 14:40 |  | 2018-07-16 14:05 | 2018-07-16 14:05 | Geir Almquist |  | Approved | 03.05.2018 14:42:55 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-04 14:10 | 2018-05-04 14:10 | 2018-05-03 14:40
CHG0030545 | DigiPlex Stockholm 1 AB | Refurbish toilets, tiling, painting, change light fittings | Normal | Closed | 2018-05-04 12:34 | 2018-05-24 12:34 |  | 2018-08-16 14:37 | 2018-08-16 14:37 |  |  | Approved |  | 2018-05-24 08:11 | 2018-08-07 11:56 | 2018-05-03 12:34
CHG0030543 | DigiPlex Norway AS | Genset Connection | Normal | Closed | 2018-05-03 10:07 | 2018-08-31 10:07 |  | 2018-08-30 08:36 | 2018-08-30 08:36 |  |  | Approved | 03.05.2018 12:14:18 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-20 07:27 | 2018-08-16 07:27 | 2018-05-03 10:17
CHG0030539 | DigiPlex Norway AS | Årlig service på 5 Stk. Chillerere | Normal | Closed | 2018-05-03 14:51 | 2018-05-09 14:52 |  | 2018-07-16 13:33 | 2018-07-16 13:33 |  |  | Approved | 02.05.2018 14:57:17 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-05-03 14:08 | 2018-05-09 14:09 | 2018-05-02 14:29
CHG0030537 | DigiPlex Rosenholm AS | Fiber cabling from CCR room to modules | Normal | Closed | 2018-05-08 08:00 | 2018-05-22 17:00 |  | 2018-06-07 07:31 | 2018-06-07 07:31 |  |  | Approved | 08.05.2018 09:25:39 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-08 08:05 | 2018-05-14 08:30 | 2018-05-02 14:02
CHG0030536 | DigiPlex Stockholm 1 AB | Panel Modification of Data Transfer Control Panel | Normal | Closed | 2018-05-03 09:52 | 2018-05-04 09:52 |  | 2019-04-12 11:21 | 2019-04-12 11:21 |  |  | Approved |  | 2018-05-02 08:31 | 2018-05-02 10:01 | 2018-05-02 09:54
CHG0030535 | DigiPlex Stockholm 1 AB | Install temp sensors | Normal | Closed | 2018-05-03 09:47 | 2018-05-04 09:47 |  | 2018-07-02 23:34 | 2018-07-02 23:34 |  |  | Approved |  | 2018-05-03 17:47 | 2018-05-04 17:47 | 2018-05-02 09:48
CHG0030533 | DigiPlex Norway AS | Upgrade CCUs in -01MOD08.4 and -01MOD08.2 | Normal | Closed | 2018-05-02 09:01 | 2018-05-11 09:01 |  | 2018-11-14 07:24 | 2018-11-14 07:24 |  | 2018-05-02 | Approved | 02.05.2018 09:23:15 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-05-02 09:01 | 2018-05-11 14:11 | 2018-05-02 09:02
CHG0030529 | DigiPlex Norway AS | Yearly service of Fire Panels, DNAS | Standard | Canceled |  |  |  | 2018-05-03 08:12 |  |  |  | Approved |  |  |  | 2018-04-30 14:14
CHG0030527 | DigiPlex Rosenholm AS | Inntransport montasje ifm aggregat befukter | Normal | Closed | 2018-04-30 07:00 | 2018-06-01 16:00 |  | 2018-06-16 22:09 | 2018-06-16 22:09 |  |  | Approved | 04.05.2018 08:26:07 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). |  | 2018-05-28 09:29 | 2018-04-27 09:30
CHG0030526 | DigiPlex Stockholm 1 AB | Measure the call points for function before removing from wall around DH1 | Emergency | Canceled | 2018-04-20 07:00 | 2018-04-20 17:00 |  | 2018-09-10 09:01 |  |  |  | Requested | 30.04.2018 15:01:25 - ceghult (Approval history) Group approval for eCAB Approval approved by user Christian Eghult (eCAB approval). | 2018-04-20 10:00 | 2018-04-20 14:00 | 2018-04-26 16:08
CHG0030525 | DigiPlex Stockholm 1 AB | Emergency light fittings | Normal | Closed | 2018-04-30 07:42 | 2018-05-02 07:43 |  | 2018-07-11 14:12 | 2018-07-11 14:12 |  | 2018-07-11 | Approved |  | 2018-04-30 15:44 | 2018-07-04 15:44 | 2018-04-26 07:44
CHG0030524 | DigiPlex Norway AS | Electrical changeover and installation off new boards. | Normal | Closed | 2018-04-26 14:55 | 2018-06-22 14:55 |  | 2018-09-03 11:35 | 2018-09-03 11:35 |  |  | Approved | 26.04.2018 10:49:41 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-08 08:14 | 2018-06-14 08:29 | 2018-04-25 14:58
CHG0030523 | DigiPlex Stockholm 1 AB | DH7.2 BMS Signal and system testing for sign off. | Normal | Closed | 2018-05-02 14:32 | 2018-05-04 14:32 |  | 2018-07-11 14:22 | 2018-07-11 14:22 |  | 2018-07-11 | Approved |  | 2018-05-02 15:51 | 2018-05-04 15:51 | 2018-04-25 14:33
CHG0030521 | DigiPlex Rosenholm AS | Sjekk av generator etter funn under service | Normal | Closed | 2018-04-26 08:23 | 2018-04-26 08:23 |  | 2018-06-13 10:06 | 2018-06-13 10:06 |  |  | Approved | 25.04.2018 08:44:23 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-04-26 08:29 | 2018-04-26 08:29 | 2018-04-25 08:23
CHG0030520 | DigiPlex Stockholm 1 AB | Connection and integrity testing | Normal | Closed | 2018-04-24 18:20 | 2018-05-08 18:20 |  | 2018-07-11 14:04 | 2018-07-11 14:04 |  |  | Approved |  | 2018-04-24 15:48 | 2018-05-08 15:48 | 2018-04-24 18:22
CHG0030519 | DigiPlex Stockholm 1 AB | Remove the tap off units on to the A + B string | Normal | Closed | 2018-04-25 17:16 | 2018-04-25 17:16 |  | 2018-07-04 11:50 | 2018-07-04 11:50 |  |  | Approved |  | 2018-04-25 15:55 | 2018-04-25 15:55 | 2018-04-24 17:16
CHG0030517 | DigiPlex Rosenholm AS | Test av redundanse i DP rack i CCRA | Normal | Closed | 2018-05-07 09:00 | 2018-05-07 09:15 |  | 2018-06-13 10:09 | 2018-05-09 10:39 |  |  | Approved | 25.04.2018 08:19:03 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-07 10:13 | 2018-05-07 10:13 | 2018-04-24 15:32
CHG0030516 | DigiPlex Rosenholm AS | Omkobling av switcher i PLT06 og PLT04 | Normal | Closed | 2018-05-02 15:08 | 2018-05-25 15:08 |  | 2018-06-13 10:09 | 2018-06-13 10:06 |  |  | Approved | 25.04.2018 08:23:31 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-02 08:29 | 2018-05-25 08:29 | 2018-04-24 15:09
CHG0030515 | DigiPlex Rosenholm AS | Shutdown of A and B side of H3 Shortbreak board | Normal | Closed | 2018-05-03 08:00 | 2018-05-03 16:00 |  | 2018-06-13 10:09 | 2018-05-09 10:39 |  |  | Approved | 25.04.2018 08:39:05 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-03 10:11 | 2018-05-03 10:11 | 2018-04-24 14:03
CHG0030514 | DigiPlex Rosenholm AS | Midletidig bytte av tilførsel for sluse | Normal | Closed | 2018-04-25 08:00 | 2018-05-15 16:00 |  | 2018-11-12 07:26 | 2018-11-12 07:26 |  |  | Approved | 24.04.2018 13:57:29 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-24 10:18 | 2018-11-01 10:19 | 2018-04-24 13:49
CHG0030512 | DigiPlex Rosenholm AS | Ny feed til 2 etg R02-MOD 01 Shortbreak | Normal | Closed | 2018-05-03 08:00 | 2018-05-03 16:00 |  | 2018-06-13 10:09 | 2018-05-09 10:38 |  |  | Approved | 24.04.2018 12:27:23 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-03 10:10 | 2018-05-03 10:10 | 2018-04-24 11:44
CHG0030511 | DigiPlex Rosenholm AS | Ny feed til 2 etg R02-MOD 01 Critical B | Normal | Closed | 2018-05-24 20:00 | 2018-05-25 16:00 |  | 2018-08-01 13:21 | 2018-08-01 13:21 |  | 2018-04-26 | Approved | 24.04.2018 12:20:27 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-24 08:28 | 2018-05-25 08:28 | 2018-04-24 11:36
CHG0030510 | DigiPlex Rosenholm AS | Ny feed til 2.etg R02MOD01 Critical A og flytte tapoff for MOD06 | Normal | Closed | 2018-05-22 07:00 | 2018-05-25 16:00 |  | 2018-06-13 10:10 | 2018-06-13 10:10 |  | 2018-04-26 | Approved | 24.04.2018 12:17:44 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-22 08:28 | 2018-05-23 08:28 | 2018-04-24 11:34
CHG0030509 | DigiPlex Rosenholm AS | BMS service access | Normal | Closed | 2018-04-24 10:50 | 2018-05-04 18:00 |  | 2018-06-26 11:40 | 2018-06-26 11:40 | Patrick Bakke |  | Approved | 24.04.2018 11:08:59 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-04-24 10:50
CHG0030507 | DigiPlex Norway AS | BMS service access | Normal | Closed | 2018-04-30 07:00 | 2018-05-04 18:00 |  | 2018-06-13 10:26 | 2018-06-13 10:26 | Patrick Bakke |  | Approved | 24.04.2018 11:08:33 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). |  | 2018-05-04 09:29 | 2018-04-24 10:24
CHG0030504 | DigiPlex Norway AS | Schneider works with installing UPS. | Normal | Closed | 2018-04-23 14:48 | 2018-09-01 14:48 |  | 2018-10-11 15:35 | 2018-10-11 15:35 |  | 2018-10-11 | Approved | 23.04.2018 08:49:16 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-23 17:22 | 2018-07-30 17:22 | 2018-04-20 14:52
CHG0030503 | DigiPlex Norway AS | New pipe installation and connection of 2 new CCU’s. | Normal | Closed | 2018-04-23 09:37 | 2018-06-29 09:37 |  | 2018-09-15 09:48 | 2018-09-15 09:48 |  |  | Approved | 23.04.2018 07:50:13 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-29 13:02 | 2018-06-26 13:02 | 2018-04-20 09:41
CHG0030501 | DigiPlex Stockholm 1 AB | Refurbishment of loading bay area | Normal | Closed | 2018-04-23 17:13 | 2018-06-21 17:13 |  | 2018-09-28 10:44 | 2018-09-28 10:44 |  |  | Approved |  | 2018-04-19 17:23 | 2018-09-10 16:29 | 2018-04-19 17:23
CHG0030500 | DigiPlex Norway AS | 8114 - Removal of redundant freecoolers on the roof | Normal | Closed | 2018-04-23 08:00 | 2018-04-27 15:24 |  | 2018-05-24 08:43 | 2018-05-24 08:43 |  | 2018-04-20 | Approved | 20.04.2018 12:38:34 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-04-23 14:53 | 2018-04-27 14:53 | 2018-04-19 15:24
CHG0030499 | DigiPlex Fet AS |  | Normal | Canceled |  |  |  | 2018-04-24 12:41 |  |  |  | Requested |  |  |  | 2018-04-19 14:00
CHG0030498 | DigiPlex Stockholm 1 AB | Relocation of fire aspiration panel in DH7.1 | Normal | Closed | 2018-04-24 11:26 | 2018-04-26 11:26 |  | 2018-07-04 11:50 | 2018-07-04 11:50 |  |  | Approved |  | 2018-06-25 07:55 | 2018-06-26 07:55 | 2018-04-19 11:28
CHG0030497 | DigiPlex Stockholm 1 AB | Commisioing of process water system | Normal | Canceled | 2018-04-23 11:22 | 2018-04-30 11:22 |  | 2018-05-24 15:16 |  |  |  | Requested | 09.05.2018 12:49:01 - ceghult (Approval history) Christian Eghult rejected the task. Approval comments: 09.05.2018 12:49:00 - Christian Eghult (Comments) See earlier comments 09.05.2018 12:06:01 - Christian Eghult (Comments) MOP steps 7,8 and 9 requires the leaf filter to have been installed 23.04.2018 12:09:27 - Christian Eghult (Comments) 1. A Digiplex assigned technical authority has to be available for verification and monitoring of the commissioning procedure. Please specify who. 2. Please upload a copy of the commissioning protocol. 3. The water has been standing stagnant and may present both technical and H&S issues. Please include visual inspection for debris in the tanks and present prof of when the water quality has been approved and tanks cleaned as a prerequisite for the work. 4. Steps to ensure that the Munters unit have water pressure at all times needs to be included. We allow running on a single feed but the manual circuit selection valves to each unit has to be set properly at each test and restored when the tests are concluded. Affected units: DH1 1-6, DH7.1 1-4, DH7.2 5-8, DH6 1-6. 5. Level indications and alarm functions for each tank needs to be proven. |  |  | 2018-04-19 11:22
CHG0030496 | DigiPlex Norway AS | Elcor works with installing UPS. | Normal | Closed | 2018-04-23 10:22 | 2018-07-27 10:22 |  | 2018-10-11 15:35 | 2018-10-11 15:35 |  | 2018-10-11 | Approved | 23.04.2018 09:30:31 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-24 17:17 | 2018-07-27 17:17 | 2018-04-19 10:31
CHG0030495 | DigiPlex Norway AS | Test of UPS B resilience during loss of CW | Normal | Closed | 2018-04-19 08:00 | 2018-04-19 16:00 |  | 2018-04-25 15:26 | 2018-04-25 15:26 |  |  | Approved | 18.04.2018 14:53:22 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). |  |  | 2018-04-18 14:15
CHG0030493 | DigiPlex Rosenholm AS | Turn OFF Critical B-side power string for L2E project - connected to CHG0030511 | Normal | Closed | 2018-05-24 20:00 | 2018-05-25 06:00 |  | 2018-07-25 11:37 | 2018-07-25 11:37 |  | 2018-04-26 | Approved | 24.04.2018 12:49:50 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). | 2018-05-24 08:27 | 2018-05-25 08:27 | 2018-04-17 12:17
CHG0030491 | DigiPlex Stockholm 1 AB | To install the ACO drain section in the East yard | Normal | Closed | 2018-04-17 09:49 | 2018-05-01 09:49 |  | 2018-06-07 13:45 | 2018-06-07 13:45 |  |  | Approved |  | 2018-04-22 11:17 | 2018-05-23 11:18 | 2018-04-17 09:51
CHG0030489 | DigiPlex Norway AS | Crane lifting of scrapped equipment | Normal | Closed | 2018-04-17 14:34 | 2018-05-11 14:34 |  | 2018-06-07 07:28 | 2018-06-07 07:28 |  |  | Approved | 17.04.2018 10:09:43 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-23 07:49 | 2018-04-27 07:50 | 2018-04-16 14:38
CHG0030486 | DigiPlex Norway AS | Reactive repair after monthly check of emergency lighting, DNAS | Normal | Closed | 2018-04-16 08:00 | 2018-05-04 16:00 |  | 2018-05-09 10:30 | 2018-05-09 10:30 |  |  | Approved | 16.04.2018 10:57:04 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-16 13:14 | 2018-05-04 13:14 | 2018-04-13 12:10
CHG0030485 | DigiPlex Norway AS | Access ifbm modulvask | Normal | Closed | 2018-04-17 09:02 | 2018-04-17 16:00 |  | 2018-04-25 15:26 | 2018-04-25 15:26 |  |  | Approved | 16.04.2018 13:52:38 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-17 10:00 | 2018-04-17 13:40 | 2018-04-13 08:50
CHG0030483 | DigiPlex Rosenholm AS | Turn OFF Critical A-side power string for L2E project - connected to CHG0030510 | Normal | Closed | 2018-05-22 20:00 | 2018-05-23 06:00 |  | 2018-06-13 10:09 | 2018-05-25 14:04 | Anders Lundin Bjørnstad | 2018-04-26 | Approved | 24.04.2018 12:48:44 - julfsryggen (Approval history) Group approval for Change-Technical assess group approved by user Jonny Ulfsryggen (Technical approvals norway). 13.04.2018 08:35:00 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-22 18:00 |  | 2018-04-13 00:09
CHG0030482 | DigiPlex Norway AS | 02MOD02, removing old Busbar leading up to 03 floor. | Normal | Closed | 2018-04-30 13:32 | 2018-05-04 13:32 |  | 2018-06-16 15:22 | 2018-06-16 15:22 |  |  | Approved | 23.04.2018 09:32:44 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-13 08:58 | 2018-05-18 08:58 | 2018-04-12 13:33
CHG0030481 | DigiPlex Norway AS | Changeover 02MOD08 CY to DY. | Normal | Closed | 2018-04-13 13:14 | 2018-04-27 13:14 |  | 2018-06-07 07:28 | 2018-06-07 07:28 |  |  | Approved | 23.04.2018 09:35:35 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-05-01 08:35 | 2018-05-09 08:35 | 2018-04-12 13:16
CHG0030480 | DigiPlex Rosenholm AS | Installasjon av 2 stk brytere i tavle H3 short break, Tillkobling av nye stigere til +R02-Mod 01 | Normal | Canceled | 2018-05-04 07:00 | 2018-05-04 16:00 |  | 2018-04-24 12:38 |  |  |  | Requested |  |  |  | 2018-04-10 15:34
CHG0030479 | DigiPlex Rosenholm AS | Montere ny tap off på 3200A bus bar +R1=494.05-ks02, Tilkobling av nye tilførsler på 1000A tap off til +R02.MOD 01 | Normal | Canceled | 2018-06-06 07:00 | 2018-06-07 15:00 |  | 2018-04-24 12:38 |  |  |  | Requested |  |  |  | 2018-04-10 15:18
CHG0030478 | DigiPlex Norway AS | Pump room composition of pump 1-2 and 3 | Normal | Closed | 2018-04-11 08:00 | 2018-04-30 16:00 |  | 2018-08-16 09:19 | 2018-08-16 09:19 |  |  | Approved | 10.04.2018 14:09:48 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-10 14:12 | 2018-07-06 14:13 | 2018-04-10 13:58
CHG0030477 | DigiPlex Rosenholm AS | Stanley sjekker muligheten for å opprette alarmpunkt på gitterdør i PLT08 | Normal | Closed | 2018-04-16 13:46 | 2018-04-17 13:47 |  | 2018-05-09 10:29 | 2018-05-09 10:29 |  |  | Approved | 13.04.2018 08:36:13 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-30 10:12 | 2018-04-30 10:12 | 2018-04-10 13:47
CHG0030476 | DigiPlex Norway AS | Connecting 1 CCU. | Normal | Closed | 2018-04-11 13:38 | 2018-04-13 13:38 |  | 2018-05-07 17:37 | 2018-05-07 17:37 |  | 2018-04-27 | Approved | 10.04.2018 14:04:42 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-04-11 21:10 | 2018-04-12 21:10 | 2018-04-10 13:41
CHG0030475 | DigiPlex Norway AS | Refurbishment of -01MOD08.4 | Normal | Closed | 2018-04-11 13:28 | 2018-05-31 13:28 |  | 2018-06-28 10:54 | 2018-06-28 10:54 |  |  | Approved | 10.04.2018 14:05:09 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-04-04 10:33 | 2018-06-08 10:33 | 2018-04-10 13:30
CHG0030474 | DigiPlex Rosenholm AS | No break A: Flytte tap off +R1(MOD06)=494.05-QE0601, Fra +R1=494.05-KS01, Til +R1=494.06-KS01, Montere ny 1000A tap off på 3200A, Tilkobling av nye tilførsler | Normal | Canceled | 2018-05-03 07:00 | 2018-05-03 16:00 |  | 2018-04-24 12:37 |  |  |  | Rejected | 10.04.2018 14:50:20 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). |  |  | 2018-04-10 11:52
CHG0030471 | DigiPlex Stockholm 1 AB | Dismantle of old duct work in loading bay area during contruction | Normal | Closed | 2018-04-05 20:14 | 2018-04-06 20:14 |  | 2018-06-07 13:45 | 2018-06-07 13:45 |  |  | Approved |  | 2018-04-09 14:44 | 2018-04-09 14:43 | 2018-04-04 20:31
CHG0030470 | DigiPlex Rosenholm AS | AVA bytter kabel etter diesel lekkasjer | Normal | Closed | 2018-04-05 08:26 | 2018-04-26 08:26 |  | 2018-04-13 10:38 | 2018-04-13 10:38 | Halvor Bjerke | 2018-04-13 | Approved | 04.04.2018 08:42:09 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-05 10:44 | 2018-04-06 09:35 | 2018-04-04 08:26
CHG0030469 | DigiPlex Norway AS | Balance ventialtion in all modules | Normal | Closed | 2018-04-04 08:00 | 2018-04-06 16:00 |  | 2018-05-24 08:39 | 2018-05-24 08:39 |  |  | Approved | 04.04.2018 08:30:08 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-03 14:54 | 2018-05-16 14:55 | 2018-04-03 21:01
CHG0030468 | DigiPlex Norway AS | Install Cold aisle containment for 00MOD04.1 | Normal | Closed | 2018-04-05 08:00 | 2018-04-27 15:51 |  | 2018-07-10 10:07 | 2018-07-10 10:07 |  |  | Approved | 04.04.2018 08:26:30 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-06-11 18:04 | 2018-06-29 18:05 | 2018-04-03 15:47
CHG0030466 | DigiPlex Norway AS | Installing Rig area for Level 3 | Normal | Closed | 2018-04-04 08:00 | 2018-04-09 16:00 |  | 2018-04-25 15:27 | 2018-04-25 15:27 |  |  | Approved | 03.04.2018 12:18:05 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-04-03 10:04 | 2018-04-05 10:04 | 2018-04-03 11:55
CHG0030465 | DigiPlex Rosenholm AS | 4M service på CCUer | Normal | Closed | 2018-04-16 09:33 | 2018-04-27 09:33 |  | 2018-04-25 15:28 | 2018-04-25 15:28 |  |  | Approved | 03.04.2018 09:55:10 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-16 09:57 | 2018-04-20 13:20 | 2018-04-03 09:34
CHG0030464 | DigiPlex Norway AS | To carry out commissioning of BMS -01Mod09 and 02Mod08. | Normal | Closed | 2018-04-03 09:00 | 2018-04-20 16:21 |  | 2018-05-07 17:36 | 2018-05-07 17:36 |  | 2018-04-27 | Approved | 03.04.2018 09:10:37 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-03 21:26 | 2018-04-10 21:26 | 2018-04-03 08:25
CHG0030463 | DigiPlex Stockholm 1 AB | Electrical instalaltion for DH7.1.4 and DH7.1.7 | Normal | Closed | 2018-04-09 08:51 | 2018-05-11 08:51 |  | 2018-07-04 11:49 | 2018-07-04 11:49 |  |  | Approved |  | 2018-04-09 15:52 | 2018-05-25 15:53 | 2018-03-29 08:52
CHG0030462 | DigiPlex Norway AS | Pipeworks and connection new ccu. | Normal | Canceled |  |  |  | 2018-09-03 12:42 |  |  |  | Rejected | 03.05.2018 09:17:03 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). |  |  | 2018-03-27 13:23
CHG0030461 | DigiPlex Norway AS | Disconnecting all electrical, BMS and VVS installation in strip out area in 3 floor. | Normal | Closed | 2018-04-02 07:44 | 2018-04-27 13:44 |  | 2018-09-20 09:06 | 2018-09-20 09:06 |  |  | Approved | 04.04.2018 08:52:35 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-27 08:36 | 2018-05-31 08:36 | 2018-03-26 13:47
CHG0030459 | DigiPlex Norway AS | Test of service portal catalog item | Normal | Canceled |  |  |  | 2018-03-24 10:39 |  |  |  | Requested |  |  |  | 2018-03-24 10:38
CHG0030458 | DigiPlex Norway AS | Install kitchen in reception area, DNAS | Normal | Closed | 2018-03-27 14:21 | 2018-04-06 14:21 |  | 2018-05-09 10:28 | 2018-05-09 10:28 |  |  | Approved | 03.04.2018 12:20:29 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-04-03 13:13 | 2018-05-08 13:13 | 2018-03-23 08:46
CHG0030456 | DigiPlex Norway AS | Lifting Operations Radiator, Vent house and Genset. | Normal | Closed | 2018-03-23 06:47 | 2018-03-23 16:47 |  | 2018-05-07 15:44 | 2018-05-07 15:44 |  | 2018-04-27 | Approved | 22.03.2018 06:55:25 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-03-23 21:15 | 2018-03-23 21:15 | 2018-03-22 06:48
CHG0030454 | DigiPlex Norway AS | Disconnection generator A and equipment in UPS room A | Normal | Closed | 2018-03-22 13:38 | 2018-04-13 13:38 |  | 2018-05-07 15:43 | 2018-05-07 15:43 |  | 2018-04-27 | Approved | 21.03.2018 14:22:30 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-21 14:05 | 2018-03-28 14:07 | 2018-03-20 19:51
CHG0030448 | DigiPlex Stockholm 1 AB | Move beacon inside DH1A | Emergency | Closed | 2018-03-21 13:19 | 2018-03-22 13:20 |  | 2018-04-30 15:03 | 2018-04-30 15:03 | Christian Eghult |  | Approved | 30.04.2018 15:02:58 - ceghult (Approval history) Group approval for CAB Approval approved by user Christian Eghult (eCAB approval). 20.03.2018 15:17:00 - aolsen (Approval history) Group approval for eCAB Approval approved by user Alexander Olsen (eCAB approval). | 2018-03-25 13:00 | 2018-03-25 11:14 | 2018-03-20 13:21
CHG0030441 | DigiPlex Rosenholm AS | Service på generatorer | Normal | Closed | 2018-04-03 09:21 | 2018-04-06 09:21 |  | 2018-04-20 09:32 | 2018-04-20 09:32 |  | 2018-04-20 | Approved | 20.03.2018 14:47:27 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-04-03 10:44 |  | 2018-03-20 09:22
CHG0030440 | DigiPlex Norway AS | Cobber cabling from 03OFF01 to 00Mod05 | Normal | Closed | 2018-03-21 13:47 | 2018-03-28 13:47 |  | 2018-03-23 09:14 | 2018-03-23 09:14 |  | 2018-03-23 | Approved | 20.03.2018 14:55:20 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-21 07:55 | 2018-03-22 07:56 | 2018-03-19 13:50
CHG0030437 | DigiPlex Norway AS |  | Normal | Canceled |  |  |  | 2018-03-20 09:58 |  |  |  | Not Yet Requested |  |  |  | 2018-03-19 13:22
CHG0030436 | DigiPlex Norway AS |  | Normal | Canceled |  |  |  | 2018-03-20 09:58 |  |  |  | Not Yet Requested |  |  |  | 2018-03-19 13:21
CHG0030435 | DigiPlex Norway AS | Changing Output Capacitors in UPS's in E and F. | Normal | Closed | 2018-03-20 08:00 | 2018-03-21 16:00 |  | 2018-07-16 14:10 | 2018-07-16 14:10 | Geir Almquist |  | Approved | 19.03.2018 13:43:30 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-20 14:08 | 2018-03-21 14:08 | 2018-03-19 13:05
CHG0030430 | DigiPlex Rosenholm AS | Ombygging av R02 | Normal | Closed | 2018-03-19 07:00 | 2018-07-31 17:00 |  | 2018-06-13 10:09 | 2018-06-13 10:09 |  |  | Approved | 16.03.2018 12:54:18 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-03-19 08:27 | 2018-06-07 08:27 | 2018-03-16 12:30
CHG0030428 | DigiPlex Norway AS | Control of gas damper, strobe and alarm bell in the module. Test number 4 of fire alarm is delayed until 2018 because the bottles have been replaced. | Normal | Closed | 2018-03-21 12:42 | 2018-03-22 12:42 |  | 2018-03-23 09:11 | 2018-03-23 09:11 |  | 2018-03-23 | Approved | 16.03.2018 12:53:04 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-03-21 09:10 | 2018-03-22 09:10 | 2018-03-16 12:43
CHG0030426 | DigiPlex Rosenholm AS | GK fremføring av tilførsler til R02 | Normal | Closed | 2018-03-19 12:18 | 2018-06-01 12:18 |  | 2018-07-25 11:41 | 2018-07-25 11:41 |  |  | Approved | 16.03.2018 12:56:04 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-03-16 07:58 | 2018-07-24 07:59 | 2018-03-16 12:19
CHG0030424 | DigiPlex Norway AS | Strip out level 3 | Normal | Closed | 2018-03-19 10:07 | 2018-05-11 10:08 |  | 2018-08-23 09:22 | 2018-08-23 09:22 |  | 2018-03-16 | Approved | 22.03.2018 08:19:50 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-03-15 09:23 | 2018-06-29 16:00 | 2018-03-16 10:08
CHG0030423 | DigiPlex Stockholm 1 AB | Switch upgrade of Mini Pillars | Normal | Closed | 2018-03-23 09:00 | 2018-04-06 16:00 |  | 2018-08-31 08:00 | 2018-08-31 08:00 |  | 2018-03-16 | Approved | 20.03.2018 17:07:44 - nnystrom (Approval history) Group approval for Change-Technical assess group SE approved by user Niclas Nyström (Technical approvals sweden). | 2018-05-15 15:19 | 2018-06-03 15:19 | 2018-03-16 09:34
CHG0030422 | DigiPlex Norway AS | 3m service of Humidifiers, DNAS + Filter replacements AHUs, DNAS | Normal | Closed | 2018-03-19 08:00 | 2018-05-31 16:00 |  | 2018-06-28 10:57 | 2018-06-28 10:57 |  |  | Approved | 15.03.2018 14:05:03 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-03-15 08:28 | 2018-06-20 08:28 | 2018-03-15 13:55
CHG0030420 | DigiPlex Rosenholm AS | 12M sjekk av detektorer | Normal | Closed | 2018-04-04 12:10 | 2018-04-04 12:10 |  | 2018-04-20 09:31 | 2018-04-20 09:31 |  | 2018-04-20 | Approved | 15.03.2018 13:21:29 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-04-04 10:53 | 2018-04-04 10:53 | 2018-03-15 12:11
CHG0030419 | DigiPlex Norway AS | Monthly check of Emergency Lighting and General Lighting, DNAS | Normal | Closed | 2018-03-26 08:00 | 2018-03-28 16:00 |  | 2018-04-25 15:32 | 2018-04-25 15:32 |  |  | Approved | 15.03.2018 13:20:16 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-03-26 08:00 | 2018-03-28 16:00 | 2018-03-15 12:46
CHG0030418 | DigiPlex Norway AS | Pull back and move various cabels from 03OFF area | Normal | Closed | 2018-03-21 08:00 | 2018-03-23 16:00 |  | 2018-03-23 09:13 | 2018-03-23 09:13 |  | 2018-03-23 | Approved | 20.03.2018 14:54:17 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-21 09:10 | 2018-03-22 09:13 | 2018-03-14 12:47
CHG0030416 | DigiPlex Norway AS | Reloctae central humidifier lance to main ventilation raiser | Normal | Closed | 2018-03-18 08:00 | 2018-03-19 16:00 |  | 2018-03-23 09:09 | 2018-03-23 09:09 |  | 2018-03-16 | Approved | 16.03.2018 09:16:38 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-03-18 09:00 | 2018-03-18 12:00 | 2018-03-13 16:29
CHG0030415 | DigiPlex Norway AS | Craning new DX units on roof. | Normal | Closed | 2018-03-14 01:00 | 2018-03-23 01:00 |  | 2018-05-07 17:36 | 2018-05-07 17:36 |  | 2018-04-27 | Approved | 16.03.2018 09:15:52 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-03-20 21:17 | 2018-03-20 21:17 | 2018-03-13 10:43
CHG0030414 | DigiPlex Norway AS | Troubleshooting on Battery Charger in Generator Control Panel B | Normal | Closed | 2018-03-13 08:00 | 2018-03-13 16:00 |  | 2018-03-23 09:08 | 2018-03-23 09:08 |  | 2018-03-23 | Approved | 12.03.2018 09:17:20 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2018-03-13 08:00 | 2018-03-13 16:00 | 2018-03-12 08:59
CHG0030413 | DigiPlex Norway AS | Dismounting outside wall prior to genset removal. | Normal | Closed | 2018-03-12 13:21 | 2018-04-27 13:21 |  | 2018-06-07 07:29 | 2018-06-07 07:29 |  |  | Approved | 12.03.2018 14:13:06 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-19 08:38 | 2018-03-23 08:39 | 2018-03-11 20:10
CHG0030412 | DigiPlex Norway AS | Fans, Vent house, Ventilation damper and Radiator disconnection prior to removal. | Normal | Closed | 2018-03-12 13:11 | 2018-04-06 13:11 |  | 2018-05-07 17:38 | 2018-05-07 17:38 |  | 2018-04-27 | Approved | 12.03.2018 14:16:36 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-12 21:03 | 2018-03-28 21:04 | 2018-03-11 20:04
CHG0030411 | DigiPlex Norway AS | Engine preservation | Normal | Closed | 2018-03-12 13:10 | 2018-04-06 13:10 |  | 2018-05-07 15:55 | 2018-05-07 15:55 |  | 2018-04-27 | Approved | 12.03.2018 14:18:08 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-13 21:23 | 2018-03-29 21:24 | 2018-03-11 12:34
CHG0030410 | DigiPlex Norway AS | Genset disconnection | Normal | Closed | 2018-03-12 13:07 | 2018-04-06 13:08 |  | 2018-07-10 10:06 | 2018-07-10 10:06 |  |  | Approved | 12.03.2018 14:19:38 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-03-13 21:12 | 2018-04-03 21:13 | 2018-03-11 12:30
CHG0030409 | DigiPlex Norway AS | Install Cold aisle containment in00MOD05 | Normal | Closed | 2018-03-12 08:00 | 2018-03-30 16:00 |  | 2018-04-25 15:32 | 2018-04-25 15:32 |  | 2018-03-09 | Approved | 09.03.2018 10:10:02 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 09.03.2018 10:08:50 - pviken (Approval history) Pål Rune Viken approved the task. 09.03.2018 08:51:05 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-03-08 10:09 | 2018-04-06 10:09 | 2018-03-08 13:35
CHG0030406 | DigiPlex Norway AS | Disconnecting and removing 3 ccu's. | Normal | Closed | 2018-03-06 13:19 | 2018-03-30 13:19 |  | 2018-05-07 15:42 | 2018-05-07 15:42 |  | 2018-04-27 | Approved | 06.03.2018 14:31:11 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-03-12 21:30 | 2018-03-23 21:30 | 2018-03-06 10:03
CHG0030405 | DigiPlex Norway AS | Work/test 02MOD08 Installing and connecting new DX units. | Normal | Closed | 2018-03-06 13:00 | 2018-03-23 13:00 |  | 2018-05-07 13:57 | 2018-05-07 13:57 | Rolf Arne Storøy |  | Approved | 06.03.2018 14:31:10 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-03-08 21:20 | 2018-03-21 21:21 | 2018-03-06 09:56
CHG0030403 | DigiPlex Rosenholm AS | Haga Berg skal slipe gulv i R02 før sparkling av gulv. | Normal | Closed | 2018-02-23 09:52 | 2018-03-02 09:53 |  | 2018-03-16 09:09 | 2018-03-16 09:09 |  | 2018-03-16 | Approved | 22.02.2018 13:38:49 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-02-23 10:55 | 2018-02-25 10:55 | 2018-02-22 09:53
CHG0030402 | DigiPlex Norway AS | ServiceNow version upgrade to Kingston | Normal | Closed | 2018-02-26 15:00 | 2018-02-26 18:00 |  | 2018-03-12 13:50 | 2018-03-12 13:50 |  | 2018-03-09 | Approved | 26.02.2018 09:50:01 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-02-26 15:02 | 2018-02-26 17:02 | 2018-02-22 09:47
CHG0030401 | DigiPlex Norway AS | Moving load from A-string to E-string (critical) and C-string (short break) | Normal | Closed | 2018-02-22 14:30 | 2018-02-22 15:00 |  | 2018-03-09 09:15 | 2018-03-09 09:15 |  | 2018-03-09 | Approved | 21.02.2018 09:25:37 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-02-22 14:30 | 2018-02-23 12:30 | 2018-02-20 16:25
CHG0030400 | DigiPlex Fet AS | Annual service of UPS | Normal | Canceled | 2018-04-04 09:15 | 2018-04-10 09:15 |  | 2018-04-26 09:53 |  |  |  | Not Yet Requested |  |  |  | 2018-02-19 09:17
CHG0030399 | DigiPlex Fet AS | Annual service of gates. | Normal | Closed | 2018-02-18 08:04 | 2018-02-18 15:05 |  | 2018-04-25 15:33 | 2018-04-25 15:33 |  |  | Approved | 26.02.2018 09:54:24 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). |  |  | 2018-02-16 13:59
CHG0030397 | DigiPlex Norway AS | Yearly service of Galaksi 7000 | Normal | Closed | 2018-02-20 12:35 | 2018-02-27 12:35 |  | 2018-03-23 09:08 | 2018-03-23 09:08 |  | 2018-03-16 | Approved | 20.02.2018 12:35:35 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-02-20 09:07 | 2018-02-27 09:07 | 2018-02-15 13:50
CHG0030395 | DigiPlex Norway AS | Fiber cabling from CCR rooms to modules | Normal | Closed | 2018-02-19 09:38 | 2018-03-16 09:38 |  | 2018-05-07 10:42 | 2018-05-07 10:42 |  |  | Approved | 15.02.2018 09:49:15 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-02-20 08:00 | 2018-03-08 16:00 | 2018-02-14 09:45
CHG0030391 | DigiPlex Norway AS | Continual work of removing and relocationg temperature sensors in module | Normal | Canceled | 2018-02-19 12:27 | 2018-02-21 12:27 |  | 2018-05-07 10:42 |  |  |  | Approved | 12.02.2018 12:35:12 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). |  |  | 2018-02-12 12:28
CHG0030390 | DigiPlex Rosenholm AS | Steve C skal legge til alarm ved feil på befukteren. | Normal | Closed | 2018-02-13 07:00 | 2018-02-13 17:00 |  | 2018-02-16 09:33 | 2018-02-16 09:33 |  | 2018-02-16 | Approved | 12.02.2018 10:31:09 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-02-13 15:37 | 2018-02-13 15:37 | 2018-02-12 10:26
CHG0030389 | DigiPlex Norway AS | Moving critical load CSSB1B from CSSB1E to CS1B | Normal | Closed | 2018-02-14 14:30 | 2018-02-14 15:00 |  | 2018-02-16 09:21 | 2018-02-16 09:21 |  | 2018-02-16 | Approved | 09.02.2018 09:02:59 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-02-14 14:30 | 2018-02-14 15:00 | 2018-02-08 15:42
CHG0030388 | DigiPlex Norway AS | Install DX units to support customer demand | Normal | Closed | 2018-02-05 21:20 | 2018-03-01 21:20 |  | 2018-05-07 09:30 | 2018-05-07 09:30 |  | 2018-05-04 | Approved | 05.02.2018 08:49:05 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-03-06 08:46 | 2018-03-06 08:47 | 2018-02-02 14:45
CHG0030386 | DigiPlex Norway AS | Updating access control system AIMS to new Thor Guard | Normal | Closed | 2017-11-09 09:05 | 2018-02-28 09:05 |  | 2018-08-08 12:05 | 2018-08-08 09:31 | Ellen Cathrine Martinsen |  | Approved | 02.02.2018 09:18:58 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-11-09 09:07 | 2018-04-04 09:12 | 2018-02-02 08:19
CHG0030383 | DigiPlex Norway AS | Install synchronization on generators towards mains | Normal | Closed | 2018-02-08 09:46 | 2018-02-08 09:47 |  | 2018-02-16 09:37 | 2018-02-16 09:37 |  | 2018-02-16 | Approved | 01.02.2018 10:02:10 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-02-08 09:00 | 2018-02-08 16:00 | 2018-02-01 09:45
CHG0030382 | DigiPlex Norway AS | Access ifbm modulvask | Normal | Closed | 2018-02-06 10:00 | 2018-02-06 16:00 |  | 2018-02-14 13:37 | 2018-02-14 13:37 | Wenke Falkman |  | Approved | 02.02.2018 09:59:46 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-02-06 10:30 | 2018-02-06 16:00 | 2018-01-31 12:26
CHG0030381 | DigiPlex Rosenholm AS | 6M service av sluse | Normal | Closed | 2018-02-26 09:30 | 2018-02-26 09:30 |  | 2018-03-09 09:16 | 2018-03-09 09:16 |  | 2018-03-09 | Approved | 31.01.2018 09:39:08 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-02-19 09:02 | 2018-02-19 09:02 | 2018-01-31 09:31
CHG0030379 | DigiPlex Norway AS | Sjekk/rep av leak detection 02 MOD 07 | Normal | Closed | 2018-01-31 10:00 | 2018-01-31 16:00 |  | 2018-02-02 09:35 | 2018-02-02 09:35 |  | 2018-02-02 | Approved | 30.01.2018 15:47:59 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2018-01-31 12:00 | 2018-01-31 14:00 | 2018-01-30 14:50
CHG0030378 | DigiPlex Fet AS |  | Normal | Canceled |  |  |  | 2018-01-29 09:42 | 2018-01-29 09:42 | Tommy Solberg |  | Not Yet Requested |  |  |  | 2018-01-29 09:41
CHG0030377 | DigiPlex Fet AS | Connect emergency power generator for AM. | Normal | Canceled |  |  |  | 2018-02-01 09:36 | 2018-02-01 09:36 | Sondre Braathen |  | Not Yet Requested |  |  |  | 2018-01-29 09:39
CHG0030376 | DigiPlex Fet AS | Replace old Hafslund meter with new. | Normal | Closed | 2018-02-07 12:24 | 2018-02-07 12:24 | Dag Oscar Brækken | 2018-02-09 09:24 | 2018-02-09 09:24 |  | 2018-02-09 | Approved | 25.01.2018 12:26:52 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2018-01-25 12:24
CHG0030375 | DigiPlex Norway AS | 3M test av batterier | Normal | Closed | 2018-02-06 07:00 | 2018-02-07 17:00 |  | 2018-02-16 09:30 | 2018-02-16 09:30 |  | 2018-02-16 | Approved | 31.01.2018 10:04:02 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-02-06 13:55 | 2018-02-07 13:55 | 2018-01-23 15:52
CHG0030374 | DigiPlex Norway AS | Rebuild ventilation ducts in 04COR01 | Normal | Closed | 2018-01-25 10:55 | 2018-02-02 10:55 |  | 2018-02-16 09:14 | 2018-02-16 09:14 |  | 2018-02-16 | Approved | 23.01.2018 13:26:45 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-01-22 09:10 | 2018-01-25 16:00 | 2018-01-22 10:55
CHG0030372 | DigiPlex Norway AS | Diesel tank service and cleaning | Normal | Closed | 2018-01-25 09:21 | 2018-01-25 09:22 |  | 2018-02-16 09:22 | 2018-02-16 09:22 |  | 2018-02-16 | Approved | 02.02.2018 09:17:37 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). 26.01.2018 09:40:57 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2018-01-25 08:00 | 2018-01-26 16:00 | 2018-01-22 09:24
CHG0030370 | DigiPlex Rosenholm AS | Diesel tank service and cleaning | Normal | Closed | 2018-01-23 08:00 | 2018-01-24 16:00 |  | 2018-01-26 09:30 | 2018-01-26 09:24 |  | 2018-01-26 | Approved | 18.01.2018 13:06:39 - albjornstad (Approval history) Group approval for Change-Technical assess group approved by user Anders Lundin Bjørnstad (Technical approvals norway). | 2018-01-23 08:23 | 2018-01-24 15:23 | 2018-01-18 12:57
CHG0030369 | DigiPlex Rosenholm AS | Sjekk/rep av leak detection MOD06 | Normal | Closed | 2018-01-22 07:00 | 2018-01-22 17:00 |  | 2018-02-02 09:33 | 2018-02-02 09:33 |  | 2018-02-02 | Approved | 17.01.2018 13:23:29 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-01-23 15:24 | 2018-01-23 15:24 | 2018-01-17 12:50
CHG0030363 | DigiPlex Norway AS | Antistatisk vask av 1 modul | Normal | Closed | 2018-01-23 15:00 | 2018-01-23 15:00 |  | 2018-01-26 09:21 | 2018-01-26 09:21 |  |  | Approved | 17.01.2018 13:20:10 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-01-23 08:00 | 2018-01-23 12:00 | 2018-01-15 15:01
CHG0030360 | DigiPlex Norway AS | Heat load test -01MOD08.1 | Normal | Closed | 2018-01-12 11:30 | 2018-01-12 16:00 |  | 2018-01-19 10:35 | 2018-01-19 10:35 |  | 2018-01-19 | Approved | 12.01.2018 11:33:36 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-01-14 09:33 | 2018-01-14 16:34 | 2018-01-12 09:47
CHG0030359 | DigiPlex Rosenholm AS | 3M test av batterier | Normal | Closed | 2018-02-05 07:00 | 2018-02-05 16:00 |  | 2018-02-19 07:30 | 2018-02-19 07:30 |  | 2018-02-16 | Approved | 12.01.2018 13:12:13 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). 12.01.2018 09:54:26 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2018-02-05 08:13 | 2018-02-05 08:14 | 2018-01-12 08:59
CHG0030358 | DigiPlex Norway AS | Install remote control of mains breaker | Normal | Closed | 2018-01-17 09:01 | 2018-03-16 15:33 |  | 2018-06-28 09:09 | 2018-06-28 09:09 |  | 2018-06-28 | Approved | 12.01.2018 09:53:03 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2018-01-14 14:02 | 2018-06-14 14:02 | 2018-01-11 17:32
CHG0030353 | DigiPlex Norway AS | Antistatisk vask av 3 moduler | Normal | Closed | 2018-01-16 08:00 | 2018-01-17 16:00 |  | 2018-01-26 09:21 | 2018-01-26 09:21 |  |  | Approved | 11.01.2018 11:50:48 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-01-16 08:00 | 2018-01-17 17:00 | 2018-01-11 11:46
CHG0030352 | DigiPlex Rosenholm AS | Antistatisk vask av R01MOD08 | Normal | Closed | 2018-01-16 07:00 | 2018-01-16 16:00 |  | 2018-01-19 10:37 | 2018-01-19 10:37 |  | 2018-01-12 | Approved | 11.01.2018 09:57:06 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-01-16 07:00 | 2018-01-16 16:00 | 2018-01-10 15:07
CHG0030347 | DigiPlex Norway AS | Heatload test -01MOD01.2 | Normal | Closed | 2018-01-11 09:33 | 2018-01-11 09:33 |  | 2018-01-19 10:32 | 2018-01-19 10:32 |  |  | Approved | 12.01.2018 10:28:12 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). 10.01.2018 09:40:07 - aolsen (Approval history) Group approval for Change-Technical assess group approved by user Alexander Olsen (Technical approvals norway). | 2018-01-12 09:00 | 2018-01-12 16:00 | 2018-01-10 09:34
CHG0030346 | DigiPlex Fet AS | Installation of G7 generator, electrical distribution | Normal | Closed | 2018-02-05 12:13 | 2018-02-06 12:13 |  | 2018-06-11 22:45 | 2018-06-11 22:45 |  |  | Approved | 22.01.2018 06:21:19 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). |  |  | 2018-01-08 09:21
CHG0030345 | DigiPlex Stockholm 1 AB | Connect Colt network link DS1 - DNAS | Normal | Closed | 2018-01-11 14:00 | 2018-01-11 16:00 |  | 2018-08-16 11:22 | 2018-08-16 11:22 |  | 2018-08-16 | Approved | 04.01.2018 23:41:09 - nnystrom (Approval history) Group approval for Change-Technical assess group SE approved by user Niclas Nyström (Technical approvals sweden). | 2018-04-30 11:22 | 2018-04-30 11:22 | 2018-01-04 23:26
CHG0030344 | DigiPlex Fet AS | DFAS Firewall upgrade | Normal | Closed | 2018-01-11 09:30 | 2018-01-11 13:00 |  | 2018-01-19 09:13 | 2018-01-19 09:13 |  | 2018-01-05 | Approved | 05.01.2018 09:43:23 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2018-01-11 09:09 | 2018-01-12 16:00 | 2018-01-04 23:17
CHG0030343 | DigiPlex Fet AS | Connect fiberlink (Eidsiva) DFAS - DNAS. | Normal | Canceled | 2018-01-11 09:00 | 2018-01-11 16:00 |  | 2018-09-13 09:28 |  |  | 2018-01-05 | Approved | 05.01.2018 09:44:04 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). |  |  | 2018-01-04 22:58
CHG0030342 | DigiPlex Norway AS | Fiber cabling from CCR rooms to modules | Normal | Closed | 2018-01-04 08:00 | 2018-02-09 15:00 |  | 2018-02-16 09:23 | 2018-02-16 09:23 |  | 2018-02-16 | Approved | 04.01.2018 10:30:44 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2018-01-03 08:17 | 2018-02-02 08:16 | 2018-01-02 15:29
CHG0030340 | DigiPlex Norway AS | Test by AVA of moduls at Ulven | Normal | Closed | 2017-12-21 08:00 | 2017-12-22 16:00 |  | 2018-01-26 09:36 | 2018-01-26 09:31 | Geir Almquist | 2018-01-26 | Approved | 20.12.2017 11:20:29 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-12-21 09:30 | 2017-12-22 09:31 | 2017-12-20 11:19
CHG0030339 | DigiPlex Fet AS | INC0011230 - Broken fan in A1-1 | Normal | Canceled |  |  |  | 2018-02-01 09:36 | 2018-02-01 09:36 | Sondre Braathen |  | Rejected | 21.12.2017 09:30:57 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). |  |  | 2017-12-20 09:00
CHG0030338 | DigiPlex Fet AS | PRB0040027 - Testing cooling solution | Normal | Canceled | 2017-12-20 08:43 | 2017-12-20 08:43 |  | 2018-02-01 09:35 | 2018-02-01 09:35 | Sondre Braathen |  | Approved | 20.12.2017 10:35:27 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2017-12-20 09:30 |  | 2017-12-20 08:43
CHG0030331 | DigiPlex Rosenholm AS | 12M Test av leak detection | Normal | Closed | 2018-01-08 07:00 | 2018-01-09 17:00 |  | 2018-01-12 10:45 | 2018-01-12 10:45 |  | 2018-01-12 | Approved | 19.12.2017 13:30:47 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-01-04 09:37 | 2018-01-05 09:37 | 2017-12-18 15:07
CHG0030326 | DigiPlex Fet AS | Enter your description here | Normal | Canceled | 2017-12-18 12:27 | 2017-12-20 12:28 |  | 2018-02-13 12:29 | 2018-01-10 16:45 |  |  | Not Yet Requested |  |  |  | 2017-12-15 12:23
CHG0030321 | DigiPlex Norway AS | Secure cage installation | Normal | Closed | 2018-01-02 08:34 | 2018-01-05 08:34 |  | 2018-01-12 10:54 | 2018-01-12 10:54 |  | 2018-01-12 | Approved | 19.12.2017 13:20:49 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2018-01-03 10:47 | 2018-01-10 10:47 | 2017-12-15 08:39
CHG0030315 | DigiPlex Norway AS | Wrong settings on breaker in module. | Emergency | Closed | 2017-12-14 10:00 | 2017-12-14 12:00 |  | 2017-12-15 09:55 | 2017-12-14 13:07 | Alexander Olsen | 2017-12-15 | Approved | 14.12.2017 12:07:11 - galmquist (Approval history) Group approval for eCAB Approval approved by user Geir Almquist (CAB approval). | 2017-12-14 13:07 | 2017-12-14 13:07 | 2017-12-13 16:10
CHG0030314 | DigiPlex Fet AS | PRB0040027 structured cabling | Normal | Canceled | 2018-01-05 11:57 | 2018-02-01 11:57 |  | 2018-02-01 09:36 | 2018-02-01 09:36 | Sondre Braathen |  | Not Yet Requested |  |  |  | 2017-12-12 14:44
CHG0030313 | DigiPlex Fet AS | PRB0040027 Cooling solution | Normal | Canceled | 2017-12-11 14:37 | 2017-12-21 14:38 |  | 2018-02-01 09:36 | 2018-02-01 09:36 | Sondre Braathen |  | Not Yet Requested |  | 2017-12-10 14:38 |  | 2017-12-12 14:38
CHG0030300 | DigiPlex Norway AS | Reclassification of gas suppression in 00PLT02 | Normal | Closed | 2018-02-26 07:00 | 2018-02-28 17:00 |  | 2018-04-16 08:43 | 2018-04-16 08:43 |  | 2017-12-15 | Approved | 14.12.2017 12:14:04 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2017-12-18 09:00 |  | 2017-12-07 13:58
CHG0030296 | DigiPlex Rosenholm AS | Schneider replace one defect battery | Normal | Closed | 2017-12-11 07:00 | 2017-12-11 16:00 |  | 2017-12-15 09:13 | 2017-12-15 09:13 | Halvor Bjerke | 2017-12-15 | Approved | 06.12.2017 10:31:25 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-12-11 08:53 | 2017-12-11 08:54 | 2017-12-06 08:18
CHG0030291 | DigiPlex Norway AS | Annual maintenance on all cameras at Digiplex Ulven | Normal | Closed | 2017-12-11 08:00 | 2017-12-15 16:00 |  | 2018-02-13 12:29 | 2017-12-22 09:01 | Alexander Olsen |  | Approved | 06.12.2017 09:49:12 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2017-12-18 09:00 |  | 2017-12-05 12:00
CHG0030288 | DigiPlex Norway AS | Install gas dampers in 00MOD01.1, 1.4 and 1.6. | Normal | Closed | 2017-12-13 10:47 | 2017-12-13 10:47 |  | 2017-12-22 11:06 | 2017-12-22 11:06 |  | 2017-12-15 | Approved | 15.12.2017 09:28:14 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). 04.12.2017 11:05:01 - fekay (Approval history) Group approval for Change-Technical assess group rejected by user Frode Elden Kay (Technical approvals norway). | 2017-12-13 09:27 | 2017-12-13 09:27 | 2017-12-04 10:47
CHG0030278 | DigiPlex Fet AS | DFAS 24/7 on site watch | Normal | Closed | 2017-12-01 14:00 | 2017-12-08 09:28 | Tommy Solberg | 2018-01-12 10:50 | 2018-01-12 10:50 |  | 2018-01-12 | Approved | 01.12.2017 10:48:47 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals norway). | 2017-12-01 09:31 | 2017-12-21 08:00 | 2017-12-01 10:11
CHG0030275 | DigiPlex Fet AS | Health check on copper wiring. A2-1, A and B side. | Normal | Closed | 2017-11-29 08:39 | 2017-11-29 08:40 |  | 2017-12-15 09:40 | 2017-12-15 09:40 | Halvor Bjerke | 2017-12-15 | Approved | 29.11.2017 08:50:32 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). | 2017-11-29 08:45 | 2017-11-29 10:16 | 2017-11-29 08:38
CHG0030273 | DigiPlex Norway AS | Reclassification of gas suppression | Normal | Closed | 2017-12-18 08:00 | 2017-12-22 17:00 |  | 2017-12-22 10:35 | 2017-12-22 10:35 |  | 2017-12-01 | Approved | 29.11.2017 12:54:24 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-12-18 09:00 | 2017-12-19 09:15 | 2017-11-28 12:04
CHG0030271 | DigiPlex Rosenholm AS | COWI planning of L2E | Normal | Closed | 2017-11-28 09:00 | 2017-11-28 16:00 |  | 2018-02-13 12:29 | 2017-12-01 09:28 |  |  | Approved | 28.11.2017 08:43:19 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-11-29 11:41 | 2017-12-01 07:53 | 2017-11-23 12:38
CHG0030263 | DigiPlex Norway AS | New link between chilled water rings in ground floor, 00COR02 | Emergency | Closed | 2017-11-23 08:00 | 2017-11-27 16:00 |  | 2017-12-15 09:23 | 2017-12-15 09:23 | Halvor Bjerke | 2017-12-15 | Approved | 22.11.2017 15:25:22 - galmquist (Approval history) Group approval for eCAB Approval approved by user Geir Almquist (CAB approval). | 2017-11-22 16:09 | 2017-12-06 07:14 | 2017-11-22 15:08
CHG0030255 | DigiPlex Rosenholm AS | 12M service on access control and CCTV | Normal | Closed | 2017-12-19 07:00 | 2017-12-20 17:00 |  | 2017-12-22 10:34 | 2017-12-22 10:34 |  | 2017-11-24 | Approved | 23.11.2017 11:05:19 - dobraekken (Approval history) Group approval for Change-Technical assess group approved by user Dag Oscar Brækken (Technical approvals norway). 21.11.2017 08:21:54 - galmquist (Approval history) Group approval for Change-Technical assess group approved by user Geir Almquist (Technical approvals norway). | 2017-12-19 09:48 | 2017-12-19 09:18 | 2017-11-20 15:12
CHG0030254 | DigiPlex Rosenholm AS | COWI 3D scan | Normal | Closed | 2017-11-21 07:00 | 2017-11-21 17:00 |  | 2018-02-13 12:29 | 2017-11-24 09:18 |  | 2017-11-24 | Approved | 20.11.2017 09:50:54 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-11-20 12:52 | 2017-11-23 11:50 | 2017-11-20 08:52
CHG0030252 | DigiPlex Rosenholm AS | 4M service of all CCU's | Normal | Closed | 2017-11-20 07:00 | 2017-12-01 16:00 |  | 2017-12-01 09:24 | 2017-12-01 09:24 |  | 2017-11-17 | Approved | 14.11.2017 11:02:37 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-11-17 09:19 | 2017-12-01 07:56 | 2017-11-13 09:01
CHG0030248 | DigiPlex Rosenholm AS | Pon Power replace defect water/fuel separator | Normal | Closed | 2017-11-13 08:00 | 2017-11-13 16:00 |  | 2017-11-17 10:37 | 2017-11-17 10:37 |  | 2017-11-17 | Approved | 09.11.2017 11:26:17 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals norway). | 2017-11-13 11:27 | 2017-11-17 08:33 | 2017-11-09 10:23
CHG0030246 | DigiPlex Norway AS | Forcepoint Email Cloud is protecting inbound email from malware and phishing. | Emergency | Closed | 2017-11-07 17:00 | 2017-11-07 18:00 |  | 2017-11-10 09:13 | 2017-11-10 09:13 |  | 2017-11-10 | Approved | 07.11.2017 17:58:22 - albjornstad (Approval history) Group approval for eCAB Approval approved by user Anders Lundin Bjørnstad (CAB approval). | 2017-11-07 17:00 | 2017-11-07 19:00 | 2017-11-07 17:39
CHG0030240 | DigiPlex Norway AS | Tuning of module after instalment of cold aisle containment. | Normal | Closed | 2018-01-14 08:00 | 2018-03-29 16:00 |  | 2018-10-25 08:10 | 2018-10-25 08:10 |  |  | Approved | 08.01.2018 10:55:43 - atorp (Approval history) Group approval for Change-Technical assess group approved by user Atle Torp (Technical approvals). | 2018-01-14 09:37 | 2018-10-17 09:38 | 2017-11-06 13:42
CHG0030239 | DigiPlex Rosenholm AS | Yearly full scale test of fire detection and gas suppression systems | Normal | Closed | 2017-12-08 07:00 | 2017-12-08 17:00 |  | 2017-12-15 09:16 | 2017-12-15 09:16 | Halvor Bjerke | 2017-12-15 | Approved | 15.11.2017 10:23:17 - pviken (Approval history) Group approval for CAB Approval approved by user Pål Rune Viken (CAB approval). 09.11.2017 12:57:28 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals). | 2017-12-08 09:42 | 2017-12-08 17:00 | 2017-11-06 12:45
CHG0030238 | DigiPlex Rosenholm AS | Minor service on gensets | Normal | Closed | 2017-12-11 07:00 | 2017-12-15 16:00 |  | 2017-12-15 09:15 | 2017-12-15 09:15 | Halvor Bjerke | 2017-11-17 | Approved | 09.11.2017 11:35:33 - fekay (Approval history) Group approval for Change-Technical assess group approved by user Frode Elden Kay (Technical approvals). | 2017-12-11 10:35 | 2017-12-14 09:02 | 2017-11-06 10:36
CHG0030233 | DigiPlex Norway AS | WiFi firmware upgrade DNAS & DRAS | Normal | Closed | 2017-10-30 17:00 | 2017-10-30 18:00 | Atle Torp | 2017-11-10 09:28 | 2017-11-10 09:28 |  | 2017-11-10 | Approved | 06.11.2017 11:48:09 - hbjerke (Approval history) Group approval for CAB Approval approved by user Halvor Bjerke (CAB approval). 03.11.2017 12:05:12 - fekay (Approval history) Group approval for Service Team NO approved by user Frode Elden Kay (Technical approvals). | 2017-10-30 17:00 | 2017-10-30 19:30 | 2017-11-03 10:40
CHG0030231 | DigiPlex Rosenholm AS | 12M service of Galaxy 7000 UPS | Normal | Closed | 2017-11-06 07:25 | 2017-11-10 16:26 |  | 2017-11-27 16:30 | 2017-11-17 10:40 |  | 2017-11-17 | Approved | 02.11.2017 08:50:32 - pviken (Approval history) Group approval for CAB Approval approved by user Pål Rune Viken (CAB approval). 31.10.2017 14:50:14 - fekay (Approval history) Group approval for Service Team NO approved by user Frode Elden Kay (Technical approvals). | 2017-11-05 11:06 | 2017-11-17 08:32 | 2017-10-31 14:30
CHG0030223 |  | Repair gen 4.2 after bad oil test results | Normal | Closed | 2017-10-30 08:00 | 2017-10-31 16:00 |  | 2017-11-03 12:47 | 2017-11-03 12:47 |  |  | Approved | 31.10.2017 14:25:58 - fekay (Approval history) Group approval for Service Team NO approved by user Frode Elden Kay (Technical approvals). 20.10.2017 12:33:50 - fekay (Approval history) Group approval for Service Team NO rejected by user Frode Elden Kay (Technical approvals). | 2017-11-03 10:13 | 2017-11-03 10:13 | 2017-10-18 14:02
CHG0030222 | DigiPlex Rosenholm AS | Disk replacement DRAS IBM SAN | Normal | Closed | 2017-10-19 10:00 | 2017-10-19 11:30 |  | 2018-01-19 17:19 | 2017-10-20 12:55 |  |  | Approved | 18.10.2017 10:30:56 - albjornstad (Approval history) Group approval for Service Team NO approved by user Anders Lundin Bjørnstad (Technical approvals). 18.10.2017 08:31:28 - albjornstad (Approval history) Group approval for Service Team NO rejected by user Anders Lundin Bjørnstad (Technical approvals). | 2017-10-19 08:38 | 2017-10-20 12:54 | 2017-10-17 23:13
CHG0030221 |  | Firmware upgrade DS1 guest network | Emergency | Closed | 2017-10-17 17:00 | 2017-10-17 18:00 |  | 2017-10-20 12:50 | 2017-10-20 12:48 |  | 2017-10-20 | Approved | 17.10.2017 16:21:37 - nnystrom (Approval history) Group approval for eCAB Approval approved by user Niclas Nyström (CAB approval). | 2017-10-17 17:00 | 2017-10-17 21:00 | 2017-10-17 16:10
CHG0030213 | DigiPlex Rosenholm AS | Yearly service of pipeworks | Normal | Closed | 2017-11-01 07:15 | 2017-11-07 19:00 |  | 2017-11-24 09:22 | 2017-11-24 09:22 |  | 2017-11-17 | Approved | 31.10.2017 13:01:15 - pviken (Approval history) Group approval for CAB Approval approved by user Pål Rune Viken (CAB approval). 31.10.2017 10:38:42 - fekay (Approval history) Group approval for Service Team NO approved by user Frode Elden Kay (Technical approvals). 27.10.2017 12:58:44 - pviken (Approval history) Group approval for CAB Approval rejected by user Pål Rune Viken (CAB approval). 25.10.2017 09:09:45 - fekay (Approval history) Group approval for Service Team NO approved by user Frode Elden Kay (Technical approvals). 17.10.2017 12:41:43 - fekay (Approval history) Group approval for Service Team NO approved by user Frode Elden Kay (Technical approvals). | 2017-11-03 12:41 | 2017-11-08 12:39 | 2017-10-17 12:29
CHG0030203 |  | Activate improved e-mail protection | Emergency | Closed | 2017-10-12 06:00 | 2017-10-12 06:30 |  | 2017-10-20 12:52 | 2017-10-20 12:52 |  |  | Approved | 12.10.2017 07:59:20 - nnystrom (Approval history) Group approval for CAB Approval approved by user Niclas Nyström (CAB approval). | 2017-10-18 10:16 | 2017-10-20 12:35 | 2017-10-11 17:45