## Clarifications-Observation
Sr. No. | Control Number | Control Activity | Clarification/ Findings details | Digiplex Responsible | Sites | Digiplex Management Response | Deloitte Comments | Status
1 | CA.06 | Digiplex management has established a Balanced Scorecard to reflect business objectives, structure and processes. | Evidence of balance scorecard is pending. | Steven | N/A | Steve update 30.11.2020 - this has not been undertaken Steven (18.12.20): "DigiPlex has being undergoing a Gartner process to take the game plan to the next level, the SLT have key members reviewing this to set 2021 objectives and beyond." | Received evidence of a review of this process. | Observation
2 | CA.18 | Appropriate fire detection & suppression systems are in implemented at data centres. Fire detection and suppression systems are covered under annual maintenance contract with respective vendors. | Evidence for testing the control was not provided | Geir | DNAS |  | Contract is from Honeywell. It is a common contract for DRAS and DNAS | Closed
3 | CA.19 | Fire detection and suppression systems are maintained as per the established maintenance schedule | Evidence for testing the control was not provided | Geir | DNAS |  |  | Closed
4 | CA.20 | Appropriate HVAC controls are in place to maintain heat, ventilation and air conditioning in the data centre. Temperature controls & monitoring is in place HVAC systems are covered under annual maintenance contract with respective vendors. | Evidence for testing the control was not provided | Geir | DNAS | Steve Update 04.12.2020 Schneider are the ones who do the technical maintenance (OEM Agent) on the chiller units Novaco clean filters | Contract with NOVACO is pending Update 04.12 - Steven to investigate for the Novaco contract. The maintenance was performed on 05 May 2020. We need the Schneider contract then and their maintenence report. UPDATE: HVAC maintenance reports received. | Observation
5 | CA.21 | HVAC systems are maintained as per the established maintenance schedule | Evidence for testing the control was not provided | Geir | DNAS |  |  | Closed
6 | CA.22 | Uninterrupted Power System (UPS) and DGs are installed at the primary and secondary data centre facilities to provide uninterrupted power supply and ensure backup whenever there are any power interruptions. UPS and DGs is covered under annual maintenance contract with respective vendors. | Evidence for testing the control was not provided | Geir | DNAS | Steve update 30.11.2020 -2) No, these are going to be decommissioned as part of our Powermigration-project before summer 2021. Service done based on PO's. 2 Pills UPS will be decommissioned in early December and the remaining UPS will be disconnected in February 2021. | Contract pending for UPS2 - Aktiv Power (Pillar Power systems) - Can you please confirm that Pillar Power systems contract was automatically renewed in 2020? DG - BOS tech/ Hedmark Services - we will be leveraging the contract evidence from 2019 audit for this. | Closed
7 | CA.23 | UPS and DGs are maintained as per the established maintenance schedule | There has been a delay in performance of the annual maintenance for the UPS and DG equipment Last Performed: October 2019 Next Scheduled: November 2020 | Christian Eghult | DS1 | Steve Update The Delay was caused by Covid-19 |  | Observation
8 | CA.23 | UPS and DGs are maintained as per the established maintenance schedule | Evidence for testing the control was not provided | Geir | DNAS |  | Maintenance reports pending for UPS1 - Schneider UPS 2 - Aktiv Power | Closed
9 | CA.25 | Closed Circuit Television (CCTV) systems are installed at strategic locations at the entry and exit points of the data centre facilities to record all the events. The CCTV systems are continuously monitored by the Physical Security team. The CCTV equipment is maintained on a regular basis. | Awaiting the maintenance report for 2020 which was scheduled to be performed in Sept/ October 2020. The last maintenance was performed on 24 September 2019. | Pete | DRAS DFAS | Steve update 02.12.2020 - SEE CA25 in DRAS folder | DRAS - Couldn't find it (the reports provided are from 24 september 2019) DFAS - The maintenance calendar for 2020 did not include the schedule for CCTVs and the report provided shows that the last maintenance was done 24.october 2019 Steven is chasing Atle Received Maintenance calender (DFAS) that states that CCTV maintenance was conducted November 2020 | Observation
10 | CA.28 | The access control and alarm systems are regularly maintained as per defined scheduled. | As the maintenance of the equipment is scheduled for December 2020 we requested for the last maintenance performed in Dec 2019 as evidence. However, we could not locate the evidence in the information shared with us. Request you to upload the information again. | Pete | DNAS DRAS | Steve update 02.12.2020 - SEE CA25 in DRAS folders Update 04.12.2020 Access Control is maintained by GK CCTV is currently maintained by NOKAS. The service was brought forward as part of our changing supplier to Stanley Security. moved the files to the correct folders. | DNAS - We have received the maintenance report from 2020. We understand that 2020's maintenance was performed on 04 Nov instead of the scheduled Dec 2020 routine. Also noted that the report was for Nokas, is that correct? Yes It was Nokas but it will move to Stanley. Steven to chase this. Who is responsible for doing the maintenance (is it Nokas or GK)? If GK, can we have the maintenance report from GK. DRAS - The last report I could locate was August 2019. Could not find the one for 2020. UPDATE: DRAS reports from 2020 received. | Observation
11 | CA.31 | Digiplex has processes in place to periodically review physical access to ensure consistency with job responsibilities. | 1. The SOP document for user access review was found corrupt. Request you to reshare the file. 2. The evidence provided for user access review did not detail how the review was performed. We request you to walk us through the documents and help us with our queries | Pete | N/A |  | Point #1 - Closed Point #2 - We understand the user access review report provided to us covered a review of all Digiplex users performed by Yngve Urdal and closed by Pete O'Sullivan. Kindly confirm and add to our understanding for us to close this point. Sid to drop an email to Pete and ask your questions | Closed
12 | CA.34 | Entry and exit details of the visitors accessing the data centre facilities are logged and documented. Access to visitors is granted only after obtaining appropriate approvals from designated personnel in the management All visitors must be escorted by an authorized personnel while on the premises. | Visitor register for DRAS was not available for our review. | Pete | DRAS | Steve- update 30.11.2020 the individuals listed as callers are requestors for a visitor and are not approvers. Once a request has been made the designated approver in the work flow approves the visitor | Please confirm if all the following users/ ids are authorized to approve visitor requests as they are listed as 'Callers' in the Service Now extract: Hadi Issa Security DS1 Kristin Ohnstad Jon Johansson Christian Eghult Ola Fall Maria Lindström Security DFAS Khurram Makhdumi Robin Osterman Befor Kjetil Nordahl Dag Oscar Brækken Niklas Karlsson Erik Liif Moises Isenia Patrik Sjoberg John Ditmeyer Bo Hihldor Catalin Peter Jahrl Thomas Roloff | Closed
13 | CA.34 | Entry and exit details of the visitors accessing the data centre facilities are logged and documented. Access to visitors is granted only after obtaining appropriate approvals from designated personnel in the management All visitors must be escorted by an authorized personnel while on the premises. | Request you to walk us through the evidence of visitor registers for other 3 sites. | Pete | DNAS DFAS DS1 |  |  | Closed
14 | CA.35 | Movements of materials within the data centre is monitored and tracked, logged and only permitted with proper authorization | Evidence for testing the control was not provided | Pete | All four locations | Steve update- Please see Goods Handling procedure for all sites |  | Closed
15 | CA.42 | Digiplex has established and documented a change management process which is approved by the as per the change policy. Changes are raised, classified, tracked and approved in Service Now ticketing system. | Two out of 16 sample changes did not have two separate approvers as described in the policy. Sample Tickets: CHG0031652 CHG0031841 | Karl Audun Lad | N/A | Steven (18.12.20): "The two changes where emergency changes – our process is that this gets approved by the CAB retrospectively – The IT Director is in the CAB hence why his name appears twice." |  | Observation
16 | CA.30 | Access to data centre facilities is revoked on the last working day of resigned/terminated employee. Customer access is revoked based on intimation from authorized customer personnel through ticket in Service Now. | For the list provided by HR for Digiplex employees who resigned during the audit period, we identified that the list might have captured information of the location of employees incorrectly. Sample Details: 1. Daniel Drangsholt was listed as an employee working out of DNAS however on inspection of evidence we understand that he had access to DS1 and not DNAS. 2. Similar is the case for Nils Christensen. | Olga | N/A | Hiring location and assignment location maybe different based on the employee contract. Steve update- Hiring is Site Specfic as each Datacenter is a business in it own right In relation to Daniel and Nils - they were based at DNAS -Extentsion of DNAS is Building 82 our Head Office in addtion DS1 also has a DigiPlex Office for our Swedish Colleagues. Unlike DRAS, DFAS which donot hold DigiPlex offices |  | Closed
17 | CA.30 | Access to data centre facilities is revoked on the last working day of resigned/terminated employee. Customer access is revoked based on intimation from authorized customer personnel through ticket in Service Now. | For one out seven resigned employees, a delay in revocation of access to data center was noted. Sample Details: Name: Christopher Gordon Rees LWD: 25.02.2020 Location: DFAS Access Revoked on: 03.03.2020 Delay in Revocation: 7 days | Pete/ Steven | DFAS | Steve Update - The time delay was caused due to setting up the process following receieving the audit report in mid January 2020. This was the first run at the process Steven (18.12.20): "The request was processed the same day as it was put onto the system – the delay was getting onto the system which the date shows in Request RED0013739 attached" |  | Observation

## Extract from the RFI
Control Number | Control Activity # | Requirements | Status | Responsible | Location | Digiplex Comments | Deloitte Comments
CA.06 | Digiplex management has established a Balanced Scorecard to reflect business objectives, structure and processes. | 1. Screenshot of balance scorecard 2. Document explaining the KPI's included in the scorecard (to see if it reflects business objectives, structure and processes) 3. Objective Target Setting & Review | Partially reveived | Steven |  | 1. Digiplex uses a Game plan for our balanced scorecard approach see CA 6 2 Process uploaded | Missing per 23.10.2020: Evidence of balanced scorecard performed
CA.31 | Digiplex has processes in place to periodically review physical access to ensure consistency with job responsibilities. | 1. User access review process document/ SOP 2. Evidnece to demonstrate that user access review was performed as per periodicity for the year 2020 - List of Access Cards | Partially received | Pete | Common |  | User access review process document/ SOP is corrupt (just demands Adobe) Please resend file. Evidence of review performed is not detailed to determine how the review was performed, for which users, for which site.
CA.34 | Entry and exit details of the visitors accessing the data centre facilities are logged and documented. Access to visitors is granted only after obtaining appropriate approvals from designated personnel in the management All visitors must be escorted by an authorized personnel while on the premises. | 1. Visitor access policy 2. Vendor access policy 3. List of vendor users who are authorized to access data centre for maintenance purposes (from the access control system) You can also provide a complete list of users from the access control system with their classification (vendor, customer, DigiPlex employee, etc. ) and we can select samples from it accordingly. 4. Visitor register for the year 2020 Samples for visitors and vendors to be selected after receipt of the population | Partially received | Pete | All four locations |  | Visitor register for DRAS is not available. Descrepancies in the visitor register for other sites.
CA.23 | UPS and DGs are maintained as per the established maintenance schedule | 1. Preventive maintenance schedule and preventive maintenance reports for the year 2020 | Partially received |  | DS1 | UPS - Maintenance report for 2019 uploaded. 2020 booked for week 46. Generator service reports for 2020 uploaded. CA21 HVAC) will be done next week. CA23 (UPS) will be done 9-15 november. - Christian Eghult 26.10.2020 | Last maintenance was performed October 2019. This years maintenance confirmed by Christian.
CA.25 | Closed Circuit Television (CCTV) systems are installed at strategic locations at the entry and exit points of the data centre facilities to record all the events. The CCTV systems are continuously monitored by the Physical Security team. The CCTV equipment is maintained on a regular basis. | To be inspected on site 2. Maintenance reports and contract for CCTV | Partially received | Pete | DRAS | Service report from 2019 uploaded. | Last maintenance of CCTV was performed 24.09.2019.
CA.25 | Closed Circuit Television (CCTV) systems are installed at strategic locations at the entry and exit points of the data centre facilities to record all the events. The CCTV systems are continuously monitored by the Physical Security team. The CCTV equipment is maintained on a regular basis. | To be inspected on site 2. Maintenance reports and contract for CCTV | Partially received |  | DFAS | Service report from 2019 uploaded. | Last maintenance of CCTV was performed 24.10.2019.
CA.28 | The access control and alarm systems are regularly maintained as per defined scheduled. | 1. Copy of the annual maintenance contract with vendor/ service provider - GK Contract - Nokas Invoice 2. Preventive maintenance schedule and preventive maintenance reports for the year 2020 3. Test results for mock tests performed on the alarm system during the year 2020 | Partially received | Pete | DNAS | Security Systems annual mainteneace is scheduled for Dec 2020. DEC 2019 service report is available | Cant find maintenance from DEC 2019 for DNAS
CA.28 | The access control and alarm systems are regularly maintained as per defined scheduled. | 1. Copy of the annual maintenance contract with vendor/ service provider - Stanley security contract 2. Preventive maintenance schedule and preventive maintenance reports for the year 2020 3. Test results for mock tests performed on the alarm system during the year 2020 | Partially received | Pete | DRAS | From Pete: CCTV and Access Control System PPM visits are scheduled for December each year. The most recent service visits for DNAS,DRAS,DRAS and DS1 took place in December 2019. Those records have been uploaded to the relevant CA28 folder for each site. | Cant find maintenance from DEC 2019 for DRAS
CA.42 | Digiplex has established and documented a change management process which is approved by the ‘Transformation Director’. Changes are raised, classified, tracked and approved in Service Now ticketing system. | 1. Change management policy 2. List of changes during 2020 for all 4 locations 3. Sample changes to be selected and ServiceNow tickets will be asked later Samples selection: - CHG0031884 - CHG0031053 - CHG0031652 - CHG0031847 - CHG0031638 - CHG0031716 - CHG0031841 - CHG0031982 - CHG0031782 - CHG0031625 - CHG0031627 - CHG0031852 - CHG0031916 - CHG0031949 - CHG0031837 - CHG0031882 | Ready for review |  | Steve |  | Missing per 26.19.2020: Missing an answer on request to Karl Audun Lad for CHG0031652 Exception: 14 of 16 change tickets followed the procedure in the policy.
CA.35 | Movements of materials within the data centre is monitored and tracked, logged and only permitted with proper authorization | 1. SOP/ Procedure document describe the process of movement of materials 2. Goods Movement register for the year 2020 | Pending | Pete | All four locations |  | Missing per 19.10.2020: - SOP/Procedure document describe the process of movement of materials - Goods movement register for the review period (1.1.2020 - 31.10.2020)
CA.18 | Appropriate fire detection & suppression systems are in implemented at data centres. Fire detection and suppression systems are covered under annual maintenance contract with respective vendors. | 1. Details about fire suppression and fire detection system installed (type, make, model, warranty, etc. ) 2. Copy of the annual maintenance contract with vendor/ service provider - Fire detection - Fire suppression (Same as DRAS) | Pending | Geir | DNAS
CA.19 | Fire detection and suppression systems are maintained as per the established maintenance schedule | 1. Preventive maintenance schedule and preventive maintenance reports for the year 2020 - Fire detection - Fire suppression | Pending | Geir | DNAS
CA.20 | Appropriate HVAC controls are in place to maintain heat, ventilation and air conditioning in the data centre. Temperature controls & monitoring is in place HVAC systems are covered under annual maintenance contract with respective vendors. | 1. Details about HVAC system/s installed (type, make, model, warranty, etc. ) 2. Copy of the annual maintenance contract with vendor/ service provider | Pending | Geir | DNAS
CA.21 | HVAC systems are maintained as per the established maintenance schedule | 1. Preventive maintenance schedule and preventive maintenance reports for the year 2020 for HVAC systems | Pending | Geir | DNAS
CA.22 | Uninterrupted Power System (UPS) and DGs are installed at the primary and secondary data centre facilities to provide uninterrupted power supply and ensure backup whenever there are any power interruptions. UPS and DGs is covered under annual maintenance contract with respective vendors. | 1. Details about UPS and DG system/s installed (type, make, model, warranty, etc. ) 2. Copy of the annual maintenance contract with vendor/ service provider - UPS - DG | Pending | Geir | DNAS
CA.23 | UPS and DGs are maintained as per the established maintenance schedule | 1. Preventive maintenance schedule and preventive maintenance reports for UPS and DG the review period (1.1.2020 to 31.10.2020) | Pending | Geir | DNAS